## Faciilty1
Area for improvement:Standard- 1.1 The building is in good physical condition
Strategy: 1 | Making the building disability friendly | Start Date | End Date | Responsible members (persons have been de-identified) | Budget | Status | New Deadline (add date of entering) | Explanation for not meeting the deadline | Proposed Plan for meeting new deadline
Activity 1 | Meeting the PIU to discuss the blue prints of the new OPD construction and including him in all the discussion for standard 1.1 | 6 February'15 | 12 March'15 |  |  | Completed
Activity 2 | Mapping of the facility for disability friendly environment | 3 May'15 | 6 June'15 |  |  | Completed
Activity 3 | Making a list of new requirements and list of repairs, and following up for changes with the PIU with the intention to make the area user friendly | May' 15 | June'15 |  |  | Completed
Activity 4 | Sharing the list of repairs and new requirements as well as the mapping of the facility with the PIU and hospital head | May' 2015 | June' 2015 |  |  | Pending
Activity 5 | Signage mapping : A board at the entrance, directing to the area where the wheel chair will be available- Bi-lingual | May' 2015 | July'2015 |  |  | Pending
Activity 6 | Checking the number of wheel chair in every ward, and getting 1 allotted per ward | May' 2015 | June' 2015 |  |  | Completed
Activity 7 | A disability frienly toilet for person with other forms of disabilities- meeting the PIU for the same | May' 2015 | July' 2015 |  |  | Completed | Feb
Activity 8 | Making a list of items in the ward that are disabled friendly | May'2015 | 5 June' 2015 |  |  | Completed | August
Activity 9 | After making the list, listing the other items that are needed but not available. Making them available in the ward | May'2015 | 8 June'2015 |  |  | Completed
Activity 10 | Monitoring of disabled friendly items to check if they need repair | May' 2015 | 8 June' 2015 |  |  | Completed/ Ongoing
Strategy: 2 | Providing assistance to users soiling on the bed | Start Date | End Date | Responsible Person | Budget | Status
Activity 1 | Users soiling and urinating on the bed will be provided Mackintosh, except for those who are elderly to avoid bed sores | May' 2015 | July' 2015 |  |  | Completed
Activity 2 | Toilet training to be provided, for those who are unable to move, staff to attend those who are unable to walk is necessary | May' 2015 | 16 July' 2015 |  |  | Completed and on-going
Activity 3 | Training of staff to use bed pan and other form of assistance | 1 June' 2015 | 1 July' 2015 |  |  | Completed and on-going
Activity 4 | A monitoring format of users every week after toilet training has started by the attendant staff and nursing staff will be done, so that their bed with macantors can be changed once they stop soiling. | 1 June' 2015 | 1 July' 2015 |  |  | on-going
Activity 5 | Monitorng done by persons responsible on a regular basis | 1 June' 2015 | 1 July' 2015 |  |  | on-going
Activity 6 | Champions start giving this training in batches from 23rd to 28th | 23 June' 2015 | 28 June' 2015 |  |  | on-going
Activity 7 a(New) | Training of sanitation and hygeine for the service users of all the wards | 3rd March, 2016 |  |  |  | Completed/ ongoing
Activity 7b (New) | Monitoring to be done on the improvement of the service users | 10th March, 2015 |  |  |  | Completed / ongoing
Strategy: 3 | Modifying and Improving the inquiry system in the facility | Start Date | End Date | Responsible members | Budget | Status
Activity 1 | Inquiry area to be placed before the case writer’s cabin and this change to be included in the new infrastructure of the OPD (Sharing with PIU) | 2 March' 2015 |  |  |  | Completed
Activity 2 | Information brochers and pamplets to be made available on the inquiry desk | July' 2015 |  |  |  | Pending | 2016-03-18
Activity 3 | A small study to be conducted - registering all inquiries that come to the table for a period of one month | 10 February' 2015 | 1 March' 2015 |  |  | Completed
Activity 4 | Clustering the areas of inquiry to find themes on which pamplet and information will be designed | 9 March' 2015 | 12 March' 2015 |  |  | Completed
Activity 5 | Working on Module for training the person on the inquiry based on themes coming out from the study | June' 2015 | July' 2015 |  |  | Activity Removed with the alternative which is completed
Activity 6 | Knowledge Consortium on areas of knowledge the users and caregivers may require will be develop- like an information online bank | August' 2015 |  |  |  | Pending | Long term plan, will be taken up next year
Strategy: 4 | Improvement in Safety fire measures | Start Date | End Date | Responsible members | Budget | Status
Activity 1 | Reviewing the fire exit policy by the core committee and identifying the process measures that are not happening | 5 March' 2015 |  |  |  | Pending | 2016-03-18
Activity 2 | Training, instead of demonstartions to be done for all the staff and Users : | March' 2015 |  |  |  | In-progress
| Training calender needs to planned so that all the staff are trained -Training to be conducted every three months | New |  |  |  | Pending | 2016-03-21
| Evacuation mock drills with the users, need to be planned | December |  |  |  | Pending | Will be planned on 21st March with the calender
Activity 3 | Smoke detectors will be placed in every ward- Meeting for PIU and Head of the facility for general ward and OPD | 2nd march, 2015 |  |  |  | Pending | Long term plan, will be taken up next year
Activity 4 | Contacting fire department at xxx for mock drills | May'2015 |  |  |  | Completed
Strategy: 5 | Addressing Leakage and Ventilation | Start Date | End Date | Responsible members | Budget | Remark
Activity 1 | Foot- ball (of a water tank) needs to be put in the tanks | 10 Feb' 2015 | 12 Feb' 2015 |  |  | Completed
Activity 2 | Areas causing leakage have to be identified at the time of disability mapping and listed down | 3 May' 2015 | 3 June' 2015 |  |  | Completed
Activity 2 | Areas causing leakage need repairs, which had to be conveyed to the PIU | June' 2015 | June' 2015 |  |  | Completed
Activity 3 | Rain water harvesting and solar panels to be installed | August' 2015 |  |  |  | Pending | Long term plan, will be taken up next year
Activity 4 | Mosquito nets to be installed like civil hospital | August' 2015 |  |  | This years difficulty in allocating budget for the activity | Pending | Long term plan, will be taken up next year
Activity 5 | Monitoring and cleaning of the existing exhaust fans | June' 2015 |  |  |  | Completed/ Ongoing | Needs a follow-up with the person responsible
Activity 6 | Cover the exhaust fans with thin nets to save them from birds and their eggs: Informing the PIU / Head of the house keeping | June' 2015 |  |  |  | Pending
Activity 7 | Installation of big exhaust fan/ Coolers in the wards | June' 2015 |  |  |  | Completed/ Ongoing | Discuss the alternatives/ Coolers
Activity 8 | Putting door frames with nets | June' 2015 |  |  |  | Pending
Activity 9 | Meeting the PIU for the same | June' 2015 |  |  |  | Completed
Strategy:6 | Approaching the Donar and Funders for making provisions for infrastructural material | Start Date | End Date | Responsible members | Budget | Remark
Activity 1 | Making a list of basic and big requirements of the facility | Arpil' 2015 |  |  | Budget | Completed
Activity 2 | Approaching the donors for them | Arpil' 2015 |  |  |  | Completed/ Ongoing
Strategy:7 | Increase of basic requirements for user- working on individual belongings | Start Date | End Date | Responsible members | Budget | Remark
Clothing and towels
Activity 1 | 1 towel per user | June' 2015 |  |  |  | Ongoing | Check Status
Activity 2 a | Tooth brushes for all users. They will be given to the user to take home at the time of discharge. | June' 2015 |  |  |  | Ongoing
| They can be stored in a new cupboard that has to be made and distribution of them can be done every morning similar to the distribution of medicines. | June' 2015 |  |  |  | Pending
| Dr. meets with the caregivers to address the following above issues of clothes/ towels and tooth brush | 11th Aug'15 |  |  |  | Completed
| All the caregivers are informed that they will bring 2 set of clothes, tooth brush and towel at the time of admission | 11th Aug'15 |  |  |  | Completed
| Circular for caregivers needs to be sent out in order to inform them to bring their clothes towel and toothbrush for the users at the time of admission. | August |  |  |  | Completed | August
Activity 2 b | Tagging and identification of clothes brought by inpatient users:
| Making marks/ tags for the identification of clothes. The tags will have the name embroidered of the user and these tags will be sewed on the clothes brought by the users from their homes. |  |  |  |  | Completed/ Ongoing | December
| This is being done for identification. Tagging of clothes will be done by a group of service users from the OT. The process will be done once the user has been admitted. |  |  |  |  | Completed/ Ongoing | December
| These group of patients need to undergo training by the attendant staff/ linen keeper. |  |  |  |  | Completed/ Ongoing | December
Statergy 8 | Bowls instead of dishes should be arranged instead of serving tea in plates
Activity 1 | It has been discussed that Tea cup and snacks plate will be provided to the patients who will be collected by donation | August | September |  |  | Completed | September
Activity 2 | After their procurement users will be involved in an activity in which they will paint the cup or mark the cup with different colors for ward wise identification. | August | September |  |  | Completed | December
Activity 3 | All the users will also be trained to use their tea cups and plates and wash them themselves post the use, so that they get use to doing their work by themselves when they go home | August | September |  |  | Completed | December
Activity 4 | The users will be trained and material required for cleaning the cups will be provided to them by the hospitals. This will be done as a pilot project starting with the chronic ward. | August | September |  |  | Completed | December
Activity 5 | Monitoring mehanism for esuring the 5th activity is in process - checks in 15 days | August | September |  |  | Completed | December
Completed
Activity 9 | Maintaining Sanitation and Hygeine
Activity 1 | Monitoring the quality of the house keeping material every 3 months | June' 2015 |  |  |  | Completed
| A list of house keeping material will be submitted by Mr Yogesh (House keeping head) and this check list will be used to provide feedback on a monthly basis. | New 1st April, 2016 |  |  |  | Pending
Activity 2 | Planning a training calender for House keeping staff on hygeine and sanitation | September'15 |  |  |  | Completed | 15th March 2016
Strategy: 8 | Areas of repairs | Start Date | End Date | Responsible members | Budget | Remark
Activity 1 | Flush facility should be installed and corrected in every toilet. New flushes should be installed so that leakage of water can be controlled. | June' 2015 |  |  |  | Completed | November
Activity 2 | • Water drainage system needs repair | June' 2015 |  |  |  | Completed/ Ongoing
Activity 3 | • Gutter lines needs repair | June' 2015 |  |  |  | In-progress | November
Strategy: 9 | Making areas prominent and revamping | Start Date | End Date | Responsible Person | Budget | Remark
Activity 1 | . The area should be selected keeping in mind the visibility. | July' 2015 |  |  |  | Completed
| Signages for water cooler should be made | July' 2015 |  |  |  | Completed
Activity 2 | · Signage directing towards the Occupational therapy unit and the workshops will be placed for directions and visibility | July' 2015 |  |  |  | Completed
Area for improvement: 1.3: Facility meets hygiene and sanitary requirements
Strategy: 1 | Increasing material, monitoring its use and allocating human resources | Start Date | End Date | Responsible members | Budget | Remark
Activity 1 | Allocating Human resources only for cleaning bathroom: 1 sweeping staff for only cleaning the bathroom per ward | June' 2015 |  |  |  | Completed/ Ongoing | August- November
Activity 2 | Cleaning material will be approved before being used instead of direct usage in the facility for assuring “quality cleaning material” | June' 2015 |  |  |  | Completed/ Ongoing | September
Activity 3 | A protocol needs to be developed for appropriate disposing of cleaning material, utilization of cleaning material, hazardous material and bio medical waste were raise | June' 2015 |  |  |  | Completed/ Ongoing
Activity 4 | A committee of cleanliness quality control will be made for monitoring and making superize visits | June' 2015 |  |  |  | Completed/ Ongoing | Completed
Activity 5 | This team will make a report and identify issues and meet with the head of house keeping to discuss improvement once a month: alloting a date to the calender needed | June' 2015 |  |  |  | Pending
Activity 6 | Cleanliness Quality Control Committee responsible to address the grievances of the sweeping staff and the sisters in charge of each ward on cleaning issues (Process needs planning) | June' 2015 |  |  |  | Pending | November
Activity 7 | checklist for maintaining of the schedule of cleaning will be prepared | June' 2015 |  |  |  | Completed/ Ongoing | September
Activity 8 | Nursing incharge will use this check list to supervise | June' 2015 |  |  |  | Completed/ Ongoing | September
Stratergy 2 | Training for hygiene and sanitation and Monitoring | Start Date | End Date | Responsible members | Budget | Remark
Activity 1 | Trainings should be done by housekeeping head with the presence of the nursing incharges(as it will help them supervising) and the quality control team on use of these cleaning equipments | July' 2015 |  |  |  | Completed | 2016-03-15
| - Use of hazardous material - Use of personal productive equipments - Training to address spillage | July' 2015 |  |  |  | Completed | 2016-03-15
Activity 2 | Planning a calender for the training |  |  |  |  | Completed | 2016-03-15
Activity 3 | Creating a monitoring body to check hygeine and sanitation | July' 2015 |  |  |  | Completed
Activity 4 | Creating teams within wards to maintain cleaning | July' 2015 |  |  |  | Pending
Activity 5 | Inter ward competition on cleaning | July' 2015 |  |  |  | Pending
Strategy: 3 | Increase in infrastructure for Hygiene | Start Date | End Date | Responsible members | Budget | Remark
Activity 1 | • Number of toilets to be increased | July' 2015 |  |  |  | Completed
Activity 2 | • Lockers that can be opened from outside needs to be installed in all toilets | July' 2015 |  |  |  | Pending | In discussion with Dr.
Activity 3 | • Male toilets should have urinals and female- dustbins | July' 2015 |  |  |  | Completed
Activity 4 | • All toilets should have wall mount soap dispensers | July' 2015 |  |  |  | Completed/ On-going
Activity 5 | • Sinages for seperate toilet for male and female in general wards, keeping in mind that the caregivers of opposite sex may be staying | July' 2015 |  |  |  | Completed | August
Activity 6 | • Railway type taps (meaning availability of pressing taps) | July' 2015 |  |  |  | Completed
Activity 7 | • Adequate buckets and tumblers made available | July' 2015 |  |  |  | Completed | NOV
Activity 8 | • Cloth chamber to change clothes in the bathroom : Need of use of them- pending | July' 2015 |  |  |  | Pending | Long term plan, will be taken up next year
Area of improvement : | 1.4 Service users are given food, safe drinking-water and clothing that meet their needs and preferences
Stratergy 1 | Kitchen Activity | Start Date | End Date | Responsible Person | Budget | Status
Activity 2 | Developing a team that volunteers to guide the cooking staff to made health and hygienic food | 7 April'2015 |  |  |  | Completed/ In progress
Activity 3 | After the team is identified the team be divided into teams of 3 to go to the kitchen and guide the cook in making food (1 team - 2 days) | 18 April'2015 |  |  |  | Completed/ In progress | August- September
| Name of the memnbers of the weekly team |  |  |  |  | Completed/ In progress | September
Activity 4 | A register in which the team can note their comments will be made | 20 May'2015 | 7 April'2015 |  |  | Completed/ In progress
Activity 5 | improving the menue with the same team | 26 April'2015 | 18 April'2015 |  |  | Completed/ In progress
| Medical Check up for the staff cooking or helping in cooking is needed |  | New addition |  |  | Completed/ In progress | September
Acitivity 6 | Reviewing the same menue by the administrative department | 26 April'2015 |  |  |  | Completed/ In progress
Activity 7 | Giving time to the admin department to review it and make comments if changes are requires | April'2015 |  |  |  | Completed/ In progress
Activity 8 | Finalizing the menue once the administrative department agreess | 15 April' 2015 |  |  |  | Completed/ In progress
Activity 9 | Doing audit of the raw material | April'2015 | 30 April'2015 |  |  | Completed
Activity 10 | Planning monthly audits of raw material | April'2015 |  |  |  | Completed
Stratergy 2 | Sanitation and Hygiene of the kitchen
Activity 1 | Developing a check list for the inpection of hygiene and sanitation | 18 May'2015 |  |  |  | Completed
Activity 2 | Checklist send for review and to add comments | June'2015 |  |  |  | Completed
Activity 3 | Finalising the monthly and weekly inspection | May' 2015 | 15 June' 2015 |  |  | Completed | 8th Jan
Activity 4 | Finalising the committee members for the inspections weekly inspections | May'2015 | 25 May' 2015 |  |  | Completed
Stratergy 2 | Repair centre for clothes | Start Date | End Date | Responsible Person | Budget | Status
Activity 1 | A repair centre will start in which users will be trained by the tailoring instructor | June' 2015 |  |  |  | Completed | September
Activity 2 | Tailoring instructor will train this group of 3 users to do minor and major repairs | June' 2015 |  |  |  | Completed
Activity 3 | These trained users will train another bunch of users | May' 2015 |  |  |  | Completed
Activity 4 | A monitors systems will be set in which clothes will be repaired and dispensed in 6 days of repair so that the cycle continues, a register will be maintained for the same | May' 2015 |  |  |  | Completed
Activity 5 | Tailoring in-patient facility near a room near ECT will to begin | New activity |  |  |  | Completed | September
Activity 5 a | Linen keeper- Mr. Siddhart will be shifted within the Inpatient facility to guide the process. | New activity |  |  |  | Completed | September
Stratergy 3 | Coffee dispensing machine and canteen | Start Date | End Date | Responsible Person | Budget | Status | Began but stopped becuase of certain barriers
Activity 1 | Coffee dispensing machine will be installed in the OPD area | August' 2015 |  |  |  | Pending | Currently working on the barriers
Activity 2 | Two- three users will be trained to run it | August' 2015 |  |  |  | Pending | Long term plan
Activity 3 | The users will be paid an honorarium for running the same | August' 2015 |  |  |  | Pending
Activity 4 | Users will be trained in the OT department | August' 2015 |  |  |  | Pending
(a) | Rohni Sagai- A canteen run by the users will also be started | August' 2015 |  |  |  | Pending
Area for improvement: Standard 2.2: The facility has skilled staff and provides good-quality mental health services.
Strategy: 1 | ADL training | Start Date | End Date | Responsible members | Budget | Status | December
Activity 1 | Training of Nursing staff and attendant staff to provide ADL training | May' 2015 | June' 2015 |  |  | Completed/ On-going
Activity 2 | It will be a ward based activity | May' 2015 | June' 2015 |  |  | Completed/ On-going
Activity 3 | All the nursing staff will be asked to do make a list of PWMI who need ADL training | May' 2015 |  |  |  | Completed/ On-going
Activity 4 | The staff will be doing a ADL assessment of those identified | May' 2015 | May' 2015 |  |  | Completed/ On-going
Activity 5 | The training will be provided by the nursing staff to the attendant staff. A group of nursing staff will provide the training to attendant and the staff. | June' 2015 | 10 June' 2015 |  |  | Completed/ On-going
Activity 6 | ADL assessment check /list needs to be made (Adaptation of NIMHANS) | 15 May' 2015 | 20 June' 2015 |  |  | Completed/ On-going
Activity 7 | After making the check list of screening ADL, a list of those having : Mild moderate and severe level of disability will be made | May' 2015 | 15 June' 2015 |  |  | Completed/ On-going
Activity 8 | ADL training will be provided to the staff nursing, attendant staff | May' 2015 | May' 2015 |  |  | Completed/ On-going
Activity 8 | The teams of staff will start working with the users who are at the mild level. The intention behind it is to train them to improve their ADL' s so that they can become " BUDDY Supporters" to other users who are at the moderate and severe level and join the team of staff in the same. | June' 2015 | July' 2015 |  |  | Completed/ On-going
Activity 8 a | Once the training has been provided 15-20 users beginning from the chronic ward will be trained for development of their ADL skills under one attendant. |  |  |  |  | Completed/ On-going
Activity 8 b | Each psychiatrist will review the process and improvement in the patient every 15 days.Each psychiatrist will have approx. 40 users to monitor | New addition |  |  |  | Completed/ On-going
Activity 9 | Buddy supporters will be trained along with the team of staff being training | July' 2015 | August' 2015 |  |  | Completed/ On-going
Activity 10 | Supervision and Monitoring team will be done for to check whether the skill training is given to the users in the wards | August' 2015 |  |  |  | Completed/ On-going
Activity 11 | Supervision and Monitoring of the psychiatist | New addition |  |  |  | Pending
Activity 12 | Making a protocol for the nursing student staff to be doing ADL activities as a part of their requirement of placement. | New addition |  |  |  | Pending
Statergy : 2 | Toilet and Life Skills training | Start Date | End Date | Responsible members | Budget | Status
Activity 1 | Training of nursing staff and attendant staff to provide toilet training and life skills training to users | August' 2015 |  |  |  | On-going/ Completed | March
Activity 2 | Developing a list of users from each ward that need toilet training, | July' 2015 |  |  |  | On-going/ Completed
Activity 3 | Team of attendant and nursing staff providing toilet training and life skills training to the users | August' 2015 |  |  |  | On-going/ Completed | March
Activity 4 | Supervion of these toilet training | August' 2015 |  |  |  | On-going/ Completed | March
Stratergy 3 | Sensitization and Psychological first aid training of the security guards | Start Date | End Date | Responsible members | Budget | Status
Activity 1 | Preparing content for trainings | 15 May' 2015 | 30 May' 2015 |  |  | Completed
Activity 2 | Preparing the skits and Actrivities | 15 May' 2015 | 26 May' 2015 |  |  | Completed
Activity 3 | Practicing for the training | 26 May' 2015 | 30 May' 2015 |  |  | Completed
Activity 4 | Making batches of the guards for the training | 26 May' 2015 | 30 May' 2015 |  |  | Completed
Activity 5 | Giving of training | 29 May' 2015 | 29 June' 2015 |  |  | Completed
Stratergy 4 | Basic Training on mental disorders for all the staff | Start Date | End Date | Responsible members | Budget | Status
Activity 1 | Content of training | July' 2015 |  |  |  | Pending
Activity 2 | Attend training in Mehsara, create master trainers | August' 2015 |  |  |  | Pending
Activity 3 | Master trainers will provide training | August' 2015 |  |  |  | Pending
Strategy:5 | Alloting duties and defining roles of the staff | Start Date | End Date | Responsible members | Budget | Remark
Activity 1 | Getting the daily activity schedule of the nursing and attendant staff in order to identify free/ time with less pressure time to engage them | 11 February' 2015 | 13 February' 2015 |  |  | Pending
Activity 2 | Analysing the time schedule and deciding the time and activities that can be allotted form the improvement plans | March' 2015 |  |  |  | Completed
Activity 3 | Training of the new staff, before they join on their job role on Human Rights, Recovery oriented care and Alternatives to Seclusion and Restraint and Effective Communication Skills | 8 June' 2015 | 30 June' 2015 |  |  | Completed
Activity 4 | Allotment of work according to skills, education and interest on rehabilitation among the staff | 8 June' 2015 | 30 June' 2015 |  |  | Completed
Activity 5 | Feedback by staff will be taken | 30 June' 2015 |  |  |  | Completed
Activity 6 | Job specific roles need to be defined and staff will be oriented | 30 June' 2015 |  |  |  | Completed
Activity 7 | Supervisor to be given to fresh recruits : nursing, attendant and sweeping staff | August' 2015 |  |  |  | Pending
Activity 8 | Defining the role of supervisors | August' 2015 |  |  |  | Pending
Strategy: 6 | Follow up services by psychiatrist and medical officers | Start Date | End Date | Responsible members | Budget | Completed
Stratergy 7 | Trainings on human rights of the staff so that they can provide information to the users | Start Date | End Date | Responsible members | Budget | Status
Activity 1 | Providing information to about human rights to the users in written form in the form of Citizen Charter on display | August' 2015 |  |  |  | On-going
Activity 2 | The knowledge on human rights will be added behind the OPD medicine card | August' 2015 |  |  |  | On-going
Activity 3 | Information in various committee available on citizen charter | August' 2015 |  |  |  | On-going
Strategy: 8 | Step by step refining the process of meeting the user and caregiver to take the case history | Start Date | End Date | Responsible members | Budget | Status
Activity 1 | Working on a new case form | new Activity - december | january |  |  | in-progress
Activity 1 a | Taking the case history and details with the user with the caregiver together | September' 2015 |  |  |  | Pending
Activity 2 | Taking details without the caregiver | September' 2015 |  |  |  | Pending
Activity 3 | Talking to the caregiver | September' 2015 |  |  |  | Pending
Activity 4 | Training the professionals to ask about sensitive areas example: asking a women about reproductive health and private part issue | September' 2015 |  |  |  | Pending | April - 1st week
Activity 5 | Making a list of questions to be asked for sensitive issues and not assuming that they will tell -- For all professionals | September' 2015 |  |  |  | Pending | April - 1st week
Activity 6 | Providing a manual to ask sensitive questions | September' 2015 |  |  |  | Pending
Stratergy 9 | Case conference of staff every month with the Head of the facility | Start Date | End Date | Responsible members | Budget | Status
Activity 1 | Discussing 2 successful cases | 7 April' 2015 |  |  |  | Completed and are in process
Activity 2 | Discussing two difficult cases in which they feel they are stuck | 9 April' 2015 |  |  |  | Completed and are in process
Activity 3 | Barriers and issues faced on the field | 9 April' 2015 |  |  |  | Completed and are in process
a | Making the performa for case conference | 9 April' 2015 |  |  |  | Completed and are in process
b | *Inviting experts as and when required | 9 April' 2015 |  |  |  | Completed and are in process
c | PSV presenting cases and contributing in conferences | 2016-04-01 |  |  |  | Completed
Area for improvement: 2.3 : Treatment psychosocial rehabilitation and links to support networks and services and other
services are elements of a service user-driven recovery plan and contribute to a service user's ability to live independent in the community
Statergy 1 | Working on strenghts and choices of the user | Start Date | End Date | Responsible members | Budget | Status
Activity 1 | Making a flow chart of areas of a strengths and discussing them with the user when he/ she comes to the facility | August' 2015 |  |  |  | Status needs to be checked
doing it on the 3rd follow up on the post admission counseling
Statergy 2 | A improvement plan also will be made while identifying their weekness and choices will be presented to the user | Start Date | End Date | Responsible members | Addressed by the project by introducing Recovery Plans
Activity 1 | A short term and long term goals with the users will be identified for every and its progress will be monitored every 15 days | July' 2015 |  |  |  | Completed
Activity 2 | CGI mapping by the psychiatrist will also be done | August' 2015 |  |  |  | Status needs to be checked
Statergy 3 | Basic Life skills and self- care skills for the users | Start Date | End Date | Responsible members | Budget | Status
Activity 1 | Trainings for life skills and self care with homogenous group | August' 2015 |  |  |  | Completed
Activity 2 | Done by the nursing student for which a protocol needs to be developed for nursing schools and supervisors | 2016-04-01
Stratergy 4 | Access to personal information: personal reviewing of files by the users so that they can adding notes | Start Date | End Date | Responsible members | Budget | Status
Activity 1 | Paper pencil should be provided for writing for the users | September' 2015 |  |  |  | Pending
Activity 2 | When the users will add a need in their files, or a choice- the onduty nurse will forward it to the conserned staff or will forwarded it to the staff in the next shift | September' 2015 |  |  |  | Pending
Activity 3 | Allotment of time for reviewing the files and adding notes for the users | September' 2015 |  |  |  | Pending
Activity 4 | Once the note/ choice is forwarded, it should be signed by the conserned staff and then bought to the user for signature so that he/she is informed that its acknowledged | September' 2015 |  |  |  | Pending
Activity 5 | Within two days, follow up should be done on the request | September' 2015 |  |  |  | Pending
Activity 6 | After the follow up the user should be informed about the status | September' 2015 |  |  |  | Pending
Activity 7 | A mechanism to monitor will be developed | September' 2015 |  |  |  | Pending
Activity 8 | A way to create awareness that such a process exits in the inpatient facility needs to be done | September' 2015 |  |  |  | Pending
Activity 9 | When the users read the files, one nursing staff should sit with the user incase they need assistance to understand the file | September' 2015 |  |  |  | Pending
Strategy:5 | Material for Display to share information | Start Date | End Date | Responsible members | Budget | Status | Content went for printing
Activity 1 | A road map to recovery needs to be prepared in a pictorial form and displayed in the OPD and IPD area (all wards too ) | July' 2015 |  |  |  | Pending
Activity 2 | The map will include the process necessary to go through for recovery (areas): Example: Medicine, alternative treatments, and the units that provide these areas and responsible persons/ or department in the facility to contact. | July' 2015 |  |  |  | Pending
Activity 3 | Areas of display needs to be decided | July' 2015 |  |  |  | Pending
a | Making the hard copies for display will be made | July' 2015 |  |  |  | Pending
b | List of responsibilities of the users and caregivers will be shared verbally and displayed | July' 2015 |  |  |  | Completed
Activity 4 | List of services provided by different units will be displayed | July' 2015 |  |  |  | Completed
Activity 5 | List of services provided by different units will be displayed | July' 2015 |  |  |  | Completed
Activity 6 | Preparation of the content of the material | July' 2015 |  |  |  | Completed
Strategy:6 | Creating awareness among users on options on treatment and rehabilitation | Start Date | End Date | Responsible members | Budget | Remarks
Activity 1 | Sensitization program :Services available with in the hospital for staff so that they can be oriented about them to the users and caregivers | 10 March' 2015 |  |  |  | Completed
| Making a list of services available | 10 March' 2015 |  |  |  | Completed
Activity 2 | Inter-linkage and referrals OT and workshop should be linked to activities with in the wards - A process for the same needs to be deveoped | March' 2015 |  |  |  | Completed
Activity 3 | Developing of inward activities by reviewing existing list of activity with Person A | March' 2015 |  |  |  | Completed
Activity 4 | List of Ngo and organisation for rehabilitation made and then orientation of staff involved in rehabilitation to the existing list | March' 2015 |  |  |  | Completed
Activity 5 | IEC material to be developed on the services provided by the facility | March' 2015 |  |  |  | Completed
Activity 6 | Poster and charts in the different areas of wards that include- inside wards and OPD on facilities needs to be displayed with information on treatment and rehabilitation | March' 2015 |  |  |  | Completed
Strategy:7 | Peer counselling group- PSV's | Start Date | End Date | Responsible members | Budget | Status
Activity 1 | Identify users from the facility | August'2015 |  |  |  | In- progress
Activity 2 | workshops for them will be conducted to make a team of “peer counsellors” within the facility. | August'2015 |  |  |  | In- progress
Strategy:8 | Collaboration with MH field action projects and urban health projects for follow up | Start Date | End Date | Responsible Person | Budget | Status
Activity 1 | Collaborating with mental health staff on field : like project by BPA | July'2015 | September'2015 |  |  | Pending | Long term plan
Activity 2 | Providing a training about the follow up process to the supervisors so that the supervisors can provide the training to the field workers | July'2015 | September'2015 |  |  | Pending
Activity 3 | Identifying area, village and home of the user before he/she get discharge- linking him to the supervisor of that village, so that the superviors links the user to the health worker visiting his house | July'2015 | September'2015 |  |  | Pending
Activity 4 | Follow up with the user will be done | July'2015 | September'2015 |  |  | Pending
Activity 5 | 2 months follow up with the supervors on the follow ups happening | July'2015 | September'2015 |  |  | Pending
Activity 6 | Meeting with the supervors every 2 months --- to discusss the progress in cases. | July'2015 | September'2015 |  |  | Pending
Activity 7 | Direct follow up of the user -phone calls/ at the time of users visit to the facility | July'2015 | September'2015 |  |  | Pending
Activity 8 | *Same process will be followed up wih the health centre | July'2015 | September'2015 |  |  | Pending
Activity 9 | Training of all the supervors provided by HMH-A | July'2015 | September'2015 |  |  | Pending
Activity10 | Exploring funding from DHMP | July'2015 | September'2015 |  |  | Pending
Area of improvement | Standard 3.1: Service users' preferences on the place and form of treatment are always a priority | [5 empty] | The head needs to choose the manual method
Stratergy 1 | Developing a System of Follow up | Start Date | End Date | Responsible members | Budget | Status | Mach 18th
Activity 1 | Developing a tracker system in which the HIMS will track all the dropouts (those who had a consultation the follow month and did not come) | May' 2015 |  |  |  | Pending
Activity 2 | Letter to Person A for permissions and and TATA (that runs the HIMS) needs to be send | June' 2015 |  |  |  | Completed
Activity 3 | Once the letter will be received a letter system or an automatic message system will be created by which the users will be remined for their follow up visits | June' 2015 | July' 2015
Statergy 2 | Planning for Discharge | Start Date | End Date | Responsible members | Budget | Status
Activity 1 | Plan for follow up visit needs to be developed:When to come for follow up to the facility |  |  |  |  | Pending
| how to identify your triggers and who to approach | August' 2015 |  |  |  | On-going . Completed
Activity 2 | Home visits by community health workers will begin once collaboation is done with BPA | August' 2015 | time frame |  |  | Pending | Activity Cancelled
Activity 3 | Post discharge counselling will be provided | August' 2015 |  |  |  | On-going/ Completed
Activity 4 | Mid term couselling post discharge will be done to prepare the users to live in the community | September' 2015 |  |  |  | On-going/ Completed
Activity 5 | When service user is admiited, the caregivers will have to come for a follow-up counselling session by the 3rd week of the stay | New |  |  |  | Pending
Activity 6 | Doing a session post a week of discharge with the relative will preparing him/ her for care and giving support | September' 2015 |  |  |  | On-going . Completed
Activity 7 | Need based counselling- informing the user about it , as they are always welcomed | September' 2015 |  |  |  | On-going . Completed
Activity 8 | Making sure that address is correctly taken for follow ups | September' 2015 |  |  |  | Completed
Stratergy 3 | Providing alternatives: Rehabilitation with NGO and Organisations | Start Date | End Date | Responsible members | Budget | Status
Activity 1 | A list of organisations and NGO’s across the state of Gujarat and other government mental health services will be preapred | June' 2015 |  |  |  | Completed
Activity 2 | Listing all the NGO and plan a road map for better linkages will be preapred | June' 2015 |  |  |  | Pending | Removed
Stratergy 4 | Follow ups with the NGO in which the users are rehabilitated: | Start Date | End Date | Responsible members | Budget | Status
Activity 1 | A protocol on making visits to NGO in which wandering persons with mental illness rehabilitated from the facility will be made | July' 2015 |  |  |  | Completed
Activity 2 | Report on each visist and ways to address the to supports that the NGO's will be developed with them | July' 2015 |  |  |  | Completed
Activity 3 | A monitoring mechanism to check the visits will be developed | July' 2015 |  |  |  | Completed
Activity 4 | Responisble persons for Organisation and NGO visits needs to be identify | July' 2015 |  |  |  | Completed
Stratergy 5 | Informing the Users about alternative for of treatment | Start Date | End Date | Responsible members | Budget | Status
Activity 1 | Telling the user about the alternative forms of treatments. | August' 2015 |  |  |  | Completed
a | In the facility/ outside the facility | August' 2015 |  |  |  | Completed
b | Sharing the pros and cons of treatment | August' 2015 |  |  |  | Completed
c | - Information on side effects | August' 2015 |  |  |  | Completed
Activity 2 | - ECT if not taken, its pros and cons. They should also be informed about alternatives available and pros and cons of choosing the alternatives. | August' 2015 |  |  |  | Completed
Stratergy 6 | Simplify the admission procedure: | Start Date | End Date | Responsible members | Budget | Status
Activity 1 | Alloting a time and day to the discharge keeping, keeping in mind that the same day is not the psychiatrist OPD consultation day | 10 April' 2015 |  |  |  | Completed
Activity 2 | A check list that will have the process of the admission needs to be made for the caregiver and user to know when and whom to approach | 10 April' 2015 |  |  |  | Completed
Activity 4 | The discharge couselling will be provided by the by psychiatric nursing staff/ senior staff | 16 April' 2015 |  |  |  | Pending
Activity 5 | A check list for the discharge procedure, like the admission also needs to be made keeping in mind the couselling services | 16 April' 2015 |  |  |  | Completed
Activity6 | The staff will be trained and supervised | September' 2015 |  |  |  | Pending
Activity 7 | A check list needs to be reviewed and counselling process in the same need to be added. | July' 2015 |  |  |  | Pending
| The concerned person for the process will tick and sign in the checklist and the file will be proceeded to the next person . | July' 2015 |  |  |  | Pending
Activity 8 | A stamp for post discharge couselling needs to be prepared | September' 2015 |  |  |  | Pending
Startergy 7 | Compulsory Visits of caregivers for IPD users | Start Date | End Date | Responsible Person | Budget | Status
Activity 1 | Caregivers will meet the staff along with the service users after 15 days of admission to discuss the improvement and recovery status | August'2015 |  |  |  | Completed
Activity 2 | Staff makes sure that the users will is given respect. When the caregivers visit, users will be given the option to refuse to meet | August'2015 |  |  |  | Completed
Activity 3 | If the visit is due, follow up by the social worker will be done | August'2015 |  |  |  | Completed
Activity 4 | Caregivers can meet the user when they are under observation, change in the policy needs to be made for the same | August'2015 |  |  |  | Pending
Activity 5 | Users are allowed to talk on phone to who ever they want from the caregivers telephone when they are being visited | August'2015 |  |  |  | Completed
Stratergy 8 | Telephone calls for inpatient department
Activity 1 | The service users will make calls when they want to by the phone available in the medical officers room | 2016-03-01 |  |  |  | Completed
Activity 1 | Pilot: Availability of phone on saturdays and Sundays | 2016-03-01 |  |  |  | Completed/ Ongoing
Improvement Area | Standard 3.2 Procedures and safeguards are in place to prevent detention and treatment without free and informed consent.
Stratergy 1 | Strenghtening procedure of informed consent | Start Date | End Date | Responsible members | Budget | Status
Activity 1 | Consent for admission will be taken of the user | August'2015 |  |  |  | Completed and Ongoing
Activity 2 | Information on admission will be given to the user with a language that the user understands | August'2015 |  |  |  | Completed and Ongoing
Activity 3 | -Pros and Cons of not being admitted will be told to him / her in the process of counselling | August'2015 |  |  |  | Completed and Ongoing
Activity 4 | - In situations when the user lacks insight because of his symptoms, substitute decision of the caregiver for the admission will be taken,will be documented as subsitute decision making . | August'2015 |  |  |  | Completed and Ongoing
Activity 5 | -Reasons which lead to substitute decision making will be documented. | August'2015 |  |  |  | Completed and Ongoing
Activity 6 | Need of reviewing the consent form by the core committee to add items like " substitute decision making" | August'2015 |  |  |  | Completed and Ongoing
Activity 7 | The consent form will have a separate column that will say out the reason and whose consent has been taken. | August'2015 |  |  |  | Completed and Ongoing
Activity 8 | In situations when user does not gives consent: It will be clearly written/ ticked that, “User did not give consent” and the reason below stating the reason will be made. | August'2015 |  |  |  | Completed and Ongoing
Stratergy 2 | Consent process at the time of admission | Start Date | End Date | Responsible members | Budget | Status
Activity 1 | Change in admission policy: direct admissions in acute wards are not allowed and users have to stay in the general ward needs to be made | July'2015 |  |  |  | Completed and Ongoing
Activity 2 | When they are admitted in the general ward, an observation chart will be made to monitor their progress. | July'2015 |  |  |  | Completed and Ongoing
Activity 4 | Repeated consent: once the user has refused consent, and he/ she is still admitted; his/her follow up will be done every 10 days in order to identify whether he/ she has gained insight. | July'2015 |  |  |  | Completed and Ongoing
Activity 5 | Repeated consent process: Once the staff feels that he/ she has gained insight, the consent process will be done again. | July'2015 |  |  |  | Completed and Ongoing
Stratergy 3 | Consent for ECT- ECT couselling | Start Date | End Date | Responsible members | Budget | Status
Activity 1 | Separate consent for each ECT will be taken | 26 May' 2015 |  |  |  | Completed and Ongoing | August- September
Activity 2 | The users consent will be taken instead of caregivers consent. In cases when user does not have insight, caregivers consent will be documented. | 26May' 2015 |  |  |  | Completed and Ongoing | August- September
Activity 3 | Before each ECT, the process of consent will start from the user. |  |  |  |  | Completed and Ongoing | August- September
Stratergy 4 | Changes in admission protocol | Start Date | End Date | Responsible members | Budget | Status
Activity 1 | It was suggested that a change in the admission protocol should be made for those users coming to the facility without caregivers asking for admission | August'2015 |  |  |  | Pending
Activity 2 | Users coming to the facility seeking admission will be taken inside the facility for observation and their reletives will be contacted and informed about the process. | August'2015 |  |  |  | Pending
Improvement Area: Standard 3.2 Procedures and safeguards are in place to prevent detention and treatment without free and informed consent.
Stratergy 1 | Dissemination of information by sharing knowledge | Start Date | End Date | Responsible members | Budget | Status
Activity 1 | Information with the users coming to the OPD service and IPD will be verbally shared through counselling services | July' 2015 |  |  |  | Completed
Activity 2 | A television where information will flash will be set up in the OPD | August' 2015 |  |  |  | Completed | IEC used instead of Television
Activity 3 | The user will be given informaton in the process of 5 set of couselling services | September' 2015 |  |  |  | Ongoing/ Pending
Activity 4 | Information on treatment and recovery plan will be discussed with the users. | August' 2015 |  |  |  | Ongoing/ Pending
Activity 5 | The users will be informed of alternatives that may include: therapy and other | July' 2015 |  |  |  | Ongoing/ Pending
Activity6 | Making a list of alternative methods | August' 2015 |  |  |  | Pending
Activity 7 | Making a formal method of using the student psychologist students - Person A coming to the facility | July' 2015 |  |  |  | Pending
Activity 8 | Sharing information about NGO's and linking users to other mental health organisations | July' 2015 |  |  |  | Ongoing/ Complete
Activity 9 | Making a formal system to dispense information in the facility on services that have to be taken from out side, creating linkage , simplifyng the process | July' 2015 |  |  |  | Pending
Activity10 | Developing a training on side effects of medicine and providing it to the staff so that they can share it with the users | July' 2015 |  |  |  | Pending
Activity11 | Both verbal and written information should be provided for all | August' 2015 |  |  |  | Completed
Activity12 | Preparation SOP's for dissemination of information | August' 2015 |  |  |  | Ongoing
Statergy 2 | Reviewing and reformulating Grievence redressal committee and policy | Start Date | End Date | Responsible members | Budget | Status
Activity 1 | Grievence redressal policy for users and caregivers needs to be reviewed | July' 2015 |  |  |  | Completed | September
activity 2 | Grievence reddressal by strenghtening the internal communication system | July' 2015 |  |  |  | Completed | September
Activity 3 | Making a new policy and a system to identify grievences | August;2015 | 30th August'2015 |  |  | Completed | September
Strategy:3 | Developing an internal communication system to facilitate complaints | Start Date | End Date | Responsible members | Budget | Status | Activity removed as did not gain consensus on its value and fesability
Activity 1 | An internal communication system will be developed in which the users will approach the attendant staff. . | June' 2015 |  |  |  | Completed
Activity 2 | A register for the same will be maintained by the senior attendant staff and will be handed over to the nursing staff. | July' 2015 |  |  |  | Activity changed and replace
Activity 3 | The role of the nursing staff will be to approach the staff whom the user wants to meet and then the responsibility will be on the shoulders of the staff to come and meet the user in three days | July' 2015 |  |  |  | Activity changed and replace
Activity 4 | The staff will meet the user in a private room and document the summary of the meeting in the case paper | July' 2015 |  |  |  | Activity changed and replace
Activity 5 | The summary and the register will be monitored by the a monitoring body | July' 2015 |  |  |  | Activity changed and replace
Activity 6 | In case there is a grievence told to the staff whom the user wants to meet. The staff will write in the summary report of the file- Information Confidential' and the respondibility will lie on the staff to report and take it to the grievence committee | July' 2015 |  |  |  | Activity changed and replace
Stratergy 4 | Providing provisions for feedback | Start Date | End Date | Responsible members | Budget | Status
Activity 1 | Feedback Boxes will be available in all wards and OPD | July' 2015 |  |  |  | In-progress | December
Activity 2 | IEC Material on the importance of feedback | July' 2015 |  |  |  | In-progress | December
Activity 3 | Suprize User and caregiver interviews for feedback will be taken by the interview committee | July' 2015 |  |  |  | In-progress | December
Activity 4 | Feedback form to be made and stationary to help provide feedback to be made available (Part of the grievence policy) | July' 2015 |  |  |  | In-progress | December
Activity 5 | Submission of report on feeback and sharing it with the staff will be done. A protocol to do the process will be developed (Part of the grievence policy) | July' 2015 | july |  |  | In-progress | December
Activity 6 | Issues should be documented to be addressed on priority basis (Part of the grievence policy) | July' 2015 |  |  |  | In-progress | December
Activity 7 | Introducing a new feedback form for service users by caregivers in the OPD | New April |  |  |  | In-progress
Improvement Area | 3.3 Service users can exercise their legal capacity and are given the support they may require to exercise their legal capacity.
Stratergy | Legal Representation for the user: | Start Date | End Date | Responsible members | Budget | Status | Dr is working on it
Activity 1 | . A collaboration with the lawyers coming to the facility to provide legal aid to the users. | July' 2015 |  |  |  | Pending | October
Activity 2 | Days and hours will be alloted for the same | July' 2015 |  |  |  | Pending | October
Activity 3 | Procedure to approach the legal aid (lawyers) needs to be developed | July' 2015 |  |  |  | Pending | October
Improvement Area | Standard 4.1: Service users have the right to be free from verbal, mental, physical and sexual abuse and physical and emotional neglect.
Stratergy 1 | Training the staff in theraputic communication | Start Date | End Date | Responsible members | Budget | Taken up by the project
Improvement Area | Standard 4.2: Alternative methods are used in place of seclusion and restraint as means of de- escalating potential crises
Strategy:1 | Addressing restrain and seclusion | Start Date | End Date | Responsible members | Budget | Status
Activity 1 | All the seclusions happening in IPCU should be documented | May' 2015 |  |  |  | Initiated by the Project through seclusion, restraint and involuntary medication form
Activity 2 | Monitoring body should be made to review the practices | May' 2015 |  |  |  | Completed
| Practice was putting users in seclusion before ECT is admisnistered for the whole nights is done, alternatives for the same need to identified | New addition |  |  |  | Completed
Area of improvement | Standard 4.5: Safeguards are in place to prevent torture or cruel, inhuman or degrading treatment and other forms of ill- treatment and abuse.
Stratergy 1 | Creating knowledge about committees among users and caregivers | Start Date | End Date | Responsible Person | Budget | Status | January
Activity 1 | Awareness about the existing committees and newly formed committees made | September'2015 |  |  |  | Ongoing / Completed
a | This will include: | September'2015 |  |  |  | Ongoing / Completed
b | -When to approach | September'2015 |  |  |  | Ongoing / Completed
c | - Key person to contact in each committee | September'2015 |  |  |  | Ongoing / Completed
d | - Making the person approcahable | September'2015 |  |  |  | Ongoing / Completed
e | - The process of approaching | September'2015 |  |  |  | Ongoing / Completed
f | - Issues of addressing the confidentiality | September'2015 |  |  |  | Ongoing / Completed
Activity 2 | All of the above is included in the citizen charter that will be displayed in the facility | 2016-04-01 |  |  |  | Ongoing / Completed | Will be displayed by April 15th
Stratergy 3 | Addressing compalaints and activating exiting grievence addressing cell | Start Date | End Date | Responsible members | Budget | Status
Activity 1 | Meeting with the grievance redressal committee to review the policy | July'2015 | August'2015 |  |  | In progress
Activity 2 | Developing a mechanism to ensure confidentiality of complaints | July'2015 | August'2015 |  |  | In progress
Activity 3 | Timely action : period of addressing a complaints will be decided through the meeting | July'2015 | August'2015 |  |  | In progress
Activity 4 | Ground level committee of staff | July'2015 | August'2015 |  |  | In progress
a | - to suprise interviews by the interview committee | July'2015 | August'2015 |  |  | Removed from the final policy
b | - Liason committee doing its roles and responsiblities as investigation agents | July'2015 | August'2015 |  |  | In progress
c | - meet with the body for monitoring for the same every 2 weeks to inform them about the status | July'2015 | August'2015 |  |  | In progress
Activity 5 | The monitoring body roles need to be defined by the core committee | July'2015 | August'2015 |  |  | In progress
Improvement Area | Standard 5.1: Service users are supported in gaining access to a place to live and have the financial resources necessary to live in the community.
Strategy:1 | Activities for the users in the inpatient facility | Start Date | End Date | Responsible Person | Budget | Status
Activity 1 | Asssessment of strenghts, skills, education and hobbies of the user in the inpatient facility | June'2015 |  |  |  | On-going
Activity 2 | After identifying their strenghts - Planning tasks on three level : Ward based activities, semi-skilled activities and skilled activities | June'2015 |  |  |  | On-going
Activity 3 | Making groups of users and alloting them activities based on their choice and preference | June'2015 |  |  |  | On-going
Activity 4 | Planning of activities : Ward based activities, semi-skilled activities and skilled activities | June'2015 | July'2015 |  |  | On-going
Activity 5 | For Users of Chronic ward: an OT regime needs to be planned | June'2015 | July'2015 |  |  | On-going
Activity 6 | For exercise regime : Medical officer needs to be consulted | June'2015 |  |  |  | On-going
Activity 7 | Monitoring ward based activities of users so that they can be taken up to the next level | June'2015 |  |  |  | On-going
Stratergy | Ward based activity | Start Date | End Date | Responsible Person | Budget | Status
Activity 1 | Physical exercise will be done every morning in the garden area provided for the chronic and acute ward. Male and female users will be engaged in the activity together. | August |  |  |  | In-progress
Activity 2 | • Once a week yoga as a morning activity under guidance of physiotherapist | August |  |  |  | Ongoing/ Complete
Activity 3 | 3 days indoor activity- 3 days outdoor activity will be planned | August |  |  |  | In-progress
Statergy2 | Linkages with CSR of companies to create awareness to invest in Mental Health Projects (providing vocation to the users ) | Start Date | End Date | Responsible Person | Budget | Ongoing
Stratergy 3 | Caregiver Counseling on ways to take care of caregivers once they are back at their home after discharge / information on care for caregivers at the OPD | Start Date | End Date | Responsible Person | Budget | Pending
Stratergy 4 | Supporting the users find housing | Start Date | End Date | Responsible Person | Budget | Status
Activity 1 | Contacting Organisations for residential pursposes for users housing needs | October'2015 |  |  |  | Check status
Activity 2 | Initiate a project on half way home | October'2015 |  |  |  | Pending | Long term plan
Statergy 5 | Education as an areas to be explored | Start Date | End Date | Responsible Person | Budget | Status
Stratergy 6 | Strenghtening the day care centre and Project Saksham on vocational opportunities | Start Date | End Date | Responsible Person | Budget | Status
Improvement Area | Standard 5.2: Service users can access education and employment opportunities.
Stratergy 7 | Employment Portal ---- | Start Date | End Date | Responsible Person | Budget | Status
Strategy: 8 | Micro finace group for users coming to the workshop | Start Date | End Date | Responsible Person | Budget | Status
Statergy 9 | Review of job satisfaction of of OPD users/ Vocation review | Start Date | End Date | Responsible Person | Budget | Status
Activitity 1 | Disscussing the users current status at work and assess their progress | August'2015 |  |  |  | Ongoing | In discussion with GFSI
Activity 2 | Identify the barriers faced at work through the asssessment | August'2015 |  |  |  | Check status
Activity 3 | Identify days of work lost | August'2015 |  |  |  | Check status
Activity 4 | Supporting them to work with their barriers | August'2015 |  |  |  | Check status
Activity 5 | Engaging them at home when they miss days at work so that they are not out of activity | August'2015 |  |  |  | Check status
Activity 6 | Counselling the caregivers on the ways by which they can motivate the users | August'2015 |  |  |  | Check status
Activity 7 | The facility intervenes with the employer when needed | August'2015 |  |  |  | Check status
Activity 8 | Organising motivational sessions for the users working | August'2015 |  |  |  | Check status
Stratergy 10 | Addressing employment needs - Project Saksham | Start Date | End Date | Responsible members | Budget | Status
Activity 1 | Identifying Interest, expectations and desirability of the users | August' 2015 |  |  |  | In-progress
Activity 2 | Job analysis will be done | August' 2015 |  |  |  | In-progress
Activity 3 | Re- assessment of will be done after every 15 days for identify interest, expectations and desires | August' 2015 |  |  |  | In-progress
Activity 4 | Users will work on their recovery with the psychiatric nursing staff to plan psychiatric nursing care and community care for themselves | August' 2015 |  |  |  | In-progress
Activity 5 | Identify the psychiatric nursing staff interested in rehabilitation so that a team to work on rehabilitation for the users | August' 2015 |  |  |  | In-progress
Activity 6 | ADL and life skills traing to all psychiatric staff, so that they can train the other staff in batches and on rotation | August' 2015 |  |  |  | In-progress

## Facility2a
Strategy: | Present information to users related to additional services in the area | Start Date | End Date | Responsible members | Budget | Status
Activity 1 | Collect and compile information related to mental health services across gujarat. | 2015-02-01 | 2015-02-10 |  |  | Pending/ Completed
Activity 2 | Department meet to decide and sort out a resource list. | 2015-02-10 | 2015-02-15
Activity 3 | Consolidate sotred information and print | 2015-02-15 | 2015-02-20
Activity 4 | Distribute list to all Department staff | 2015-02-15 | 2015-02-20
Activity 5 | Add information to depatment information kit. | 2015-02-15 | 2015-02-20
Activity 6 | Create department policy for yearly review of information | 2015-02-15 | 2015-02-20
Activity 7 | Create a NGO feedback form to track users expereinces with the NGO.
Activity 8
Activity 9
Activity 10
Activity 11
Activity 12
Activity 13
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18
Activity 19
Activity 20
Area for improvement:2.2
Strategy: | Create better networks with NGO's and schools thaat provide rehablitation services. | Start Date | End Date | Responsible members | Budget
Activity 1 | Complie a list of special schools and NGO's in the area. | 2015-02-01 | 2015-02-10
Activity 2 | Shortlist relevant organizations and contact one person from the Orginization | 2015-02-10 | 2015-02-28
Activity 3 | Invite/visit Organizations to present their work to the Department. | 2015-03-01 | 2015-03-30
Activity 4 | Create a visit schedule for the year | 2015-03-01 | 2015-03-10
Activity 5 | Get visits approved by CDMO | every month
Activity 5 | Add monthly visits to the Departmental policy | 2015-03-30 | 2015-04-10
Activity 8
Activity 9
Activity 10
Activity 11
Activity 12
Activity 13
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18
Area for improvement:
Activity 18
Area for improvement: 2.2
Strategy: | Training staff in providing psychosocial care | Start Date | End Date | Responsible members | Budget
Activity 1 | Request traninng form QualityRights team on psychosocial rehablitation | 2015-02-01 | 30/2/15
Activity 2 | Finalize training dates with QR team | 2015-03-01 | 2015-03-15
Activity 3 | Send staff for training | 2015-03-01 | 2015-05-30
Activity 4
Activity 5
Activity 6
Activity 7
Activity 8
Activity 9
Activity 10
Activity 11
Activity 12
Activity 13
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18
Area for improvement:2.3
Strategy: | Train staff for recovery plan | Start Date | End Date | Responsible members | Budget
Activity 1 | Request traninng form QualityRights team on psychosocial rehablitation | 2015-02-01 | 30/2/15
Activity 2 | Finalize training dates with QR team | 2015-03-01 | 2015-03-15
Activity 3 | Send staff for training | 2015-03-01 | 2015-04-30
Activity 4 | Prepare material to train other departmental staff | 2015-05-01 | 2015-05-15
Activity 5 | Train other departmental staff on the need using recovery plans. | 2015-05-15 | 2015-05-30
Activity 6 | Train staff on using and implementing recovery plans on a day today basis. | 2015-05-20 | 2015-05-31
Activity 7
Activity 8
Activity 9
Activity 10
Activity 11
Activity 12
Activity 13
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18
Area for improvement: 2.3
Strategy: | Using measures of recovery for users | Start Date | End Date | Responsible members | Budget
Activity 1 | Collect information related to various useful and culturally relevant measures of recovery | 2015-02-01 | 2015-02-28
Activity 2 | Meet as a department(after recovery training) to decide best measue to be used. | 2015-03-20 | 2015-03-30
Activity 3 | Decide procedures and policies regarding use of recovery measurement | 2015-03-20 | 2015-03-30
Activity 4
Activity 5
Activity 6
Activity 7
Activity 8
Activity 9
Activity 10
Activity 11
Activity 12
Activity 13
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18
Area for improvement:
Strategy: | Create preference checklist and train staff in using them. | Start Date | End Date | Responsible members | Budget
Activity 1 | Conduct an initial meeting to discuss the need and benefists of using preference checklist. | 2015-03-01 | 2015-03-15
Activity 2 | Collect information from preference checklists used in other hospitals. | 2015-03-15 | 2015-04-15
Activity 3 | Meet to finalize items on the checklist and the process for it to be used. | 2015-04-15 | 2015-04-20
Activity 4 | Train staff in using the checklist acooring to the users needs. | 2015-05-01 | 2015-05-10
Activity 5
Activity 6
Activity 7
Activity 8
Activity 9
Activity 10
Activity 11
Activity 12
Activity 13
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18
Area for improvement: 2.3
Strategy: | informing users of available govenrnment and community resources | Start Date | End Date | Responsible members | Budget
Activity 1 | Complie a list of available resourses(govt grants, etc) | 2015-02-01 | 2015-02-28
Activity 2 | Create a standard format of details related to each resourse(eg: Name of org, contact person, documents needed to access grant etc) | 2015-03-01 | 2015-03-10
Activity 3 | Train all department staff about the details and how it can be accessed | 2015-03-10 | 2015-03-20
Activity 4 | Add infromation department kit | 2015-03-20 | 2015-03-30
Activity 5 | Create a policy to revise infromation every year.
Activity 6
Activity 7
Activity 8
Activity 9
Activity 10
Activity 11
Activity 12
Activity 13
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18
Area for improvement:2.4
Strategy: | Contacting higher authorities to create policies for regular supply of medication | Start Date | End Date | Responsible members | Budget
Activity 1 | Make a list of essential drugs needed at the facility. | 2015-02-01 | 2015-02-10
Activity 2 | Speak with the Pharmacist/Dr. regarding the shortage | 2015-02-01 | 2015-02-10
Activity 3 | Identify government officials responsible for supply of drugs and make a formal request. | 2015-02-10 | 2015-02-20
Activity 4
Activity 5
Activity 6
Activity 7
Activity 8
Activity 9
Activity 10
Activity 11
Activity 12
Activity 13
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18
Area for improvement: 2.4
Strategy: | Creating a procedure to get a list of available medicenes from pharmacy | Start Date | End Date | Responsible members | Budget
Activity 1 | Ask pharmacy to share a list of available medecines every week to the department | 2015-01-01 | 2015-10-01
Activity 2 | meet with CDMO and systems manager to make list available on the HIMIS | 2015-02-01 | 2015-02-10
Activity 3 | Integrate pharmacy entry of druglist into hospital policy | 2015-03-01 | 2015-03-20
Activity 4
Activity 5
Activity 6
Activity 7
Activity 8
Activity 9
Activity 10
Activity 11
Activity 12
Activity 13
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18
Area for improvement: 2.4
Strategy: | Create networks with other hospitals to look for altrenate supply of medication | Start Date | End Date | Responsible members | Budget
Activity 1 | Contact hospital to ask for their source of medecine supply | 2015-02-01 | 2015-02-10
Activity 2 | Meet with CDMO to discuss creation of medecine support liks with hospital. | 2015-02-01 | 2015-02-10
Activity 3
Activity 4
Activity 5
Activity 6
Activity 7
Activity 8
Activity 9
Activity 10
Activity 11
Activity 12
Activity 13
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18
Area for improvement: 2.4, 3.4
Strategy: | Train staff in using HMIS to create individual files for users and document daily activities | Start Date | End Date | Responsible members | Budget
Activity 1 | Request CDMO to provide a computer at the department to manage data | 2015-02-01 | 2015-02-01
Activity 2 | Contact TCS to train staff in HMIS data management | 2015-02-02 | 2015-02-10
Activity 3 | Conduct an one day onsite training for dept staff | 2015-02-10 | 2015-02-15
Activity 4 | Ask hospital systems manager for additionla support for manageing data. | 2015-02-01 | 2015-02-15
Activity 5 | Track internal referrals though HMIS | 2015-02-02 | 2015-02-16
Activity 6
Activity 7
Activity 8
Activity 9
Activity 10
Activity 11
Activity 12
Activity 13
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18
Area for improvement:2.3.3.4
Strategy: | Train staff in explaining side effects of drugs to users | Start Date | End Date | Responsible members | Budget
Activity 1 | Make a list of side effects of all drugs prescribed at the department. | 2015-02-01 | 2015-02-10
Activity 2 | Ask Dr. for support in content for information related to drugs and how to present it to users.
Activity 3 | Print and display side effects of medication across OPD and every IPD
Activity 4 | Train staff in explaining side effects of drugs to users
Activity 5
Activity 6
Activity 7
Activity 8
Activity 9
Activity 10
Activity 11
Activity 12
Activity 13
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18
Area for improvement: 2.5
Strategy: | Design and use a detailed case file for users | Start Date | End Date | Responsible members | Budget
Activity 1 | Review detailed case papers used in other hospitals. | 2015-02-01 | 2015-02-28
Activity 2 | Select components required for case paper at the OPD
Activity 3 | Create a filing system for casepapers at the facility
Activity 4 | Train staff in collecting and organizing information
Activity 5 | Add process to the department policy
Activity 6
Activity 7
Activity 8
Activity 9
Activity 10
Activity 11
Activity 12
Activity 13
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18
Area for improvement:1.2
Strategy: | Make another ward to reduce crowding in the present wards | Start Date | End Date | Responsible members | Budget
Activity 1 | Discuss the issue of crowding in the facility meeting. | yet to be decided
Activity 2 | Seek permission from higher CDMO for creating space for another ward.
Activity 3
Activity 4
Activity 5
Activity 6
Activity 7
Activity 8
Activity 9
Activity 10
Activity 11
Activity 12
Activity 13
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18
Area for improvement: 1.2
Strategy: | Increase nursing staff to provide care for children and elderly population | Start Date | End Date | Responsible members | Budget
Activity 1 | Discuss hiring of new staff at the facility meeting.
Activity 2 | Seek permission from higher CDMO for assigining new staff to care for children and elderly.
Activity 3
Activity 4
Activity 5
Activity 6
Activity 7
Activity 8
Activity 9
Activity 10
Activity 11
Activity 12
Activity 13
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18
Area for improvement: 1.2
Strategy: | Provide locker facility to service users traveling from longer distances | Start Date | End Date | Responsible members | Budget
Activity 1 | Create a tender list for 6 lockers per ward. | 2015-02-01 | 2015-02-20
Activity 2 | Purchace lokcers for every ward with the approval of the CDMO. | 2015-02-20 | 2015-03-15
Activity 3 | Create guidelines for the use of lockers. | 2015-02-20 | 2015-03-15
Activity 4 | Inform/ Train incharge sisters, attendants, PRO on the guidelines. | 2015-03-15 | 2015-03-25
Activity 5
Activity 6
Activity 7
Activity 8
Activity 9
Activity 10
Activity 11
Activity 12
Activity 13
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18
Area for improvement:
Strategy: | Assign a daily physician to visit wards in order to discharge service users on time in order to reduce occupancy. | Start Date | End Date | Responsible members | Budget
Activity 1 | Discuss the need of a regular visitng physcian at the facility meeting. | 2015-02-10 | 2015-02-20
Activity 2
Activity 3
Activity 4
Activity 5
Activity 6
Activity 7
Activity 8
Activity 9
Activity 10
Activity 11
Activity 12
Activity 13
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18
Area for improvement:
Strategy: | Wash curtains in wards regularly so that they are used between beds in order to ensure privacy. | Start Date | End Date | Responsible members | Budget
Activity 1 | Add curtains to washing register. | 2015-02-01 | 2015-02-15
Activity 2 | Inform sister in charge in every ward to do monthly checks of curtains that are in use. | 2015-02-15 | 2015-02-20
Activity 3 | Visit wards monthly to ensure that curtains are being used at the wards.
Activity 4
Activity 5
Activity 6
Activity 7
Activity 8
Activity 9
Activity 10
Activity 11
Activity 12
Activity 13
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18
Area for improvement: 1.3
Strategy: | Train class four staff on higher standards of hygiene and cleanliness | Start Date | End Date | Responsible members | Budget
Activity 1 | Identify resource person / organization to train staff | 2015-02-18 | 2015-03-15
Activity 2 | Inform staff of training and set training dates | 2015-03-15 | 2015-03-30
Activity 3 | Weekly training form 10-15 staff over a period of a two months(total staff= 101) | 2015-04-01 | 2015-05-30
Activity 4
Activity 5
Activity 6
Activity 7
Activity 8
Activity 9
Activity 10
Activity 11
Activity 12
Activity 13
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18
Area for improvement:1.3
Strategy: | Creating specific daily activity sheets for duties of attendant staff and cleaning staff | Start Date | End Date | Responsible members | Budget
Activity 1 | List out specific duties of cleaning staff and attendant staff. | 2015-02-18 | 2015-02-28
Activity 2 | Create daily checklist of duties of staff. | 2015-03-01 | 2015-03-15
Activity 3 | Train staff in using the check list on a daily basis. | 2015-03-15 | 2015-03-30
Activity 4
Activity 5
Activity 6
Activity 7
Activity 8
Activity 9
Activity 10
Activity 11
Activity 12
Activity 13
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18
Area for improvement: 1.6
Strategy: | Providing waiting chairs for families to sit outside the wards | Start Date | End Date | Responsible members | Budget
Activity 1 | Make a list of required furniture outside wards. | 2015-02-01 | 2015-02-15
Activity 2 | Get approval from CDMO to buy the furniture. | 2015-02-15 | 2015-02-20
Activity 3 | Purchase and install furniture at respective wards. | 2015-03-01 | 2015-03-15
Activity 4
Activity 5
Activity 6
Activity 7
Activity 8
Activity 9
Activity 10
Activity 11
Activity 12
Activity 13
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18
Area for improvement:
Strategy: | Create specific roles with Public Relatison officers to improve interactions with service users | Start Date | End Date | Responsible members | Budget
Activity 1
Activity 2
Activity 3
Activity 4
Activity 5
Activity 6
Activity 7
Activity 8
Activity 9
Activity 10
Activity 11
Activity 12
Activity 13
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18
Area for improvement:3.4
Strategy: | Create personal files for users at the facility | Start Date | End Date | Responsible members | Budget
Activity 1 | Collect case papers that are with users over a period of 2 months. | 2015-02-01 | 30/2/15
Activity 2 | Create a temporaty filing system. | 2015-02-10 | 2015-02-15
Activity 3 | Apply to purchase files and filing cabinet. | 2015-02-15 | 2015-02-20
Activity 4 | Meet to decide a OPD fling system process/ ploicies/ | 2014-02-15 | 2015-02-20
Activity 5 | Install filing system and train staff in using the filing system | 2015-02-20 | 2015-02-02
Activity 6
Activity 7
Activity 8
Activity 9
Activity 10
Activity 11
Activity 12
Activity 13
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18
Area for improvement:3.4
Strategy: | Create departmental policies regarding access to medical files | Start Date | End Date | Responsible members | Budget
Activity 1 | Gather information related to national laws of confedentiality. | 2015-02-15 | 2014-02-28
Activity 2 | Review policies of other hospitals regarding confidentiality policies | 2015-02-16 | 2015-02-28
Activity 3 | meet as a department to adopt policies specific to the facility | 2015-03-20 | 2015-03-30
Activity 4 | Train staff on departmental policies. | 2015-04-01 | 2015-04-15
Activity 5
Activity 6
Activity 7
Activity 8
Activity 9
Activity 10
Activity 11
Activity 12
Activity 13
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18
Area for improvement:3.4
Strategy: |  | Start Date | End Date | Responsible members
Activity 1
Activity 2
Activity 3
Activity 4
Activity 5
Activity 6
Activity 7
Activity 8
Activity 9
Activity 10
Activity 11
Activity 12
Activity 13
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18

## Facility2b
Area for improvement: | 1.2 The sleeping conditions of service users are comfortable and allow sufficient privacy. | [8 empty] | Update on 28th November, 2015
Strategy 1: | Creating a regular comprehensive system for checking bedding, locks, curtains and other equipment at each ward. | Start Date | End Date | Responsible members | Budget | Status- Pending/Complete | New Deadline | Explanation for not meeting the deadline | Proposed Plan for meeting new deadline | Status- Pending/Complete | New Deadline (add date of entering) | Explanation for not meeting the deadline | Proposed Plan for meeting new deadline
Activity 1 | Make a check list and ward map of ward material(bedding,locks etc) that require to be regularly checked. | 2015-06-01 | 2015-06-05 |  | 0 | completed | 2015-09-30 | Required coordination between various departments in the hospital. | Talk to the AHA about the activities. Have a plan in place so that it can be initiated on CDMO's arival. |  | 2015-12-10 | This was discissedwith the AHA. Once bacis list of procedures and policies is consolidated , the staff will be trained in it together. | Procedural and policy related activitues have been shifted to december and January
Activity 2 | Create a procedure where all departments receive a weekly copy of the list in order to make the necessary changes. | 2015-07-01 | 2015-07-15 |  | 0 | completed | 2015-10-10 |  |  |  | 2015-01-10
Activity 3 | Get approval from CDMO for procedures created. | 2015-07-01 | 2015-07-15 |  | 0 | Pending | 2015-10-11 |  |  |  | 2015-01-20 |  |  | Procedure is being reviewed and corredted by the CDMO
Activity 4 | Train all nurses and department heads(linen keeper, steward, electrician) on conducting regular follow ups and conducting weekly checks of ward equipments. | 2015-07-15 | 2015-07-30 |  | 0 | Pending | 2015-10-12 |  |  |  | 2015-01-30
Area for improvement: | 1.2 The sleeping conditions of service users are comfortable and allow sufficient privacy.
Strategy 2: | Provide locker facility to service users traveling from longer distances. | Start Date | End Date | Responsible members | Budget
Activity 1 | Create a tender list for 6 lockers per ward. | 2015-03-01 | 2015-03-10 |  | 0 | Completed
Activity 2 | Purchase lockers for every ward with the approval of the CDMO with extra set of keys for each locker. | 2015-03-20 | 2015-03-30 |  | INR 30000 | Completed
Activity 3 | Create guidelines for the use of lockers. | 2015-05-20 | 2015-05-30 |  | 0 | Completed
Activity 4 | Create receipt book for collecting deposit for keys. | 2015-05-15 | 2015-05-25 |  | 0 | Decided by team not to do | Changed activitiy : Speak to vendors outside the hospital to keep locks for rent/ purchace.
Activity 5 | Inform/ Train in charge nurses, attendants, PRO on the guidelines. | 2015-05-15 | 2015-05-30 |  | 0 | completed | 2015-09-20 |  | need to include AHA in the training and ints planning |  | 2015-01-20 |  | Procedural and policy related activitues have been shifted to december and January
Activity 6 | Create poster for guidelines for users informing them of the use and maintainance of the locker and post it on each locker. | 2015-05-25 | 2015-05-30 |  | 0 | Completed | 2015-09-20 |  |  |  | 2015-01-20
Area for improvement: | 1.2 The sleeping conditions of service users are comfortable and allow sufficient privacy.
Strategy 3: | Wash curtains in wards regularly so that they are used between beds in order to ensure privacy. | Start Date | End Date | Responsible members | Budget
Activity 1 | Add curtains to washing register. | 2015-03-01 | 2015-03-15 |  | 0 | Completed
Activity 2 | Inform sister in charge in every ward to do monthly checks of curtains that are in use. | 2015-03-15 | 2015-03-20 |  | 0 | Completed
Activity 3 | Visit wards monthly to ensure that curtains are being used at the wards. |  |  |  | 0 | Completed
Area for improvement: | 1.2 The sleeping conditions of service users are comfortable and allow sufficient privacy.
Strategy 4: | Training staff nurses on issues related to privacy | Start Date | End Date | Responsible members | Budget
Activity 1 | Review policies of other hospitals on privacy. | 2015-05-01 | 2015-05-30 |  | 0 | Completed
Activity 2 | Discuss with core team practices of privacy that need to be adopted in the hospital. | 2015-05-30 | 2015-06-15 |  | 0 | Pending |  | To be continued after the human rights training, since it is also addressing issues relaggted to privacy. |  |  | Responsible person has discontinued with the core team.
Activity 3 | Create/ finalize a training module for nursing staff. |  | 2015-06-30 |  | 0 | Pending | 2015-09-25 |  |  |  | 2015-12-10
Activity 4 | Train all staff nurses in practices related to privacy and include the use of curtains in the module. | 2015-07-01 | 2015-07-30 |  | 0 | Pending | 2015-10-15 |  |  |  | 2015-12-10
Area for improvement: | 1.3 The facility meets hygiene and sanitary requirements.
Strategy 1 : | Train staff on higher standards of hygiene and cleanliness | Start Date | End Date | Responsible members | Budget
Activity 1 | Identify resource person / organization to train staff | 2015-05-15 | 2015-04-20 |  | 0 | Completed
Activity 2 | Create a training module for training staff. | 2015-05-20 | 2015-05-30 |  | 0 | Completed
Activity 3 | Creating training schedule with 15 staff per training | 2015-04-01 | 2015-05-30 |  | 0 | completed | 2015-09-10 | Delay in setting schedules with cleaning staff for training and changes in staff. | The staff will be revised after september. The cleaning staff supervisor has been kept in the loop about the planned trainings so that once the new staff it appointed , trainings can start immediately.
Activity 4 | Issue letter with CDMO's permission for training to all Class 4 staff | 2015-06-05 | 2015-06-10 |  | 0 | completed |  |  |  | 2015-12-05 | The trainings were delayed due to ongoing human rights trainnigs | Revise training calender
Activity 5 | Conduct first round of training for staff | 2015-06-10 | 2015-07-15 |  | INR1000 | completed |  |  |  | 2015-12-10
Activity 6 | Conduct follow up training to take feedback and address issues of implementation | 2015-07-15 | 2015-08-15 |  | 0 | Pending |  |  |  | 2015-12-25
Activity 7 | Revise module to train class 1, 2 and 3 staff. | 2015-08-15 | 2015-08-30 |  | INR1000 | Pending |  |  |  | 2015-12-08
Activity 8 | Conduct training for class 1, 2 and 3 staff. | 2015-09-01 | 2015-09-15 |  | 0
Area for improvement: | 1.3 The facility meets hygiene and sanitary requirements.
Strategy 2: | Introduce more dustbins across the facility | Start Date | End Date | Responsible members | Budget
Activity 1 | Create a map of the places in the facility that need dustbins | 2015-05-19 | 2015-05-25 |  | 0 | Completed |  | Waiting for release of funds
Activity 2 | Inform Dr. regarding the budget and get it approved | 2015-05-25 | 2015-06-05 |  | To be approved based on requirement at the facility. | Completed |  | Alternatively, work with interns to create substitutes
Activity 3 | Purchase and install dustbins | 2015-06-05 | 2015-06-15 |  | 0 | Completed
Activity 4 | Inform cleaning staff and compound caretaker to regularly use and clear dustbins. | 2015-06-05 | 2015-06-15 |  | 0 | Completed
Activity 5 | Conduct weekly rounds to see if the dustbins are maintained and used. | 2015-06-05 | 2015-06-15 |  | 0 | Completed
Area for improvement: | 1.3 The facility meets hygiene and sanitary requirements.
Strategy 3: | Revise daily activity sheets for duties of attendant staff and cleaning staff | Start Date | End Date | Responsible members | Budget
Activity 1 | List out specific duties of cleaning staff and attendant staff . | 2015-05-19 | 2015-05-25 |  | 0 | Completed
Activity 2 | Create daily time based checklist of duties of staff. | 2015-05-25 | 2015-06-05 |  | 0 | completed |  | There will be a significant reduction in number of staff in september. The team will have to reconsider the activity post that.
Activity 3 | Train staff in using the check list on a daily basis. | 2015-06-05 | 2015-06-15 |  | 0 | Completed |  |  |  | 2015-12-10 | Procedural and policy related activitues have been shifted to december and January | Meet with Aha and decide on a final procedure along with Sanitary inspector
Area for improvement: | 1.3 The facility meets hygiene and sanitary requirements.
Strategy 4: | Create a monthly "staff of the month" programme to motivate cleaning staff. | Start Date | End Date | Responsible members | Budget
Activity 1 | Form a committee from the core team reviewing staff work | 2015-05-19 | 2015-05-25 |  | 0 | completed | 2015-10-15
Activity 2 | Create a criteria for identifying good practices. | 2015-05-25 | 2015-06-05 |  | 0 | Pending |  |  |  | 2015-12-05 | delay in other activities | Coordinate with Govind Patel and Sanitary inspectory to do the first round of selection by end decemnmber
Activity 3 | Select first employee of the month / cleanliness champion. | 2015-06-05 | 2015-06-15 |  | 0 | Pending |  |  |  | 2015-12-20
Activity 4 | Prepare for a group meeting of all cleaning staff to felicitate the individual and provide them with a small token gift. | 2015-06-15 | 2015-06-30 |  | INR 100 pre month |  |  |  |  | 2015-10-20
Area for improvement: | 1.3 The facility meets hygiene and sanitary requirements.
Strategy 5: | Assign 3 cleaning staff on monthly rotation to clean toilets twice in the morning and evening | Start Date | End Date | Responsible members | Budget
Activity 1 | Create a rotation staff list for cleaning toilets. | 2015-03-01 | 2015-03-15 |  | 0 | Discontinued |  | Discussed with CDMO and to be re evaluated due to shortage of staff |  |  | Not seen as a feasible activity. Alternatively bedside referalls for consulting doctors were made complusary as part of hospital policy. This increases work time of attendants and cleanining staff in the ward, giving them more time to clean the wards.
Activity 2 | Create a register at every ward to track cleaning to toilets on time. | 2015-03-01 | 2015-03-15 |  | 0
Activity 3 | Add an item on toilet cleanliness on the feedback from and administer it to 3 users per ward every day. | 2014-03-15 | 2014-03-30 |  | 0
Activity 4 | Review user feedback every month create a report and present it to the staff. |  |  |  | 0
Area for improvement: | 1.4 Service users are given food, safe drinking-water and clothing that meet their needs and preferences.
Strategy 1: | Regularly check the drinking water supply with a tds meter | Start Date | End Date | Responsible members | Budget
Activity 1 | Purchase a TDS meter | 2015-05-20 | 2015-05-30 |  | INR 3000 | completed
Activity 2 | Create a list of all drinking water supply in the facility | 2015-05-30 | 2015-05-30 |  | 0 | completed
Activity 3 | Create a tracking sheet for monthly checks of water. | 2015-05-30 | 2015-05-30 |  | 0 | completed
Activity 4 | Create a monthly report and submit it to the CDMO | 2015-05-30 | 2015-05-30 |  | 0 | completed
Activity 5 | Follow up repairs when levels indicate contamination. | 2015-05-30 | 2015-05-30 |  | 0 | Completed
Area for improvement: | 1.4 Service users are given food, safe drinking-water and clothing that meet their needs and preferences.
Strategy 2: | Creating a standard menu for food at the facility | Start Date | End Date | Responsible members | Budget
Activity 1 | Meet with the cook and finalize a menu for the facility | 2015-02-15 | 2015-02-20 |  | 0 | Completed
Activity 2 | Print out menu and display it across notice boards at every ward. | 2015-02-20 | 2015-02-20 |  | 0 | Completed
Area for improvement: | 1.4 Service users are given food, safe drinking-water and clothing that meet their needs and preferences.
Strategy 3: | Create a protocol/ policy for cooking hygiene and standards for cooking at the facility. | Start Date | End Date | Responsible members | Budget
Activity 1 | Visit the kitchen as a core team and identify areas of improvement. | 2015-05-25 | 2015-06-05 |  | 0 | Completed
Activity 2 | Refer to cooking standards at other facilities and create a policy at the facility. | 2015-06-05 | 2015-06-20 |  | 0 | In process |  | Contract is to be renewd and new staff is going to be appointed
Activity 3 | Train kitchen staff and nursing staff on the quality standards to be maintained at the facility. | 2015-06-20 | 2015-07-15 |  | 0 | pending | 2015-12-20
Activity 4 | Conduct bi monthly supervision of the cooking and occasional surprise checks of the kitchen and the food being served. | 2015-06-20 | 2015-07-15 |  | 0 | Completed
Area for improvement: | 1.6 The facility provides a welcoming, comfortable, stimulating environment conducive to active participation and interaction.
Strategy 1: | Providing waiting chairs for families to sit outside the wards | Start Date | End Date | Responsible members | Budget
Activity 1 | Make a list of required furniture outside wards. | 2014-06-04 | 2015-06-10 |  | INR 40000 | Completed
Activity 2 | Get approval from CDMO to buy the furniture. | 2014-06-04 | 2015-06-10 |  | 0 | completed
Activity 3 | Purchase and install furniture at respective wards. | 2014-06-04 | 2015-06-10 |  | 0 | completed
Area for improvement: | 1.6 The facility provides a welcoming, comfortable, stimulating environment conducive to active participation and interaction.
Strategy 2: | Create an of leisure in the hospital for caregivers and users | Start Date | End Date | Responsible members | Budget
Activity 1 | Identify space in the hospital for creating a leisure area. | 2015-05-15 | 2015-05-25 |  | 0 | Completed
Activity 2 | Create a map and plan for the area with a list of services with the help of feedback form service users. | 2015-05-25 | 2015-06-20 |  | 0 | Pending | 2015-09-15 | Responsible members were not available to complete activit | Speak with responsible members to complete planningof the space |  | Asked to be put on hold due to issues related to funds. Not timline set as of now. | Will revisit its possibility in the comming meeting.
Activity 3 | Create budget and get it approved by cdmo | 2015-05-20 | 2015-06-30 |  | based on space requirements and funding received by advitisers | Pending | 2015-09-15 | Lack of current hospital resources to set up the area
Activity 4 | Look for sponsors for creating the space. | 2015-07-01 | 2015-07-30 |  | 0 | Pending | 2015-09-30
Activity 5 | Purchase equipment and set up space. | 2015-07-01 | 2015-07-30 |  | 0 | Pending | 2015-10-30
Activity 6 | Create rules and procured for using the space. | 2015-07-01 | 2015-07-30 |  | 0 | Pending | 2015-10-30
Activity 7 | Train watchmen and PRO in rules and procedure in maintaing the space | 2015-07-01 | 2015-07-30 |  | 0 | Pending | 2015-10-30
Area for improvement: | 1.6 The facility provides a welcoming, comfortable, stimulating environment conducive to active participation and interaction.
Strategy 3: | Create a list of services available at the hospital and make it readily available to service users. | Start Date | End Date | Responsible members | Budget
Activity 1 | Compile a list of all the services that are available in the hospital. | 2015-05-15 | 2015-05-30 |  | 0 | completed |  |  |  | 2015-01-20 | Delay in collection all hospital related information | Include additional members from the core team to complete the infomation collection. Get letter issued from CDMO to help facilitate the process.
Activity 2 | Create a brief description of each of the services and inform all hospital staff of these services. | 2015-06-01 | 2015-06-15 |  | 0 | completed |  |  |  | 2015-01-30
Activity 3 | Create brochures and signboards that inform users about the services and have them available at pubic places of the facility. | 2015-06-15 | 2015-07-15 |  | INR 3000 | in process
Activity 4 | Create a procedure to review information and keep it updated. | 2015-06-15 | 2015-07-15 |  | 0 | Pending
Area for improvement: | 1.6 The facility provides a welcoming, comfortable, stimulating environment conducive to active participation and interaction.
Strategy 4: | Create specific roles with Public Relations officers to improve interactions with service users | Start Date | End Date | Responsible members | Budget
Activity 1 | Create a handbook with all information related to the hospital. | 2015-10-01 | 2015-10-15 |  | 0 | Initiated | 2015-09-20 |  | Changed responsible person to Krtik Mistry | 2015-01-20 | Delay in collection all hospital related information | Include additional members from the core team to complete the infomation collection. Get letter issued from CDMO to help facilitate the process.
Activity 2 | Train PRO in giving information related to services in the | 015-10-2015 | 2015-10-30 |  | 0 | Pending
Area for improvement: | 1.6 The facility provides a welcoming, comfortable, stimulating environment conducive to active participation and interaction.
Strategy 5: | Present information to users related to additional services in the area | Start Date | End Date | Responsible members | Budget
Activity 1 | Collect and compile information related to mental health services across Gujarat. | 2015-02-01 | 2015-02-10 |  | 0 | Continuous | 2015-08-08 | Access to govenrmental mentla hospitals were available. Other services are being accessed.
Activity 2 | Department meet to decide and sort out a resource list. | 2015-06-10 | 2015-06-15 |  | 0 | completed | 2015-08-15
Activity 3 | Consolidate sorted information and print | 2015-06-15 | 2015-06-30 |  | INR 2000 | completed | 2015-08-15
Activity 4 | Distribute list to all Department staff | 2015-07-01 | 2015-07-10 |  | 0 | completed | 2015-08-20
Activity 5 | Add information to department information kit. | 2015-07-10 | 2015-07-15 |  | 0 | completed | 2015-08-21
Activity 6 | Create department policy for yearly review of information | 2015-07-15 | 2015-07-30 |  | 0 | Pending | 2015-08-22
Area for improvement: | 1.6 The facility provides a welcoming, comfortable, stimulating environment conducive to active participation and interaction.
Strategy 6: | Create better networks with NGO's and schools that provide rehabilitation services. | Start Date | End Date | Responsible members | Budget
Activity 1 | Compile a list of special schools and NGO's in the area. | 2015-02-01 | 2015-02-10 |  | 0 | Continuous | These activities have started . However they have not been happening at regular intervals.
Activity 2 | Shortlist relevant organizations and contact one person from the Organization | 2015-02-10 | 2015-02-28 |  | 0 | Continuous
Activity 3 | Invite/visit Organizations to present their work to the Department. | 2015-06-01 | 2015-06-30 |  | 0 | Continuous
Activity 4 | Create a visit schedule for the year | 2015-07-01 | 2015-07-10 |  | to be added as part of department travel expenditure | Pending
Activity 5 | Get visits approved by CDMO | every month |  |  | 0 | Continuous
Activity 5 | Add monthly visits to the Departmental policy | 2015-08-30 | 2015-08-10 |  | 0 | Continuous
Activity 6 | Organize a common meeting for all the NGO's in the district and create a network to refer users and caregivers. |  |  |  | 1000 | Continuous
Area for improvement: | 2.2 The facility has skilled staff and provides good-quality mental health services.
Strategy 1: | Training staff in providing psychosocial care | Start Date | End Date | Responsible members | Budget
Activity 1 | Request training form QualityRights team/ HMH-A on psychosocial rehabilitation | 2015-05-20 | 2015-06-10 |  | 0 | Completed |  | This activity was changed to a departmental activity. Weekly, thechniques and strategies of psychosocial care will be discussed in the departmental meetings to create a peer learning process in the department.
Activity 2 | Finalize training dates with QR team/ HMH-A | 2015-06-10 | 2015-06-15 |  | 0 | Discontinued
Activity 3 | Send staff for training | 2016-07-15 | 2016-07-30 |  | INR1000 | Discontinued
Activity 4 | Add training material to departmental training kit | 2016-07-15 | 2016-07-15 |  | 0 | Completed
Activity 5 | Conduct "refresher" trainings with members in the department every 6 months. |  |  |  | 0
Area for improvement: | 2.2 The facility has skilled staff and provides good-quality mental health services.
Strategy 2: | Train staff for using recovery plans | Start Date | End Date | Responsible members | Budget
To be addressed by QualtyRigths training.
Area for improvement: | 2.2 The facility has skilled staff and provides good-quality mental health services.
Strategy 3: | Using measures of recovery for users | Start Date | End Date | Responsible members | Budget
Activity 1 | Collect information related to various useful and culturally relevant measures of recovery | 2015-10-01 | 2015-10-15 |  |  | Discontinued | Team decided not to do the activity after recovery training.
Activity 2 | Meet as a department(after recovery training) to decide best measure to be used. | 2015-10-15 | 2015-10-30 |  |  | Discontinued
Activity 3 | Decide procedures and policies regarding use of recovery measurement | 2015-10-15 | 2015-10-30
Area for improvement: | 2.2 The facility has skilled staff and provides good-quality mental health services.
Strategy 4: | Developing a team approach | Start Date | End Date | Responsible members | Budget
Activity 1 | Organize a physical space for each speciality(CP, Psychiatrist, MHW) with necessary requirements(lan and electrical)connection. | 2015-05-15 | 2015-05-30 |  |  | Completed
Activity 2 | Systematically collect information form users including demographic data, psychological evaluation, psychiatric workup and treatment plan | 2015-05-15 | 2015-05-30 |  |  | Completed
Activity 3 | Select a 2 cases for discussion every week | 2015-05-30 | 2015-06-30 |  |  | Completed
Activity 4 | Discuss cases and decide future actions of treatment every Friday or Saturday. | 2015-06-15 | 2015-06-30 |  |  | Continuous
Activity 5 | Take feedback from staff regarding the plan and its implementation. | 2015-07-01 | 10-107-15 |  |  | Continuous
Area for improvement: | 2.2 The facility has skilled staff and provides good-quality mental health services.
Strategy 5: | Following up dropped out cases | Start Date | End Date | Responsible members | Budget
Activity 1 | Collect identifying information about users(address, online numbers) |  | 10th May |  |  | Completed
Activity 2 | Sort necessary information and create a system to identify users who have not followed up for | 2015-05-15 | 2015-06-01 |  |  | Completed
Activity 3 | Check to see of HMIS or excel has programs that will help track drop outs | 2015-05-15 | 2015-06-01
Activity 4 | Designate one person to maintain records and call patients. | 2015-05-15 | 2015-06-01 |  |  | Completed
Activity 5 | Ask CDMO permission to user CUG cards to making calling through hospital phone. | 2015-05-15 | 2015-06-01 |  |  | Completed
Activity 6 | Initiate follow up calls for the month . | 2015-05-15 | 2015-06-01 |  |  | Completed | 2015-12-15 | Lack of effective data collection | Address this in the upcoming meeting as a barrier to implementing activity | CHECK with ART department for systems of follow up
Activity 7 | Create departmental policy based on staff and user feedback of the process. | 2015-05-15 | 2015-06-30 |  |  | Pendng | 2015-12-15
Activity 8 | inform staff of the finalized policy and create producers to maintain the process(reports of calls made, reports of users that dropped out) |  |  |  |  | Pending
Area for improvement: | 2.2 The facility has skilled staff and provides good-quality mental health services.
Strategy 6: | Train Departmental staff on Mental Illness and Stigma | Start Date | End Date | Responsible members | Budget
Activity 1 | Prepare training module for doctors and other hospital staff | 2015-05-10 | 2015-06-20 |  |  | Alternate strategy adopted |  |  |  | 2015-12-20 | It was decided that the staff will be given information about identification of mental illness. A poster will be set placed at every doctors table that helps them identify symptoms and make adequate referrals. | Check dMHP materia for informmation
Activity 2 | Prepare a hospital protocol in assessment, diagnosis , treatment and referral. | 2015-06-20 | 2015-07-05 |  |  | Completed |  |  |  | 2015-12-20
Activity 3 | Decide staff to be trained and create a training schedule | 2015-07-05 | 2015-07-20 |  |  | Discontinued
Activity 4 | Take feedback from training and conduct follow up to monitor changes related to training. | 2015-07-20 | 2015-08-20 |  |  | Discontinued
Area for improvement: | 2.2 The facility has skilled staff and provides good-quality mental health services.
Strategy 7: | Informing service users about illness, treatment and options through groups meetings. | Start Date | End Date | Responsible members | Budget
Activity 1 | Create a group module on all illness, diagnosis, treatment methods, prevalence and general tips , health information and self care methods. | 2015-06-01 | 2015-06-20 |  | 0 | Completed
Activity 2 | Review and correct data with staff. | 2015-06-20 | 2015-06-25 |  | 0 | Completed
Activity 3 | Conduct a pilot presentation with department staff | 2015-06-25 | 2015-06-30 |  | 0 | Completed
Activity 4 | Create a monthly schedule for meetings. | 2015-06-10 | 2015-07-10 |  | 0 | Completed
Activity 5 | Inform service users about the dates and times of the meeting. | 2015-06-10 | 2015-07-10 |  | 0 | Completed
Activity 6 | Follow up with monthly meetings. |  |  |  | 0 | Continuous
Area for improvement: | 2.2 The facility has skilled staff and provides good-quality mental health services.
Strategy 7: | Use validated screening tools in screening for mental illness | Start Date | End Date | Responsible members | Budget
Activity 1 | Discuss and identify areas that require screening tool to be used on different population. | 2015-06-01 | 2015-06-20 |  | 0 | Completed
Activity 2 | Collect and translate the tools that are to be used. | 2015-06-20 | 2015-06-25 |  | 0 | Completed
Activity 3 | Create guidelines and documentation forms on how and when the tools are to be used. | 2015-06-25 | 2015-06-30 |  | 0 | Completed
Activity 4 | Create policies to annually review the tools . | 2015-06-10 | 2015-07-10 |  | 0 | Completed
Area for improvement: | 2.2 The facility has skilled staff and provides good-quality mental health services.
Strategy 8: | Creating a feedback from and process for users | Start Date | End Date | Responsible members | Budget
Activity 1 | Discuss the feedback questions with dept. staff | 2015-05-10 | 2015-05-22 |  | 0 | Completed
Activity 2 | Decide measures of feedback(rating / Questionnaire) | 2015-05-22 | 2015-05-30 |  | 0 | Completed
Activity 3 | Buy a suggestion box. | 2015-05-30 | 2015-06-15 |  | INR500 | Completed
Activity 4 | Create a process for reviewing suggestion | 2015-06-15 | 2015-06-23 |  | 0 | Completed
Activity 5 | Conduct a pilot study with the questionnaire and record feedback. | 2015-06-23 | 2015-07-25 |  | 0 | Completed
Activity 6 | Rectify issues during pilot and begin regular collection of feedback | 2015-06-25 | 2015-06-30 |  | 0 | Completed
Area for improvement: | 2.2 The facility has skilled staff and provides good-quality mental health services.
Strategy 9: | Create a token system of feedback | Start Date | End Date | Responsible members | Budget
Activity 1 | Design a detailed process for the token system. | 2015-05-15 | 2015-05-25 |  | 0 | Pending | On hold due to difficulty in implementation
Activity 2 | Arrange boxes for patients to insert tokens in | 2015-05-25 | 2015-05-30 |  | INR 1000 | Pending
Activity 3 | Create a procedure to review the token count on a weekly basis. | 2015-05-30 | 2015-06-10 |  | 0 | Pending
Strategy 1: | Present information to users related to additional services in the area | Start Date | End Date | Responsible members
Area for improvement: | 2.4 Psychotropic medication is available, affordable and used appropriately.
Strategy 1: | Creating a procedure to get a list of available medicines from pharmacy | Start Date | End Date | Responsible members | Budget
Activity 1 | Make a list of essential drugs needed at the facility. | 2015-02-01 | 2015-02-10 |  | 0 | Completed
Activity 2 | Identify government officials responsible for supply of drugs and make a formal request. | 2015-02-10 | 2015-02-20 |  | 0 | Completed
Area for improvement: | 2.4 Psychotropic medication is available, affordable and used appropriately.
Strategy 2: | Creating a procedure to get a list of available medicines from pharmacy | Start Date | End Date | Responsible members | Budget
Activity 1 | Ask pharmacy to share a list of available medicines every week to the department | 2015-02-01 | 2015-02-01 |  | 0 | Completed
Activity 2 | meet with CDMO and systems manager to make list available on the HIMIS | 2015-05-20 | 2015-05-30 |  | 0 | Pending
Activity 3 | Integrate pharmacy entry of drug list into hospital policy | 2015-05-30 | 2015-06-30 |  | 0 | Pending
Activity 4 | Review stock of psychiatric medication on HMIS on a weekly basis and send reminder to pharmacy to order low stock drugs. | 2015-06-30 | 2015-07-15 |  | 0 | Pending
Activity 5 | Make a medicine stock request sheet to regularly monitor the quantity available at the facility. | 2015-05-20 | 2015-05-30 |  | 0 | completed
Activity 6 | Send weekly stock checks to identify medicines that are low in stock and request new medicine stock in advance. | 2015-05-01 | 2015-05-30 |  | 0 | Initiated
Area for improvement: | 2.4 Psychotropic medication is available, affordable and used appropriately.
Strategy 3: | Create networks with other hospitals to look for alternate supply of medication | Start Date | End Date | Responsible members | Budget
Activity 1 | Contact other hospital to ask for their source of medicine supply | 2015-02-01 | 2015-02-10 |  | 0 | Strategy discontinued
Activity 2 | Meet with CDMO to discuss creation of medicine support links with other hospital. | 2015-02-01 | 2015-02-10 |  | 0
Area for improvement: | 2.4 Psychotropic medication is available, affordable and used appropriately.
Strategy 4: | Inform users about treatment options | Start Date | End Date | Responsible members | Budget
Activity 1 | Make a list of possible treatment for Mental illness |  | 2015-05-11 |  | 0 | Completed
Activity 2 | Create a description of the treatment in a simple way with an example so that patients understand their options | 2015-05-11 | 2015-05-26 |  | 0 | Completed
Activity 3 | Review the information sheet and make changes | 2015-05-26 | 2015-05-30 |  | 0 | Completed
Activity 4 | Type out final flyer with the information | 2015-05-30 | 2015-06-05 |  | 0 | Completed
Activity 5 | Create a protocol of informing users | 2015-06-05 | 2015-06-05 |  | 0 | Pending | Activity cancelled | Create a flow chart with basic information to be given by each staff membber to patient
Activity 6 | Disseminate information with the staff | 2015-06-05 | 2015-06-10 |  | 0 | Completed
Activity 7 | Train staff in giving the information to users | 2015-06-10 | 2015-06-10 |  | 0 | Completed
Area for improvement: | 3.4 Service users have the right to confidentiality and access to their personal health information.
Strategy 5: | Train staff in using HMIS to create individual files for users and document daily activities | Start Date | End Date | Responsible members | Budget
Activity 1 | Request CDMO to provide a computer at the department to manage data | 2015-02-01 | 2015-02-01 |  | 0 | completed
Activity 2 | Meet with system manager to identify barriers | 2015-05-02 | 2015-05-10 |  | 0 | completed
Activity 3 | Contact TCS to train staff in HMIS data management | 2015-06-10 | 2015-06-15 |  | 0 | Pending | 2015-09-11 | Requires coordination with all staff at a facility level. There is a great reluctance to use computers by staff and lack of computers available at every department to implement HMIS as a regular process.
Activity 4 | Conduct an one day onsite training for dept. staff | 01-062015 | 2015-06-15 |  | 0 | Pending
Activity 5 | Ask hospital systems manager for additional support for managing data. | 2015-06-02 | 2015-06-16 |  | 0 | Pending
Activity 6 | Track internal referrals though HMIS |  |  |  |  | Pending
Area for improvement: | 3.4 Service users have the right to confidentiality and access to their personal health information.
Strategy 6: | Train staff in explaining side effects of drugs to users | Start Date | End Date | Responsible members | Budget
Activity 1 | Make a list of side effects of all drugs prescribed at the department. |  |  |  |  | Completed |  | Was taken up as a "all facility" issue. Pending due to lack of clarity on staff side how much information needs to given to service users.
Activity 2 | Ask Dr. for support in content for information related to drugs and how to present it to users. |  |  |  |  | Completed
Activity 3 | Print and display side effects of medication across OPD and every IPD |  |  |  |  | Completed
Activity 4 | Train staff in explaining side effects of drugs to users |  |  |  |  | Pending
Activity 5 | Add explanation of side effects to the exit feedback /checklist form.
Area for improvement: | 3.4 Service users have the right to confidentiality and access to their personal health information.
Strategy 7: | Design and use a detailed case file for users | Start Date | End Date | Responsible members | Budget
Activity 1 | Create a Socio demographic profile for collecting information by referring to other online resources |  | 2015-05-12 |  |  | Completed
Activity 2 | Pilot using the form with users. | 2015-05-12 | 2015-05-20 |  |  | Completed
Activity 3 | Address problems related to implementation of forms from pilot | 2015-05-20 | 2015-05-25 |  |  | Completed
Activity 4 | Meet with staff to finalize the form and begin regular implementation with patients. | 2015-05-25 | 2015-05-30 |  |  | Completed
Activity 5 | Collect case papers that are with users over a period of 2 months. | 2015-05-30 | 2015-06-01 |  |  | Completed
Activity 6 | Develop a counselling case history sheet | 2015-06-01 | 2015-06-10 |  |  | Completed
Activity 7 | Develop clinical intake sheet | 2015-06-01 | 2015-06-10 |  |  | Completed
Activity 8 | Apply to purchase files and filing cabinet. | 2015-06-01 | 2015-04-10 |  |  | Completed
Activity 9 | Install filing system and train staff in using the filing system | 2015-06-01 | 2015-06-15 |  |  | Completed
Area for improvement: | 3.4 Service users have the right to confidentiality and access to their personal health information.
Strategy 8: | Develop policy on confidentially and train staff on it. | Start Date | End Date | Responsible members | Budget
Activity 1 | Collect information regarding policies adopted in other hospitals(HMH-a, HMH-v) |  | 10th May |  |  | Completed
Activity 2 | Create a departmental policy and review it with the staff. | 2015-06-01 | 2015-06-10 |  |  | Completed
Activity 3 | Finalize policy and seek approval form Hospital authority. | 2015-06-10 | 2015-06-15 |  |  | Completed
Activity 4 | Train staff on policy and create necessary structures to maintain confidentiality. | 2015-06-15 | 2015-06-20 |  |  | completed
Area for improvement: | 5.1 Service users are supported in gaining access to a place to live and have financial resources necessary to live in the community.
Strategy 1: | Train Mental health worker in dealing with social issues | Start Date | End Date | Responsible members | Budget
Activity 1 | Finalize content of training with HMH- A staff | 2015-05-15 | 2015-05-30 |  |  | Completed | 2015-11-10
Activity 2 | Get permission from both hospital heads to conduct training programmes. | 2015-05-30 | 2015-06-15 |  |  | Completed | 2015-11-15 | Conducted during inter site visit
Activity 3 | Conduct training at a convenient location. | 2015-06-15 | 2015-06-15 |  |  | Completed | 2015-11-20
Activity 4 | Create outcome actions and services for change in OPD. | 2015-06-15 | 2015-07-15 |  |  | completed | 2015-11-30
Area for improvement: | 5.1 Service users are supported in gaining access to a place to live and have financial resources necessary to live in the community.
Strategy 2: | Creating a brochure with information about NGO's and Rehabilitation | Start Date | End Date | Responsible members | Budget
Activity 1 | Collect information about NGO's in Mahesana |  | 2015-05-11 |  |  | Continuous
Activity 2 | Collection information about NGO's working for users with mental illness and de addiction (net surfing and samaj suraksha) |  | 2015-05-15 |  |  | Continuous
Activity 3 | Collect all information into single file and create a record sheet |  | 2015-05-15 |  |  | Continuous
Activity 4 | Create a questionnaire to collect information from NGO. |  | 2015-05-11 |  |  | Continuous
Activity 5 | Review and finalize forms . |  | 2015-05-15 |  |  | Completed
Activity 6 | Call/ visit NGO's and collect the information form the list of NGO's |  | 2015-05-19 |  |  | Completed
Activity 7 | Consolidate information into file and regularly train staff in the information. |  | 2015-05-25 |  |  | Pending | 2015-01-10 | Delayed due to only few NGo's response to aequate infomation. | The infomation will be consolidate after an aequate number of NGO's information has been collected
Activity 8 | Summarize the information and give it for typing. |  | 2015-05-27 |  |  | Pending | 2015-01-15
Activity 9 | Design and finalize brochure |  | 2015-06-05 |  |  | Pending | 2015-01-20
Area for improvement: | 5.1 Service users are supported in gaining access to a place to live and have financial resources necessary to live in the community.
Strategy 3: | Informing users of available government and community resources | Start Date | End Date | Responsible members | Budget
Activity 1 | Compile a list of available resources(govt grants, etc) | 2015-02-01 | 2015-02-28 |  |  | Completed
Activity 2 | Create a standard format of details related to each resource(eg: Name of org, contact person, documents needed to access grant etc) | 2015-03-01 | 2015-03-10 |  |  | Completed
Activity 3 | Train all department staff about the details and how it can be accessed | 2015-03-10 | 2015-03-20 |  |  | Continuous
Activity 4 | Add information department kit | 2015-03-20 | 2015-03-30 |  |  | Continuous
Activity 5 | Create a policy to revise information every year. | 2015-07-10 | 2015-07-20 |  |  | Continuous
Activity 6 | Create a poster with these details and paste in in the waiting area. | 2015-07-10 | 2015-07-20 |  |  | Continuous
Activity 7 | Create a set of brochures with this information to be give out to users | 2015-07-10 | 2015-07-20 |  |  | pending
Activity 8 | Add explanation of community resources to the exit feedback /checklist form. | 2015-07-10 | 2015-07-20 |  |  | completed
Area for improvement: | 4.1Service users have the right to be free from verbal, mental, physical and sexual abuse and physical and emotional neglect.
Develop a hospital wide policy to adress this issue
Area for improvement: | 4.2 Alternative methods are used in place of seclusion and restraint as means of deescalating potential crises.

## Facility3a
Area for improvement: 1.3
Strategy: | Cleaning of Toilets & Bathroom in ward. | Start Date | End Date | Responsible members | Budget | Status- Pending/Complete
Activity 1 | Discuss the issues with ward staff. Identify the issues related to maintaining cleanliness.
Activity 2 | Call BVG contractor
Activity 3 | Presentation of problems by ward staff regarding cleanliness of ward and toilets. Listening to contractor’s hurdles in providing service.
Activity 4 | Send official letter to BVG contractor through proper channel, for cleaning J-0 ward instead of H-0.
Activity 5 | Take follow up of the application
Activity 6 | Sign on the cleaning schedule sheet given by the BVG contractor for their punctuality for cleaning activity.
Activity 7 | Make the file of the sheet
Activity 8 | Monthly feedback and report writing to the contractor
Activity 9 | Assure the availability of cleaning material one day in advance.
Activity 10 | Feedback from the patients randomly about cleaning.
Activity 11 | Stick information in ward and toilets for keeping them clean and nit.
Activity 12 | Put doormats at entrance of each toilet.
Activity 13 | Arranging mugs and buckets for the service users’ use.
Activity 14 | Put air fresheners in toilets
Activity 15
Activity 16
Activity 17
Activity 18
Activity 19
Activity 20
Area for improvement: 1.3
Strategy: | Cleaning of Toilets & Bathroom in OPD. | Start Date | End Date | Responsible members | Budget
Activity 1 | Discuss the issues with OPD staff. Identify the issues related to maintaining cleanliness.
Activity 2 | Call BVG contractor
Activity 3 | Presentation of problems by OPD staff regarding cleanliness of OPD and toilets. Listening to contractor’s hurdles in providing service.
Activity 4 | Sign on the cleaning schedule sheet given by the BVG contractor for their punctuality for cleaning activity.
Activity 5 | Make the file of the sheet
Activity 6 | Monthly feedback and report writing to the contractor
Activity 7 | Assure the availability of cleaning material one day in advance.
Activity 8 | Feedback from the patients and staff randomly about cleaning.
Activity 9 | Stick information in OPD and toilets for keeping them clean and nit.
Activity 10 | Put doormats at entrance of each toilet.
Activity 11 | Arranging mugs and buckets for the service users’ use.
Activity 12 | Put air fresheners in toilets
Activity 13
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18
Area for improvement: 1.4
Strategy: | Providing good quality and safe drinking water to service users in ward. | Start Date | End Date | Responsible members | Budget
Activity 1 | Demand water cooler and reverse osmosis system from PIU through proper channel
Activity 2 | Send application to concerned authority through proper channel.
Activity 3 | Take follow up of the proceedings. (Application, supply of demanded things, installation.)
Activity 4 | Establish system for checking if the machines are working properly.
Activity 5 | Establish system for checking the cleanliness and hygiene.
Activity 6 | Feedback from service users and staff randomly.
Activity 7 | Arranging glass for drinking water
Activity 8
Activity 9
Activity 10
Activity 11
Activity 12
Activity 13
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18
Area for improvement: 1.4
Strategy: | Providing good quality and safe drinking water to service users in OPD. | Start Date | End Date | Responsible members | Budget
Activity 1 | Demand water cooler and reverse osmosis system from PIU through proper channel
Activity 2 | Send application to concerned authority through proper channel.
Activity 3 | Take follow up of the proceedings. (Application, supply of demanded things, installation.)
Activity 4 | Establish system for checking if the machines are working properly.
Activity 5 | Establish system for checking the cleanliness and hygiene.
Activity 6 | Feedback from service users and staff randomly.
Activity 7 | Arranging glass for drinking water
Activity 8
Activity 9
Activity 10
Activity 11
Activity 12
Activity 13
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18
Area for improvement: 1.4
Strategy: | Providing good quality and safe food according to choice of service users in ward. | Start Date | End Date | Responsible members | Budget
Activity 1 | Fill the already existing feedback form from the service users.
Activity 2 | Providing utensils (plates and spoons) to service users
Activity 3 | Provide information about availability of food to users and care givers on display board
Activity 4 | Consult with dietician for monotony of food especially in the evening
Activity 5 | Feedback from users after changing food menu after meeting as discussed in activity 4
Activity 6
Activity 7
Activity 8
Activity 9
Activity 10
Activity 11
Activity 12
Activity 13
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18
Area for improvement: 1.4
Strategy: | Provision of clothes and sanitary pads. | Start Date | End Date | Responsible members | Budget
Activity 1 | Collect the donated clothes. And keep stock of sanitary pads.
Activity 2 | Keep stock of the clothes with proper cleaning and ironing with maintenance of register.
Activity 3 | Ensure delivery of such clothes to needful by taking feedback randomly.
Activity 4
Activity 5
Activity 6
Activity 7
Activity 8
Activity 9
Activity 10
Activity 11
Activity 12
Activity 13
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18
Area for improvement: 3.1
Strategy: | Service user preference for decision making of receiving treatment | Start Date | End Date | Responsible members | Budget
Activity 1 | Discuss the issue with madam and other colleagues about the problem.
Activity 2 | Search for some data available for their subject on internet or other sources
Activity 3 | Make basic points for what should be covered.
Activity 4 | Make a temporary Performa for given options to patient for plane of treatment and type of treatment available of facility
Activity 5 | Final the Performa after discussion with the committee for implementation
Activity 6 | Covert it in to other common languages
Activity 7 | Make a policy for how to implement and how to keep its record
Activity 8 | Get print and make copies of it which can be useful for next 6 months.
Activity 9
Activity 10
Activity 11
Activity 12
Activity 13
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18
Area for improvement: 2.4
Strategy: | Make list of essential drugs | Start Date | End Date | Responsible members | Budget
Activity 1 | Gather the information from various sources regarding list of essential drugs | 2015-02-24 | 2015-03-04 |  | NIL
Activity 2 | Sort and define the list which is to be and printed out displayed | 2015-03-03 | 2015-03-20 |  | NIl
Activity 3 | Send the list to make the display chart | 2015-03-20 | 2015-03-22 |  | 3000 per chart, total 2= 6000
Activity 4 | apply the chart on the dispensory window with help of PIU | 2015-03-23 | 2015-03-25 |  | NIL
Activity 5
Activity 6
Activity 7
Activity 8
Activity 9
Activity 10
Activity 11
Activity 12
Activity 13
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18
Area for improvement:2.4
Strategy: | Assure continuous supply of the medicines | Start Date | End Date | Responsible members | Budget
Activity 1 | gather information from HMH Ahmedabad and Baroda that how are they manging constant supply | 2015-03-01 | 2015-03-05 |  | NIL
Activity 2 | adopt the applicable things to the current setup | continuous |  |  | NIL
Activity 3 | Make the list of the drugs dispensed per week | every week |  |  | NIL
Activity 4 | review of the above mentioned list | fortnightly |  |  | NIL
Activity 5 | presenting to superintendent about issues in the supply of medicines | once a month |  |  | NIL
Activity 6 | If no help from administration than arrange alternative souce of medicines e.g. through donation. |  |  |  | NIL
Activity 7 | keep the stock register and dispensing register |  |  |  | NIL
Activity 8
Activity 9
Activity 10
Activity 11
Activity 12
Activity 13
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18
Area for improvement:2.4
Strategy: | explaining information to users about medicines | Start Date | End Date | Responsible members | Budget
Activity 1 | prepare drugs information pamphlet with the help of interns | 2015-02-19 | 2015-03-09 |  | NIL
Activity 2 | take sufficient print out of the pamphlets | as and when required |  |  | NIL
Activity 3 | train the internees on the joining about their role in explaining effects, side effects, indications etc about medicines | every 15th day when new batch of internees join |  |  | NIL
Activity 4 | for above mentioned training to be given, training of resident doctors | once in 6 month |  |  | NIL
Activity 5 | assuring that each new service user is getting those pamphlets and being informed | everyday |  |  | NIL
Activity 6 | on follow up ask every users about the information retained from last session | in each follow up of service user |  |  | NIL
Activity 7 | re instruct service users | as and when required |  |  | NIL
Activity 8 | feed back from the users | once in a 6 months |  |  | NIL
Activity 9 | involving feedback in the recent work | once in a 6 months |  |  | NIL
Activity 10
Activity 11
Activity 12
Activity 13
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18
Area for improvement:2.3
Strategy: | providing information about and refering service users to available habilitaion and rehabilitation services | Start Date | End Date | Responsible members | Budget
Activity 1 | prepare the list of available habilitation services in and in surrounding of the city | 2015-02-25 | 2015-03-05 |  | NIL
Activity 2 | for preparing the list take help from NGO, HMH and other bodies | 2015-02-25 | 2015-03-05 |  | NIL
Activity 3 | sort out the list of the bodies who are ready to establish linkage with our facility | 2015-03-06 | 2015-03-07 |  | NIL
Activity 4 | conduct a training on how to Disseminate this information to service users | to be decided |  |  | NIL
Activity 5 | start implementing | after training |  |  | NIL
Activity 6 | make the register and maintain data for those users who have been refereed to such linked services | to be decided |  |  | NIL
Activity 7
Activity 8
Activity 9
Activity 10
Activity 11
Activity 12
Activity 13
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18
Area for improvement:2.3
Strategy: | making structure of recovery plan for individuals with severe mental illness | Start Date | End Date | Responsible members | Budget
Activity 1 |  |  |  |  | NIL
Activity 2 |  |  |  |  | NIL
Activity 3 |  |  |  |  | NIL
Activity 4 |  |  |  |  | NIL
Activity 5 |  |  |  |  | NIL
Activity 6 |  |  |  |  | NIL
Activity 7
Activity 8
Activity 9
Activity 10
Activity 11
Activity 12
Activity 13
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18
Area for improvement:2.3
Strategy: | Involving intern doctors in new users' treatment as a guide and helper | Start Date | End Date | Responsible members | Budget
Activity 1 | Joining of interns on 1st day of psychiatry posting. And fill up pre-assessment form. | 2015-02-22 | every time the batch is changed |  | NIL
Activity 2 | Lecture on their duty and role in users treatment | every time the batch is changed |  |  | NIL
Activity 3 | Do physical examination of the patient, take history of patient about chief complains, current illness, any previous illness like D.M., Hypertension, on any medication. | daily |  |  | NIL
Activity 4 | Bring patient to resident. take part in formulating diagnosis and give medication | daily |  |  | NIL
Activity 5 | Give patient pamphlet of that illness. Explain and educate patient about it. Explain about follow up. | daily |  |  | NIL
Activity 6 |  |  |  |  | NIL
Activity 7
Activity 8
Activity 9
Activity 10
Activity 11
Activity 12
Activity 13
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18
Area for improvement:2.3
Strategy: | establish linkage with outside occupation therapt centre | Start Date | End Date | Responsible members | Budget
Activity 1 | gather information regarding availability of OT centre in city and outside city | 2015-03-05 | 2015-03-12 |  | NIL
Activity 2 | Sort out the list with the centre the facility wants to establish linkage | 2015-03-12 | 2015-03-13 |  | NIL
Activity 3 | Contact the desired centre for developing referal system | 2015-03-13 | 2015-04-13 |  | NIL
Activity 4 | make a policy for refering users to such facilities | 2015-03-15 | 2015-03-25 |  | NIL
Activity 5 | maintain a register for such activity | as and when activity done |  |  | NIL
Activity 6 |  |  |  |  | NIL
Activity 7
Activity 8
Activity 9
Activity 10
Activity 11
Activity 12
Activity 13
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18
Area for improvement:2.5
Strategy: | make SOP for treatment of female coming to facility | Start Date | End Date | Responsible members | Budget
Activity 1 | review the available and safest medical treatment options for female | 2015-02-24 | 2015-02-28 |  | NIL
Activity 2 | take reference from the already existing pregnancy registry | 2015-02-24 | 2015-02-28 |  | NIL
Activity 3 | make clear outline for female users (not only pregnant) | 2015-03-01 | 2015-03-05 |  | NIL
Activity 4 | training of all residents for this topic | last week of march |  |  | NIL
Activity 5 |  |  |  |  | NIL
Activity 6 |  |  |  |  | NIL
Activity 7
Activity 8
Activity 9
Activity 10
Activity 11
Activity 12
Activity 13
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18
Area for improvement:5.4
Strategy: | providing leisure activity in ward | Start Date | End Date | Responsible members | Budget
Activity 1 | designate one new room for leisure activities in ward | 2015-02-12 | 2015-02-13 |  | NIL
Activity 2 | enlist the activity which can be done in that room | 2015-02-13 | 2015-02-18 |  | NIL
Activity 3 | collect things to be put in room (e.g. news paper, magazines, carrom board) | 2015-02-15 | 2015-03-15 |  | NIL
Activity 4 | provide the required things |  |  |  | NIL
Activity 5 | define the time and designate a responsible person for conducting this activity |  |  |  | NIL
Activity 6 | make the register for maintaining daily record of activity |  |  |  | NIL
Activity 7
Activity 8
Activity 9
Activity 10
Activity 11
Activity 12
Activity 13
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18
Area for improvement:4.5
Strategy: | prevention of users from torture, cruel, inhuman and degrading treatment from staff or other users | Start Date | End Date | Responsible members | Budget
Activity 1 | make policy for this criterion | 2015-03-02 | 2015-03-10 |  | NIL
Activity 2 | arrange training of resident and other staff | 2015-03-11 | 2015-03-25 |  | NIL
Activity 3 | information dissemination in the form of posters | 2015-03-02 | 2015-03-20 |  | NIL
Activity 4 | establish a complaining system | 2015-03-02 | 2015-03-15 |  | NIL
Activity 5 | documentation of such events including generating incident reporting form | 2015-03-02 | 2015-03-20 |  | NIL
Activity 6 | make intervention committee whenever such incidents are reported | 2015-03-02 | 2015-03-10 |  | NIL
Activity 7
Activity 8
Activity 9
Activity 10
Activity 11
Activity 12
Activity 13
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18
Area for improvement:4.2
Strategy: | decrease the use of physical and chemical restrain | Start Date | End Date | Responsible members | Budget
Activity 1 | review already existing policy for restrain | 2015-03-05 | 2015-03-09 |  | NIL
Activity 2 | create policy to decrease use of restrain | 2015-03-10 | 2015-03-25 |  | NIL
Activity 3 | training for deescalation technique | to be decided |  |  | NIL
Activity 4 | discuss the topic in department with all staff and make revised version of restrain forms | 2015-03-10 | 2015-03-25 |  | NIL
Activity 5 | make the register for documenting restrains | to be decided |  |  | NIL
Activity 6 | monthly audit of the records | monthly |  |  | NIL
Activity 7 | identifying barriers to decrease restrains
Activity 8 | sensitising all staff to the new policy and how to implement | 2015-03-25 | 2015-03-30
Activity 9
Activity 10
Activity 11
Activity 12
Activity 13
Activity 14
Activity 15
Activity 17
Activity 18
Area for improvement:General
Strategy: | to sensitize the nursing staff for QR project and the working protocol in the department | Start Date | End Date | Responsible members | Budget
Activity 1 | prepare module of sensitization for the new joining nursing staff | 2015-03-02 | 2015-03-10 |  | NIL
Activity 2 | make policy for conduction of these module |  |  |  | NIL
Activity 3 |  |  |  |  | NIL
Activity 4 |  |  |  |  | NIL
Activity 5 |  |  |  |  | NIL
Activity 6 |  |  |  |  | NIL
Activity 7
Activity 8
Activity 9
Activity 10
Activity 11
Activity 12
Activity 13
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18
Area for improvement: 5.4
Strategy: | to mount a wall TV in OPD | Start Date | End Date | Responsible members | Budget
Activity 1 | Search for specification of TV needed to be bought | 2015-03-09 | 2015-03-15 |  | NIL
Activity 2 | Apply to superintendent for puchasing TV | 2015-03-15 | 2015-03-17 |  | NIL
Activity 3 | Buy a TV after permission | 2015-03-17 | 2015-03-30 |  | aproximate 40000
Activity 4 | install TV on the wall | 2015-04-01 | 2015-04-05 |  | NIL
Activity 5 |  |  |  |  | NIL
Activity 6 |  |  |  |  | NIL
Activity 7
Activity 8
Activity 9
Activity 10
Activity 11
Activity 12
Activity 13
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18
Area for improvement: 5.1
Strategy: | Giving support in gaining acess to place to live nad have the financial resources | Start Date | End Date | Responsible members | Budget
Activity 1 | collect information about available services in and outside of the city | 2015-03-08 | 2015-03-15 |  | NIL
Activity 2 | compile information and make a list with whom links to be stablished | 2015-03-15 | 2015-03-17 |  | NIL
Activity 3 | make a policy for refering users to such facilities | 2015-03-17 | 2015-03-30 |  | aproximate 40000
Activity 4 | display the information | 2015-04-01 | 2015-04-05 |  | NIL
Activity 5 | do inquiry for RSBY |  |  |  | NIL
Activity 6 | demand collected money from superintendent when money is collected |  |  |  | NIL
Activity 7 | do activity with those money
Activity 8 | make pamplet giving information about such services
Activity 9 | interactive session with such services (half way homes, MR school)
Activity 10 | training of staff regarding giving information for this
Activity 11 | implementation by staff
Activity 12
Activity 13
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18
Area for improvement:5.4:
Strategy: | providing leisure activity in ward | Start Date | End Date | Responsible members | Budget
Activity 1 | make a module for nursing students for providing activities to service users e.g. Physical Exercise, Craft activity | 2015-02-12 | 2015-02-13 |  | NIL
Activity 2 | train the batch of nursing student whenever it is changed | 2015-02-13 | 2015-02-18 |  | NIL
Activity 3 | each nursing student guide and help the designated user in doing leisure activity |  |  |  | NIL
Activity 4 |  |  |  |  | NIL
Activity 5 |  |  |  |  | NIL
Activity 6 |  |  |  |  | NIL
Activity 7
Activity 8
Activity 9
Activity 10
Activity 11
Activity 12
Activity 13
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18
Area for improvement: General
Strategy: | Displaying information and rights chart | Start Date | End Date | Responsible members | Budget
Activity 1 | collect data from sources | 2015-02-23 | 2015-03-10 | all residents | NIL
Activity 2 | take permission from medical superintendent for printing out new wall papers with instructionos and rights chart | 2015-02-23 | 2015-02-18 |  | NIL
Activity 3 | compile data and enlist the materials to be printed |  |  |  | NIL
Activity 4 | give it for print out |  |  |  | NIL
Activity 5 | install on wall |  |  |  | NIL
Activity 6 |  |  |  |  | NIL
Activity 7
Activity 8
Activity 9
Activity 10
Activity 11
Activity 12
Activity 13
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18

## Facility3b
Area for improvement: 1.3 The facility meets hygiene and sanitary requirements
Strategy: | Cleaning of Toilets & Bathroom in ward. | Start Date | End Date | Responsible members | Budget | Status- Pending/Complete | New Deadline (add date of entering) | Explanation for not meeting the deadline | Proposed Plan for meeting new deadlines | Status- Pending/Complete | New Deadline | Explanation for not meeting the deadline | Proposed Plan for meeting new deadlines | Status- Pending/Complete | New Deadline | Explanation for not meeting the deadline | Proposed Plan for meeting new deadlines
Activity 1 | Discuss the issues with ward staff. Identify the issues related to maintaining cleanliness. | 13 February '15 | 13 February '15 |  | NIL | Complete | - |  |  | Complete | - |  |  | Complete
Activity 2 | Call BVG contractor | 13 February '15 | 13 February '15 |  | NIL | Complete | - |  |  | Complete | - |  |  | Complete
Activity 3 | Presentation of problems by ward staff regarding cleanliness of ward and toilets. Listening to contractor’s hurdles in providing service. | 13 February '15 | 13 February '15 |  | NIL | complete | - |  |  | complete | - |  |  | Complete
Activity 4 | Send official letter to BVG contractor through proper channel, for cleaning J-0 ward instead of H-0. | 14 February '15 | 17 February '15 |  | NIL | complete | - |  |  | complete | - |  |  | Complete
Activity 5 | Take follow up of the application | whenever required |  |  | NIL | complete | - |  |  | complete | - |  |  | Complete
Activity 6 | Sign on the cleaning schedule sheet given by the BVG contractor for their punctuality for cleaning activity. | daily |  |  | NIL | complete | - |  |  | complete | - |  |  | Complete
Activity 7 | Make the file of the sheet | File to be made by 17 February '15. filing the sheet daily |  |  | NIL | pending | Not decided yet |  |  | pending | Not decided yet |  |  | continuous
Activity 8 | Monthly feedback and report writing to the contractor | 13 February '15 |  |  | NIL | pending | progressing |  |  | pending | progressing |  |  | continuous
Activity 9 | Assure the availability of cleaning material one day in advance. | daily |  |  | NIL | pending | Not decided yet |  |  | pending | Not decided yet |  |  | continuous
Activity 10 | Feedback from the patients randomly about cleaning. | weekly |  |  | NIL | pending | Not decided yet |  |  | pending | Not decided yet |  |  | continuous
Activity 11 | Stick information in ward and toilets for keeping them clean and nit. | 15 February '15 | 20 February '15 |  | INR 300 PER MONTH | complete | - |  |  | complete | - |  |  | Complete
Activity 12 | Put doormats at entrance of each toilet. | 13 February '15 | 17 February '15 |  | NIL | complete | - |  |  | complete | - |  |  | Complete
Activity 13 | Arranging mugs and buckets for the service users’ use. | 13 February '15 | 20 February '15 |  | NIL | pending | not decided yet |  |  | pending | not decided yet |  |  | Complete
Activity 14 | Put air fresheners in toilets | 13 February '15 | 20 February '15 |  | INR 200 PER MONTH | pending | not decided yet |  |  | pending | not decided yet |  |  | Complete
Area for improvement: 1.3 The facility meets hygiene and sanitary requirements
Strategy: | Cleaning of Toilets & Bathroom in OPD. | Start Date | End Date | Responsible members | Budget | Status- Pending/Complete | New Deadline |  |  | Status- Pending/Complete | New Deadline |  |  | Status- Pending/Complete | New Deadline
Activity 1 | Discuss the issues with OPD staff. Identify the issues related to maintaining cleanliness. | 13 February '15 | 13 February '15 |  | NIL | complete |  |  |  | complete |  |  |  | Complete
Activity 2 | Call BVG contractor | 13 February '15 | 13 February '15 |  | NIL | complete |  |  |  | complete |  |  |  | Complete
Activity 3 | Presentation of problems by OPD staff regarding cleanliness of OPD and toilets. Listening to contractor’s hurdles in providing service. | 13 February '15 | 13 February '15 |  | NIL | complete |  |  |  | complete |  |  |  | Complete
Activity 4 | Sign on the cleaning schedule sheet given by the BVG contractor for their punctuality for cleaning activity. | 14 February '15 | 17 February '15 |  | NIL | complete |  |  |  | complete |  |  |  | Complete
Activity 5 | Make the file of the sheet | File to be made by 17 February '15. filing the sheet daily |  |  | NIL | pending | Not decided yet |  |  | pending | Not decided yet |  |  | continuous
Activity 6 | Monthly feedback and report writing to the contractor | once monthly |  |  | NIL | pending | progressing |  |  | pending | progressing |  |  | continuous
Activity 7 | Assure the availability of cleaning material one day in advance. | daily |  |  | NIL | Complete
Activity 8 | Feedback from the patients and staff randomly about cleaning. | weekly |  |  | NIL | pending | Not decided yet |  |  | pending | Not decided yet |  |  | continuous
Activity 9 | Stick information in OPD and toilets for keeping them clean and nit. | 15 February '15 | 20 February '15 |  | INR 300 PER MONTH | complete | - |  |  | complete | - |  |  | complete
Activity 10 | Put doormats at entrance of each toilet. | 13 February '15 | 17 February '15 |  | NIL | pending |  |  |  | pending |  |  |  | complete
Activity 11 | Arranging mugs and buckets for the service users’ use. | 13 February '15 | 20 February '15 |  | NIL | Complete | [7 empty] | complete
Activity 12 | Put air fresheners in toilets | 13 February '15 | 20 February '15 |  | INR 200 PER MONTH | pending | not decided yet |  |  | pending | not decided yet |  |  | complete
Area for improvement: 1.4 Service users are given food, safe drinking-water and clothing that meet their needs and preferences.
Strategy: | Providing good quality and safe drinking water to service users in ward. | Start Date | End Date | Responsible members | Budget | Status- Pending/Complete | New Deadline |  |  | Status- Pending/Complete | New Deadline |  |  | Status- Pending/Complete | New Deadline
Activity 1 | Demand water cooler and water purifier from Medical Superintendent through proper channel | 16 February '15 | 30 June '15 |  | to be bare by hospital fund | complete |  |  |  | complete |  |  |  | complete
Activity 2 | Send application to concerned authority through proper channel. | 16 February '15 | 18 February '15 |  | NIL | complete |  |  |  | complete |  |  |  | complete
Activity 3 | Take follow up of the proceedings. (Application, supply of demanded things, installation.) | when required |  |  | NIL | complete |  |  |  | complete
Activity 4 | Establish system for checking if the machines are working properly. | 16 February '15 | 30 June '15 |  | NIL | pending |  |  |  | pending
Activity 5 | Establish system for checking the cleanliness and hygiene. | 16 February '15 | 30 June '15 |  | NIL | pendng |  |  |  | pendng
Activity 6 | Feedback from service users and staff randomly. | fortnightly |  |  | NIL | pending |  |  |  | pending
Activity 7 | Arranging glass with chain for drinking water | 16 February '15 | 1 March '15 |  | INR 100 | pending |  |  |  | pending
Area for improvement: 1.4 Service users are given food, safe drinking-water and clothing that meet their needs and preferences.
Strategy: | Providing good quality and safe drinking water to service users in OPD. | Start Date | End Date | Responsible members | Budget | Status- Pending/Complete | New Deadline |  |  | Status- Pending/Complete | New Deadline |  |  | Status- Pending/Complete | New Deadline
Activity 1 | Demand water cooler and water purifier from MS through proper channel | 16 February '15 | 30 June '15 |  | NIL | complete |  |  |  | complete
Activity 2 | Send application to concerned authority through proper channel. | 16 February '15 | 18 February '15 |  | NIL | complete |  |  |  | complete
Activity 3 | Take follow up of the proceedings. (Application, supply of demanded things, installation.) | when required |  |  | NIL | pending | Not decided |  |  | pending | Not decided |  |  | complete
Activity 4 | Establish system for checking if the machines are working properly. | 16 February '15 | 30 June '15 |  | NIL | pending | Slowly progressing |  |  | pending | Slowly progressing |  |  | pending | 10 Jan' 16
Activity 5 | Establish system for checking the cleanliness and hygiene. | 16 February '15 | 30 June '15 |  | NIL | pending | Not decided |  |  | pending | Not decided |  |  | pending | 10 Jan' 16
Activity 6 | Feedback from service users and staff randomly. | fortnightly |  |  | NIL | pending | Not decided |  |  | pending | Not decided |  |  | pending | 12 Jan' 16
Activity 7 | Arranging glass with chain for drinking water | 16 February '15 | 1 March '15 |  | INR 100 | complete partially | not decided |  |  | complete partially | not decided |  |  | complete
Area for improvement: 1.4 Service users are given food, safe drinking-water and clothing that meet their needs and preferences.
Strategy: | Providing good quality and safe food according to choice of service users in ward. | Start Date | End Date | Responsible members | Budget | Status- Pending/Complete | New Deadline |  |  | Status- Pending/Complete | New Deadline |  |  | Status- Pending/Complete | New Deadline
Activity 1 | Fill the already existing feedback form from the service users. | daily |  |  | NIL | pending | Not decided |  |  | pending | Not decided |  |  | continuous- started
Activity 2 | Providing utensils (plates and spoons) to service users | 16 February '15 | 16 March '15 |  | NIL | pending | Not decided |  |  | pending | Not decided |  |  | continuous- started
Activity 3 | Provide information about availability of food to users and care givers on display board | 16 February '15 | 15 July '15 |  | NIL | pending | Not decided |  |  | pending | Not decided |  |  | complete
Activity 4 | Consult with dietician for monotony of food especially in the evening | 16 February '15 | 20 June '15 |  | NIL | pending | Not decided |  |  | pending | Not decided |  |  | pending | 10 Jan' 16
Activity 5 | Feedback from users after changing food menu after meeting as discussed in activity 4 | 16 February '15 | 20 June '15 |  | NIL | pending | Not decided |  |  | pending | Not decided |  |  | continuous- started
Area for improvement: 1.4 Service users are given food, safe drinking-water and clothing that meet their needs and preferences.
Strategy: | Provision of clothes and sanitary pads. | Start Date | End Date | Responsible members | Budget | Status- Pending/Complete | New Deadline |  |  | Status- Pending/Complete | New Deadline |  |  | Status- Pending/Complete | New Deadline
Activity 1 | Collect the donated clothes. And keep stock of sanitary pads. | 14 February '15 | daily |  | NIL | complete |  |  |  | complete
Activity 2 | Keep stock of the clothes with proper cleaning and ironing with maintenance of register. | daily |  |  | NIL | pending | Not decided |  |  | pending | Not decided |  |  | continuous- started
Activity 3 | Ensure delivery of such clothes to needful by taking feedback randomly. | forrtnightly |  |  | NIL | pending | Not decided |  |  | pending | Not decided |  |  | continuous- started
Area for improvement: 3.1 Service users’ preferences regarding the place and form of treatment are always a priority
Strategy: | Service user preference for decision making of receiving treatment | Start Date | End Date | Responsible members | Budget | Status- Pending/Complete | New Deadline |  |  | Status- Pending/Complete | New Deadline |  |  | Status- Pending/Complete | New Deadline
Activity 1 | Discuss the issue with madam and other colleagues about the problem. | 26 February '15 | 4 April '15 |  | NIL | pending | Not decided |  |  | pending | Not decided |  |  | complete
Activity 2 | Search for some data available for this subject on internet or other sources | 26 February '15 | 16 April '15 |  | NIL | pending | Not decided |  |  | pending | Not decided |  |  | complete
Activity 3 | Make basic points for what should be covered. | 26 February '15 | 30 June '15 |  | NIL | pending | Not decided |  |  | pending | Not decided |  |  | complete
Activity 4 | Make a temporary Performa for given options to patient for plane of treatment and type of treatment available of facility | 20 July '15 | 10 July '15 |  | NIL | pending | Not decided |  |  | pending | Not decided |  |  | ongoing
Activity 5 | Finalize the Performa after discussion with the committee for implementation | 10 July '15 | 15 July '15 |  | NIL | pending | Not decided |  |  | pending | Not decided |  |  | pending | 2nd Feb'16
Activity 6 | Cover it in to other common languages | 15 July '15 | 05 August '15 |  | NIL | pending | Not decided |  |  | pending | Not decided |  |  | ongoing
Activity 7 | Make a policy for how to implement and how to keep its record | 15 July '15 | 30 July '15 |  | NIL | pending | Not decided |  |  | pending | Not decided |  |  | pending | 5 Jan'16
Activity 8 | Get print and make copies of it which can be useful for next 6 months. | as and when required |  |  | INR 5000 every 3 months | pending | Not decided |  |  | pending | Not decided |  |  | pending | 20 Feb'16
Area for improvement: 2.4 Psychotropic medication is available, affordable and used appropriately.
Strategy: | Make list of essential drugs | Start Date | End Date | Responsible members | Budget | Status- Pending/Complete | New Deadline |  |  | Status- Pending/Complete | New Deadline |  |  | Status- Pending/Complete | New Deadline
Activity 1 | Gather the information from various sources regarding list of essential drugs | 24 February '15 | 4 March '15 |  | NIL | complete |  |  |  | complete
Activity 2 | Sort and define the list which is to be and printed out displayed | 3 March '15 | 10 June '15 |  | NIl | complete |  |  |  | complete
Activity 3 | Send the list to make the display chart | 20 March '15 | 30 June '15 |  | INR 3000 per chart, total 2= INR 6000 | pending | Not decided |  |  | pending | Not decided |  |  | ongoing | 6 Jan'16
Activity 4 | apply the chart on the dispensary window with help of PIU | 23 March '15 | 5 July '15 |  | NIL | pending | NOt decided |  |  | pending | NOt decided |  |  |  | 12 Jan'16
Area for improvement: 2.4 Psychotropic medication is available, affordable and used appropriately.
Strategy: | Assure continuous supply of the medicines | Start Date | End Date | Responsible members | Budget | Status- Pending/Complete | New Deadline |  |  | Status- Pending/Complete | New Deadline |  |  | Status- Pending/Complete | New Deadline
Activity 1 | gather information from HMH on how are they manging constant supply | 1 March '15 | 5 March '15 |  | NIL | complete |  |  |  | complete
Activity 2 | adopt the applicable things to the current setup | continuous |  |  | NIL | complete |  |  |  | complete
Activity 3 | check the remaining and dispensed drug stock and put in to register | every fortnightly |  |  | NIL | Complete |  |  |  | Complete
Activity 4 | indenting required drugs from central drug store according to the above mentioned list | twice a month |  |  | NIL | Complete |  |  |  | Complete
Activity 5 | presenting to superintendent about issues in the supply of medicines | once a month |  |  | NIL | pending | Not decided |  |  | pending | Not decided |  |  | complete
Activity 6 | If no help from administration than arrange alternative souce of medicines e.g. through donation. |  |  |  | NIL | pending | Not decided |  |  | pending | Not decided |  |  | continuous
Activity 7 | keep the stock register and dispensing register | continuous |  |  | NIL | pending | Not decided |  |  | pending | Not decided |  |  | complete
Area for improvement: 2.4 Psychotropic medication is available, affordable and used appropriately.
Strategy: | explaining information to users about medicines | Start Date | End Date | Responsible members | Budget | Status- Pending/Complete | New Deadline |  |  | Status- Pending/Complete | New Deadline |  |  | Status- Pending/Complete | New Deadline
Activity 1 | prepare drugs information pamphlet with the help of interns | 2015-02-19 | 2015-03-09 |  | NIL | complete |  |  |  | complete
Activity 2 | take sufficient print out of the pamphlets | as and when required |  |  | INR 1000 /1000 pamphlate | complete |  |  |  | complete
Activity 3 | train the internees on the joining about their role in explaining effects, side effects, indications etc about medicines | every 15th day when new batch of internees join |  |  | NIL | complete |  |  |  | complete
Activity 4 | for above mentioned training to be given, training of resident doctors | once in 6 month |  |  | NIL | complete |  |  |  | complete
Activity 5 | assuring that each new service user is getting those pamphlets and being informed. after prescribing medicines ask service users to come with pamphlets to resident. And intern with help of resident will explain to service user. And service user will be asked if he/she understood it or not? | everyday |  |  | NIL | complete |  |  |  | complete
Activity 6 | on follow up ask every users about the information retained from last session | in each follow up of service user |  |  | NIL | complete |  |  |  | complete
Activity 7 | re instruct service users | as and when required |  |  | NIL | complete |  |  |  | complete
Activity 8 | feed back from the users | once in a 6 months |  |  | NIL | complete |  |  |  | complete
Activity 9 | involving feedback in the recent work by discussing in the departmental meeting | once in a 6 months |  |  | NIL | complete |  |  |  | complete
Area for improvement:2.3 Treatment, psychosocial rehabilitation and links to support networks and other services are elements of a service user-driven recovery plan and contribute to a service user’s ability to live independently in the community
Strategy: | providing information about and refering service users to available rehabilitation services | Start Date | End Date | Responsible members | Budget | Status- Pending/Complete | New Deadline |  |  | Status- Pending/Complete | New Deadline |  |  | Status- Pending/Complete | New Deadline
Activity 1 | prepare the list of available rehabilitation services in and in surrounding of the city | 25 February '15 | 5 April '15 |  | NIL | pending | Not decided |  |  | pending | Not decided |  |  | Complete
Activity 2 | for preparing the list take help from NGO, HMH and other bodies | 25 February '15 | 5 April '15 |  | NIL | pending | not decided |  |  | pending | not decided |  |  | ongoing
Activity 3 | sort out the list of the bodies who are ready to establish linkage with our facility | 6 March '15 | 30 June '15 |  | NIL | pending | not decided |  |  | pending | not decided |  |  | pending | 15 Jan'16
Activity 4 | conduct a training on how to Disseminate this information to service users | 25 June '15 | 25 September '15 |  | NIL | pending | not decided |  |  | pending | not decided |  |  | pending | not decided
Activity 5 | start implementing | after training |  |  | NIL | pending | not decided |  |  | pending | not decided |  |  | pending | not decided
Activity 6 | make the register and maintain data for those users who have been referred to such linked services | 20 June '15 | 25 June '15 |  | NIL | pending | not decided |  |  | pending | not decided |  |  | pending | not decided
Area for improvement:2.3 Treatment, psychosocial rehabilitation and links to support networks and other services are elements of a service user-driven recovery plan and contribute to a service user’s ability to live independently in the community
Strategy: | making structure of recovery plan for individuals with severe mental illness | Start Date | End Date | Responsible members | Budget | Status- Pending/Complete | New Deadline |  |  | Status- Pending/Complete | New Deadline |  |  | Status- Pending/Complete | New Deadline
Activity 1 | gather information from various sources | 15 May '15 | 20 May '15 |  | NIL | complete |  |  |  | complete
Activity 2 | intradepartmental discussion regarding the gathered information & checking feasibility in our setup | 21 May '15 | 20 June '15 |  | NIL | pending | not decided |  |  | pending | not decided
Activity 3 | to develop the plan for the setup | 21 June '15 | 20 August '15 |  | NIL | pending | not decided |  |  | pending | not decided
Activity 4 | Recieve Training from QR team | 1 June '15 | as per plan |  | NIL | complete |  |  |  | complete
Activity 5 | Make pilot study- Demonstration, Discussion | 20 June '15 | 30 June '15 |  | NIL | pending | cancelled |  |  | pending | cancelled
Activity 6 | Follow up, | 30 June '15 | 5 July '15 |  | NIL | pending | not decided |  |  | pending | not decided
Activity 7 | Make List/Register to identify users | 15 July '15 | ongoing process |  | NIL | pending | not decided |  |  | pending | not decided
Activity 8 | presentation of work done/plan made for documentation and modification | every 3 month |  |  | NIL | pending | cancelled |  |  | pending | cancelled
Activity 9 | Case study-how to reach out patient, what helps and what does not | 30 June '15 | 30 July '15 |  | NIL | pending | not decided |  |  | pending | not decided
New Activity 1: | Start filling already given recovery plan from QR project | 15 Dec' 15 | 1 Feb' 16 | [10 empty] | slowly progressive
New Activity 2 | Discuss after completing atleast one plan from one doctor for one major illness, about necessity of changing it according to local culture and specific need as per the diagnosis | 4 Feb' 16 | 4 Feb' 16 | [10 empty] | pending
New Activity 3 | Finalize the recovery plan | 1 April' 16 | 3 April' 16 | [10 empty] | pending
Area for improvement:2.3 Treatment, psychosocial rehabilitation and links to support networks and other services are elements of a service user-driven recovery plan and contribute to a service user’s ability to live independently in the community
Strategy: | Involving intern doctors in new users' treatment as a guide and helper | Start Date | End Date | Responsible members | Budget | Status- Pending/Complete | New Deadline |  |  | Status- Pending/Complete | New Deadline
Activity 1 | Joining of interns on 1st day of psychiatry posting. And fill up pre-assessment form. | 22 February '15 | every time the batch is changed |  | NIL | complete |  |  |  | complete
Activity 2 | Lecture on their duty and role in users treatment | every time the batch is changed |  |  | NIL | complete |  |  |  | complete
Activity 3 | Do physical examination of the patient, take history of patient about chief complains, current illness, any previous illness like D.M., Hypertension, on any medication. | daily |  |  | NIL | complete |  |  |  | complete
Activity 4 | Bring patient to resident. take part in formulating diagnosis and give medication | daily |  |  | NIL | complete |  |  |  | complete
Activity 5 | Give patient pamphlet of that illness. Explain and educate patient about it. Explain about follow up. | daily |  |  | NIL | complete |  |  |  | complete
Area for improvement:2.3 Treatment, psychosocial rehabilitation and links to support networks and other services are elements of a service user-driven recovery plan and contribute to a service user’s ability to live independently in the community
Strategy: | establish linkage with outside occupational therapy centre | Start Date | End Date | Responsible members | Budget | Status- Pending/Complete | New Deadline |  |  | Status- Pending/Complete | New Deadline |  |  | Status- Pending/Complete | New Deadline
Activity 1 | gather information regarding availability of OT centre in city and outside city | 5 March '15 | 12 March '15 |  | NIL | pending | not decided |  |  | pending | not decided |  |  | pending
Activity 2 | Sort out the list with the centre the facility wants to establish linkage | 12 March '15 | 13 March '15 |  | NIL | pending | not decided |  |  | pending | not decided |  |  | pending
Activity 3 | Contact the desired centre for developing referal system | 13 March '15 | 13 April '15 |  | NIL | pending | not decided |  |  | pending | not decided |  |  | pending
Activity 4 | make a policy for refering users to such facilities | 15 March '15 | 25 March '15 |  | NIL | pending | not decided |  |  | pending | not decided |  |  | pending
Activity 5 | maintain a register for such activity | as and when activity done |  |  | NIL | pending | not decided |  |  | pending | not decided |  |  | pending
Area for improvement:2.5 Adequate services are available for general and reproductive health.
Strategy: | make SOP for treatment of female coming to facility | Start Date | End Date | Responsible members | Budget | Status- Pending/Complete | New Deadline |  |  | Status- Pending/Complete | New Deadline |  |  | Status- Pending/Complete | New Deadline
Activity 1 | review the available and safest medical treatment options for female | 24 February '15 | 30 July '15 |  | NIL | pending | not decided |  |  | pending | not decided |  |  | pending
Activity 2 | take reference from the already existing pregnancy registry | 24 February '15 | 30 July '15 |  | NIL | pending | not decided |  |  | pending | not decided |  |  | pending
Activity 3 | make clear outline for all female users (not only pregnant) | 1 March '15 | 30 July '15 |  | NIL | pending | not decided |  |  | pending | not decided |  |  | pending
Activity 4 | training of all residents for this topic | last week of August |  |  | NIL | pending | not decided |  |  | pending | not decided |  |  | pending
Area for improvement:5.4 Service users are supported in taking part in social, cultural, religious and leisure activities
Strategy: | providing leisure activity in ward | Start Date | End Date | Responsible members | Budget | Status- Pending/Complete | New Deadline |  |  | Status- Pending/Complete | New Deadline |  |  | Status- Pending/Complete | New Deadline
Activity 1 | designate one new room for leisure activities in ward | 12 February '15 | 13 February '15 |  | NIL | complete |  |  |  | complete
Activity 2 | enlist the activity which can be done in that room | 13 February '15 | 25 June '15 |  | NIL | complete |  |  |  | complete
Activity 3 | collect things to be put in room (e.g. news paper, magazines, carrom board) | 15 February '15 | 25 June '15 |  | INR 200 PER MONTH | pending | not decided |  |  | pending | not decided |  |  | continuous
Activity 4 | provide the required things | 15 May '15 | whenever required |  | NIL | pending | not decided |  |  | pending | not decided |  |  | continuous
Activity 5 | define the time and designate a responsible person for conducting this activity | 15 May '15 | 20 June '15 |  | NIL | pending | not decided |  |  | pending | not decided |  |  | continuous
Activity 6 | make the register for maintaining daily record of activity | 15 May '15 | 25 May '15 |  | NIL | pending | not decided |  |  | pending | not decided |  |  | continuous
Area for improvement:4.5 Safeguards are in place to prevent torture or cruel, inhuman or degrading treatment and other forms of ill-treatment and abuse
Strategy: | prevention of users from torture, cruel, inhuman and degrading treatment from staff or other users | Start Date | End Date | Responsible members | Budget | Status- Pending/Complete | New Deadline |  |  | Status- Pending/Complete | New Deadline |  |  | Status- Pending/Complete | New Deadline
Activity 1 | make/ review policy for this criterion | 2 March '15 | 10 July '15 |  | NIL | pending | not decided |  |  | pending | not decided |  |  | ongoing
Activity 2 | arrange training of resident and other staff | 11 July '15 | 25 August '15 |  | NIL | pending | not decided |  |  | pending | not decided |  |  | pending
Activity 3 | information dissemination in the form of posters | 2 March '15 | 20 August '15 |  | NIL | pending | not decided |  |  | pending | not decided |  |  | pending
Activity 4 | establish a complaining system | 2 March '15 | 15 August '15 |  | NIL | pending | not decided |  |  | pending | not decided |  |  | pending
Activity 5 | documentation of such events including generating incident reporting form | 2 March '15 | 20 August '15 |  | NIL | pending | not decided |  |  | pending | not decided |  |  | pending
Activity 6 | make intervention committee whenever such incidents are reported | 2 March '15 | 10 August '15 |  | NIL | pending | not decided |  |  | pending | not decided |  |  | pending
New Activit 1 | install complaint box |  |  |  | NIL | [8 empty] | Complete
Area for improvement:4.2 Alternative methods are used in place of seclusion and restraint as means of de-escalating potential crises.
Strategy: | decrease the use of physical and chemical restrain | Start Date | End Date | Responsible members | Budget | Status- Pending/Complete | New Deadline |  |  | Status- Pending/Complete | New Deadline |  |  | Status- Pending/Complete | New Deadline
Activity 1 | review already existing policy for restrain | 3 March '15 | 9 July '15 |  | NIL | pending | not decided |  |  | pending | not decided |  |  | complete
Activity 2 | create policy to decrease use of restrain | 10 July '15 | 25 July '15 |  | NIL | pending | not decided |  |  | pending | not decided |  |  | ongoing
Activity 3 | training for deescalation technique | to be decided |  |  | NIL | pending | not decided |  |  | pending | not decided |  |  | pending
Activity 4 | discuss the topic in department with all staff and make revised version of restrain forms | 10 July '15 | 25 July '15 |  | NIL | pending | cancelled |  |  | pending | cancelled
Activity 5 | make the register/ file for documenting restrains | 15 May '15 | 30 May '15 |  | NIL | pending | not decided |  |  | pending | not decided |  |  | continuous
Activity 6 | monthly audit of the records | monthly |  |  | NIL | pending | not decided |  |  | pending | not decided |  |  | continuous
Activity 7 | identifying barriers to decrease restrains | as per need |  |  | NIL | pending | not decided |  |  | pending | not decided |  |  | ongoing
Activity 8 | sensitising all staff to the new policy and how to implement | 25 July '15 | 30 August '15 |  | NIL | pending | not decided |  |  | pending | not decided |  |  | pending
Area for improvement:General
Strategy: | to sensitize the nursing staff for QR project and the working protocol in the department | Start Date | End Date | Responsible members | Budget | Status- Pending/Complete | New Deadline |  |  | Status- Pending/Complete | New Deadline
Activity 1 | prepare module of sensitization for the new joining nursing staff | 2 March '15 | 10 July '15 |  | NIL | Complete |  |  |  | Complete
Activity 2 | make policy for conduction of these module | 15 May '15 | 15 June '15 |  | NIL | Complete |  |  |  | Complete
Area for improvement:5.4 Service users are supported in taking part in social, cultural, religious and leisure activities
Strategy: | to mount a wall TV in OPD and Ward | Start Date | End Date | Responsible members | Budget | Status- Pending/Complete | New Deadline |  |  | Status- Pending/Complete | New Deadline |  |  | Status- Pending/Complete | New Deadline
Activity 1 | Search for specification of TV needed to be bought | 9 March '15 | 15 March '15 |  | NIL | complete |  |  |  | complete
Activity 2 | Apply to superintendent for puchasing TV | 15 March '15 | 17 March '15 |  | NIL | complete |  |  |  | complete
Activity 3 | Buy a TV after permission | 17 March '15 | 30 August '15 |  | aproximate INR 40000 per TV | pending | Cancelled |  |  | pending | Cancelled
Activity 4 | install TV on the wall | 1 Septeember '15 | 5 September '15 |  | NIL | pending | Cancelled |  |  | pending | Cancelled
New Activvity 3 | Ask pharama company for donation of TV | [12 empty] | ongoing | 9 Jan '16
Area for improvement: 5.1 Service users are supported in gaining access to a place to live and have the financial resources necessary to live in the community.
Strategy: | Giving support in gaining acess to place to live nad have the financial resources | Start Date | End Date | Responsible members | Budget | Status- Pending/Complete | New Deadline |  |  | Status- Pending/Complete | New Deadline |  |  | Status- Pending/Complete | New Deadline
Activity 1 | collect information about available services in and outside of the city | 8 March '15 | 15 June '15 |  | NIL | complete |  |  |  | complete
Activity 2 | compile information and make a list with whom links to be stablished | 15 March '15 | 17 June '15 |  | NIL | pending | not decided |  |  | pending | not decided |  |  | Pending | 11 Jan '16
Activity 3 | make a policy for refering users to such facilities | 17 March '15 | 30 June '15 |  | NIL | pending | not decided |  |  | pending | not decided |  |  | Pending | 20 Jan '16
Activity 4 | display the information | 1 April '15 | 5 July '15 |  | NIL | pending | not decided |  |  | pending | not decided |  |  | Pending | 15 Jan '16
Activity 5 | do inquiry for RSBY | 1 April '15 | 1 May '15 |  | NIL | complete |  |  |  | complete
Activity 6 | demand collected money from superintendent when money is collected | whenever available |  |  | NIL | pending | not decided |  |  | pending | not decided |  |  | continuous
Activity 7 | do activity with those money | whenever available |  |  | NIL | pending | not decided |  |  | pending | not decided |  |  | continuous
Activity 8 | make pamplet giving information about such services | 15 May '15 | 15 July '15 |  | INR 2-3 /pamphlet | pending | not decided |  |  | pending | not decided |  |  | pending | 20 Jan '16
Activity 9 | interactive session with such services (half way homes, MR school) | to be decided these facilities |  |  | NIL | pending | not decided |  |  | pending | not decided |  |  | pending
Activity 10 | training of staff regarding giving information for this | when above decided |  |  | NIL | pending | not decided |  |  | pending | not decided |  |  | pending
Activity 11 | implementation by staff | continuous |  |  | NIL | pending | not decided |  |  | pending | not decided |  |  | pending
Area for improvement:5.4 Service users are supported in taking part in social, cultural, religious and leisure activities
Strategy: | providing leisure activity in ward | Start Date | End Date | Responsible members | Budget | Status- Pending/Complete | New Deadline |  |  | Status- Pending/Complete | New Deadline |  |  | Status- Pending/Complete | New Deadline
Activity 1 | make a module for nursing students for providing activities to service users e.g. Physical Exercise, Craft activity | 12 February '15 | 13 July '15 |  | NIL | pending | not decided |  |  | pending | not decided |  |  | Ongoing | 15 Jan'16
Activity 2 | train the batch of nursing student whenever it is changed | 13 July '15 | 27 July '15 |  | NIL | pending | not decided |  |  | pending | not decided |  |  | pending
Activity 3 | each nursing student guide and help the designated user in doing leisure activity | daily |  |  | NIL | pending | not decided |  |  | pending | not decided |  |  | pending
Area for improvement: General
Strategy: | Displaying information and rights chart | Start Date | End Date | Responsible members | Budget | Status- Pending/Complete | New Deadline |  |  | Status- Pending/Complete | New Deadline |  |  | Status- Pending/Complete | New Deadline
Activity 1 | collect data from sources | 23 February '15 | 10 July '15 |  | NIL | pending | not decided |  |  | pending | not decided |  |  | complete
Activity 2 | take permission from medical superintendent for printing out new wall papers with instructions and rights chart | 23 February '15 | 1 March '15 |  | NIL | complete |  |  |  | complete
Activity 3 | compile data and enlist the materials to be printed | 2015-05-15 | 30 June '15 |  | NIL | pending | not decided |  |  | pending | not decided |  |  | ongoing- started | 15 Jan' 16
Activity 4 | give it for print out | 1 July '15 | 7 July '15 |  | NIL | pending | not decided |  |  | pending | not decided |  |  | pending
Activity 5 | install on wall | 8 July '15 | 15 July '15 |  | NIL | pending | not decided |  |  | pending | not decided |  |  | pending

## Facility4a
Area for improvement: 1.3
Strategy 1: | Cleanliness and maintainance of toilets | Start Date | End Date | Responsible members | Budget | Status- Pending/Complete | New Deadline | Explanation for not meeting the deadline | Proposed Plan for meeting new deadline
Activity 1 | Display of Signages – Keep toilets clean, flush toilets, sanitary napkins, no spitting (Local language) | 2015-05-01 | 2015-06-01 |  | INR: 0.00 | Pending
Activity 2 | Increase the frequency of cleaning of the OPD toilets (common) | 2015-04-01 | 2015-07-01 |  | INR: 0.00 | Pending
Activity 3 | Procure the checklist from Matron office and verify the number of times it is currently cleaned | 2015-04-01 | 2015-04-01 |  | INR: 0.00 | Complete
Activity 4 | SI to supervise cleaning (OPD & IPD) | 2015-04-01 | 2015-07-01 |  | INR: 0.00 | Complete
Activity 5 | Increase the frequency of cleaning of the IPD toilets (Male and Female) | 2015-04-01 | 2015-07-01 |  | INR: 0.00 | Pending
Activity 6 | Requirements within the OPD & IPD toilets to be listed | 2015-04-01 | 2015-05-01 |  | INR: 0.00 | Complete
Activity 7 | Demand letter for reparining work that needs to be done | 2015-05-01 | 2015-06-01 |  | INR: 0.00 | Pending
Activity 8 | List prepared with civil and electrical work to be reviewed | 2015-05-01 | 2015-06-01 |  | INR: 0.00 | Pending
Activity 9 | Availability of water to be ensured within the OPD & IPD toilets | 2015-05-01 | 2015-07-01 |  | INR: 0.00 | Pending
Activity 10 | Partition between the drinking water facility and the toilet | 2015-05-01 | 2015-10-01 |  | To be discussed with the HOD and the superintendent | Pending
Activity 11 | Maintenance of the western commodes in both the in-patient and out-patient departments. | 2015-05-01 | 2015-07-01 |  | INR: 0.00 | Pending
Strategy 2: | Availability of running water and hot water within the IPD bathrooms | Start Date | End Date | Responsible members | Budget
Activity 1 | A complaint to be noted by the IPD Head nurses in the complaint register, the mechanism which is followed by all the departments within the hospital. | 2015-04-01 | 2015-04-01 |  | INR: 0.00 | Completed
Activity 2 | Follow-up with another complaint if no work has been done | 2015-05-01 | 2015-06-01 |  | INR: 0.00 | Completed
Activity 3 | A follow-up of the solar water panels which are being currently installed- follow up | 2015-05-01 | 2015-08-01 |  | INR: 0.00 | Pending
Activity 4 | Ensuring availability in both the male and female wards | 2015-05-01 | 2015-08-01 |  | INR: 0.00 | Pending
Strategy 3: | Accessibility for people with disabilties and people who are bedridden | Start Date | End Date | Responsible members | Budget
Activity 1 | Circulating the handbook on accessibility for people with disabitlies within the QR team members and presenting the team with pointers | 2015-04-01 | 2015-04-01 |  | Rs. 280/- | Completed
Activity 2 | Listing the adaptations that need to be done | 2015-04-01 | 2015-05-01 |  | INR: 0.00 | Pending
Activity 3 | Tactile flooring (on hold for now) |  |  |  | To be discussed with the HOD and Superintedent | Pending
Activity 4 | Railing cots - demand letter from the HOD | 2015-05-01 | 2015-06-01 |  | To be discussed with the HOD and Superintedent | Pending
Activity 5 | Bed Pans and catheters - Requirement to be given in the hospital register | 2015-04-01 | 2015-05-01 |  | INR: 0.00 | Pending
Activity 6 | Provision for hand-rails within the toilets | 2015-05-01 | 2015-10-01 |  | To be discussed with the HOD and Superintedent | Pending
Activity 7 | Provision of toilet chair within the IPD | 2015-05-01 | 2015-10-01 |  | To be discussed with the HOD and Superintedent | Pending
Activity 8
Activity 9
Area for improvement: 1.4
Strategy 1: | Designated area for food within the IPD | Start Date | End Date | Responsible members | Budget
Activity 1 | Designated area to be created within the ward for service users and family members to have food | 2015-05-01 | 2015-07-01 |  | INR: 0.00 | Completed
Activity 2 | Display of appropriate signages accordingly | 2015-05-01 | 2015-07-01 |  | INR: 0.00 | Pending
Activity 3 | Ensuring that the area is cleaned and hygiene is maintained. | 2015-05-01 |  |  | INR: 0.00 | Pending
Activity 5 | Guide the relatives to the place where food is served for the care-givers within the campus | 2015-05-01 |  |  | INR: 0.00 | Completed
Strategy 2: | Visit to the area where food is prepared to assess the quality and quantity | Start Date | End Date | Responsible members | Budget
Activity 1 | To check if at all any guidelines govern the food quality that are currently being followed. | 2015-05-01 | 2015-05-01 |  | INR: 0.00 | Completed
Activity 2 | Check policy with regard to food within the hospital. | 2015-05-01 | 2015-05-01 |  | INR: 0.00 | Completed
Activity 3 | Request letter to be sent to the admin through the department of psychiatry for a visit of the core team to the place where the food is prepared along with the dietician | 2015-05-01 | 2015-08-01 |  | INR: 0.00 | Pending
Activity 4 | Sub-group meeting with the dietician | 2015-05-01 | 2015-05-01 |  | INR: 0.00 | Pending
Activity 5 | Time to be decided once the approval for the same is received | 2015-05-01 | 2015-06-01 |  | INR: 0.00 | Pending
Strategy 3: | Supply of safe drinking water in good quality and quantity within the out-patient and in-patient department | Start Date | End Date | Responsible members | Budget
Activity 1 | Availability of cold water , working of chiller plants | 2015-05-01 | 2015-08-01 |  | To be done once discussed with the HOD and the superintendent | Pending
Activity 2 | Sub-group meeting to discuss the budget | 2015-05-01 | 2015-07-01 |  | To be done once discussed with the HOD and the superintendent | Pending
Activity 3 | Portable water for OPD, making water jars available (20L), | 2015-05-01 | 2015-06-01 |  | INR: 0.00 | Completed
Activity 4 | Demand letter for portable water availability within the out-patient and in-patient department, making an additional water container available for service users and their care-givers within the IPD and OPD | 2015-05-01 | 2015-06-01 |  | INR: 0.00 | Completed
Activity 5 | Signages for drinking water to be displayed within the OPD | 2015-05-01 | 2015-06-01 |  | INR: 0.00 | Completed
Activity 6 | Responsibility of maintenance and refilling of the water containers within the OPD and IPD | 2015-05-01 | 2015-05-01 |  | INR: 0.00 | Completed
Activity 7 | Alternative arrangements to refill drinking water containers from the college building or nursing hostel in case of unavailability within the hospital for any reason | 2015-05-01 | 2015-05-01 |  | INR: 0.00 | Completed
Activity 8 | With regard to quality, physical, chemical and biological properties to be assessed- Policy | 2015-06-01 | 2015-08-01 |  | INR: 0.00 | Pending
Activity 9 | Policy regarding the same to be verified, if a policy does not exist, one to be made. | 2015-06-01 | 2015-08-01 |  | INR: 0.00 | Pending
Strategy 4: | Culturally appropriate clothing to be provided to the service users | Start Date | End Date | Responsible members | Budget
Activity 1 | Survey to be conducted within the female IPD for their preference of clothing. | 2015-05-01 | 2015-06-01 |  | INR: 0.00 | Pending
Activity 2 | 2 sets of clothig to be made available within the department, 2 piece uniform as provided in the male ward and kurta-salwar. |  |  |  | To be discussed with the HOD and Superintendent | Pending
Activity 3 | The type of clothing preferred, taking from the survey to be conveyed to the superintendent | 2015-06-01 | 2015-06-01 |  | To be discussed with the HOD and Superintendent | Pending
Activity 4 | The required amount of clothing to be made available within the IPD | 2015-07-01 | 2015-08-01 |  | To be discussed with the HOD and Superintendent | Pending
Activity 5
Theme 2
Area for improvement: 2.2
Strategy 1: | Skill development of the Social worker and nursing staff with regard to issues of dealing with service users with mental illness. | Start Date | End Date | Responsible members | Budget
Activity 1 | Sensitizing the clinical and non-clinical staff members on dealing with service users with mental illness through presentation and training | 2015-06-01 | 2015-08-01 |  | INR: 0.00 | Pending
Activity 2 | Recruting psychiartic Social worker within the department of psychiatry | 2015-06-01 |  |  | INR: 0.00 | Pending
Activity 3 | Obtaining training details, modules from HMHV or related sources | 2015-05-01 | 2015-07-01 |  | INR: 0.00 | Pending
Activity 4 | A separate training module to be developed in house with respect to psycho-social rehabilitation, for servants, staff and nursing , social worker | 2015-06-01 | 2015-08-01 |  | INR: 0.00 | Pending
Strategy 2: | Exploring community resources and services and making the staff aware of the same | Start Date | End Date | Responsible members | Budget
Activity 1 | To make a register with the names of NGO's, schools, GO's working for people and children with mental illness | 2015-05-01 | 2015-08-01 |  | INR: 0.00 | Completed
Activity 2 | Visit to HMHV | 2015-05-01 | 2015-05-01 |  | INR: 0.00 | Completed
Activity 3 | Display of the directory for easy access to the service users within the OPD and IPD | 2015-06-01 |  |  | INR: 0.00 | Pending
Activity 4 | Search for NGO’s, support groups, self-help groups that might be active within the city, search online | 2015-05-01 | 2015-08-01 |  | INR: 0.00 | Pending
Strategy 3: | Recruit trained Nursing staff within the department of Psychiatry | Start Date | End Date | Responsible members | Budget |  |  |  |  | Responsible members | Budget
Activity 1 | Discuss the activity strategized with the HOD | 2015-05-01 | 2015-06-01 |  | INR: 0.00 | Pending
Activity 2 | Request letter to be send to the superintendent office | 2015-05-01 | 2015-06-01 |  | INR: 0.00 | Pending
Strategy 4: | Clinical psychologist to be recruited to the department of Psychiatry | Start Date | End Date | Responsible members | Budget
Activity 1 | Demand letter to be sent to the superintendent for recruting a clinical psychologist | 2015-06-01 | 2015-07-01 |  | INR: 0.00 | Pending
Activity 2 | Recruting a clinical psychologist as a consultant till the post for a clinical psychologist within the department is created | 2015-05-01 | 2015-08-01 |  | To be discussed | Pending
Strategy 5: | Formal Training for the JR recruited within the department of Psychiatry | Start Date | End Date | Responsible members | Budget
Activity 1 | Drafting a policy for making training in psychiatry mandatory after recruitment for JR's | 2015-06-01 | 2015-08-01 |  | INR: 0.00 | Pending
Activity 2 | 2 week formal training after joining along with observation | 2015-08-01 |  |  | INR: 0.00 | Pending
Activity 3 | Rotational duty within the IPD | 2015-08-01 |  |  | INR: 0.00 | Pending
Activity 4 | Developing content and preparing a module for the same | 2015-07-01 | 2015-08-01 |  | INR: 0.00 | Pending
Strategy 6: | ·Information dissemination on rights of the service users | Start Date | End Date | Responsible members | Budget
Activity 1 | Written document about rights of persons with disabilities to be made available through sources |  | 2016-06-01 |  | INR: 0.00 | Pending
Activity 2 | Training to the clinical and non-clinical staff with regard to the mental health act and CRPD, | 2015-06-01 | 2015-08-01 |  | INR: 0.00 | Pending
Activity 3 | Display of user rights and responsibilties in local language both within the IPD & OPD | 2015-05-01 | 2015-06-01 |  | INR: 0.00 | Pending
Activity 4 | The Gujarati version of the CRPD to be circulated to the core team | 2015-05-01 | 2015-06-01 |  | INR: 0.00 | Pending
Strategy 7: | Access to mechanisms for expressing of opinion for service users | Start Date | End Date | Responsible members | Budget
Activity 1 | Install suggestion boxes within the OPD & IPD | 2015-06-01 | 2015-07-01 |  | To be discussed with the HOD and Superintendent | Pending
Activity 2 | Follow up for the installation of the Suggestion boxes from the AHA | 2015-06-01 | 2015-07-01 |  | INR: 0.00 | Pending
Activity 3 | Essential stationary to be made available | 2015-06-01 | 2015-07-01 |  | INR: 0.00 | Pending
Activity 4 | Monitoring of the complaints/ suggestions once a week | 2015-07-01 |  |  | INR: 0.00 | Pending
Activity 5 | Maintain a register with the entry of all opinions inscribed | 2015-07-01 |  |  | INR: 0.00 | Pending
Activity 6 | Meeting once a month with all the staff members within the department of psychiatry for a feedback and discussion upon the inputs | 2015-07-01 |  |  | INR: 0.00 | Pending
Area for improvement: 2.4
Strategy 1: | Ensuring constant supply of the psychotropic drugs for the service users | Start Date | End Date | Responsible members | Budget
Activity 1 | Essential drug list to be displayed in local language within the OPD & IPD | 2015-05-01 | 2015-06-01 |  | INR: 0.00 | Pending
Activity 2 | Information dissemination to the nursing staff on the effects and side-effects of the medications. | 2015-07-01 | 2015-09-01 |  | INR: 0.00 | Pending
Activity 3 | To include 3rd generation drugs and combination in new indent |  |  |  | INR: 0.00 | Pending
Activity 4 | Procurement plan : to be drafted and implemented, alternative sources for eg. taking loan from HMHV, to be explored to ensure constant supply of medication | 2015-06-01 | 2015-09-01 |  | INR: 0.00 | Pending
Activity 5 | Regular follow-up with the store manager for the stock per month | 2015-05-01 |  |  | INR: 0.00 | Completed
Strategy 2: | Informing service users about the side-effects of the medications | Start Date | End Date | Responsible members | Budget
Activity 1 | Prepare a list of common medications and related side-effects for display within the OPD and IPD | 2015-05-01 | 2015-07-01 |  | INR: 0.00 | Pending
Activity 2 | Make pamphlet in local language- disorder specific and hand-out to the service user after explaining the same verbally | 2015-05-01 | 2015-06-01 |  | INR: 0.00 | Partly Completed
Activity 3 | Document on case papers in language, preferably in Gujarati as well as explaining the side-effects verbally | 2015-05-01 | 2015-07-01 |  | INR: 0.00 | Pending
Activity 4 | Audio-visual medium for people who are illiterate | 2015-05-01 | 2015-11-01 |  | To be discussed with the HOD and Superintendent | Pending
Theme 3
Area for improvement: 3.1
Strategy 1: | Preferences of the service users will be given priority to be heard | Start Date | End Date | Responsible members | Budget
Activity 1 | Sensitizing all the clinical and non-clinical staff on the needs of service users with mental illness | 2015-06-01 | 2015-08-01 |  | INR: 0.00 | Pending
Activity 2 | Informed consent both written and verbal from the service users | 2015-05-01 |  |  | INR: 0.00 | Partly Completed
Activity 3 | Making SOP for applying restraint | 2015-06-01 | 2015-08-01 |  | INR: 0.00 | Pending
Activity 4 | Preferece to meet the doctor to be through the staff | 2015-06-01 |  |  | INR: 0.00 | Completed
Activity 5 | Display of the rights of service users within the in-patient and out-patient department | 2015-06-01 | 2015-07-01 |  | INR: 0.00 | Pending
Strategy 2: | Develop criteria for discharge from IPD" | Start Date | End Date | Responsible members | Budget
Activity 1 | Check with HMHV for discharge procedure | 2015-05-01 | 2015-05-01 |  | INR: 0.00 | Completed
Activity 2 | Developing standardized tools to record improvement in the service user and documenting the same | 2015-05-01 | 2015-07-01 |  | INR: 0.00 | Pending
Activity 3 | Checklist for discharge | 2015-06-01 | 2015-07-01 |  | INR: 0.00 | Completed
Activity 4 | An orientation to Psycho-education to all the clinical and non-clinical staff | 2015-06-01 | 2015-08-01 |  | INR: 0.00 | Pending
Activity 5 | Educating the care-givers for recovery of the service users | 2015-06-01 | 2015-08-01 |  | INR: 0.00 | Pending
Strategy 3: | Implement the use of recovery plans in clinical practice in the OPD and IPD | Start Date | End Date | Responsible members | Budget
Activity 1 | Training of the clinical and non-clinical staff by the Master trainers | 2015-06-01 | 2015-07-01 |  | INR: 0.00 | Pending
Activity 2 | Distribution of notes to all the staff members | 2015-06-01 | 2015-07-01 |  | INR: 0.00 | Pending
Activity 3 | Follow-up session | 2015-09-01 | 2015-10-01 |  | INR: 0.00 | Pending
Activity 4 | Documentation | 2015-06-01 | 2015-10-01 |  | INR: 0.00 | Pending
Area for improvement: 3.4
Strategy 1: | Maintaining separate file per service user within the out-patient department | Start Date | End Date | Responsible members | Budget
Activity 1 | Request letter from the department of psychiatry | 2015-05-01 | 2015-06-01 |  | INR: 0.00 | Pending
Activity 2 | Follow-up and implementation | 2015-06-01 | 2015-08-01 |  | INR: 0.00 | Pending
Activity 3 | A separate file for every new case within the department of psychiatry to be issued | 2015-06-01 | 2015-08-01 |  | INR: 0.00 | Pending
Activity 4 | Informing the service users and respective care-givers of maintaining the file and carrying the same for every follow-up visit | 2015-07-01 |  |  | INR: 0.00 | Pending
Activity 5 | Recovery plans, social worker notes, clinical psychologist notes to be properly filed | 2015-06-01 |  |  | INR: 0.00 | Pending
Strategy 2: | Ensuring the information about service users is kept confidential. | Start Date | End Date | Responsible members | Budget
Activity 1 | Explanation to the IPD staff members for the need of maintaining confidentiality | 2015-05-01 |  |  | INR: 0.00 | Pending
Activity 2 | Ensuring that any intern/volunteer/researcher has a written note from the HOD with his signature stating the reason for accessing the IPD files | 2015-05-01 |  |  | INR: 0.00 | Pending
Activity 3 | Discussing the same with the HOD | 2015-05-01 | 2015-06-01 |  | INR: 0.00 | Pending
Activity 4 | Maintaining a register with the names of interns/volunteers/researchers who access the user files | 2015-05-01 |  |  | INR: 0.00 | Pending
Activity 5 | Construction of racks for storage of files or basing a cupboard by the nursing station with the specific purpose of storing files. | 2015-07-01 | 2015-10-01 |  | To be discussed | Pending
Theme 4
Area for improvement: 4.1
Strategy: | Formation of grievance redressal cell | Start Date | End Date | Responsible members | Budget
Activity 1 | Person A to help strategize activities with regard to Theme 4 | 2015-05-01 |  |  | INR: 0.00
Activity 2 | Sensitizing the staff for a need for policy and monitoring system | 2015-06-01 | 2015-08-01 |  | INR: 0.00
Activity 3 | Discussion with the HOD | 2015-06-01 |  |  | INR: 0.00
Activity 4 | Formation of committee and drafting SOP | 2015-06-01 | 2015-08-01 |  | INR: 0.00
Activity 5 | Monitoring of the suggestions boxes discussed earlier with the issues being taken up by this committee | 2015-06-01 | 2015-08-01 |  | INR: 0.00
Area for improvement: 4.5
Strategy 1: | General policy on abuse, torture, harassment for service users as well as staff | Start Date | End Date | Responsible members | Budget
Activity 1 | Discussion with the HOD for the same and follow-up | 2015-06-01 |  |  | INR: 0.00
Activity 2 | Formation of committee and drafting SOP | 2015-06-01 | 2015-08-01 |  | INR: 0.00
Activity 3 | Awareness of the functioning and objective of the committee to be notified | 2015-07-01 | 2015-08-01 |  | INR: 0.00
Strategy 2: | Access to advocates | Start Date | End Date | Responsible members | Budget
Activity 1 | Making a register of advocates associated with mental hospitals, NGO’s working for people with disabilities and similar. | 2015-05-01 | 2015-06-01 |  | INR: 0.00 | Completed
Activity 2 | Discussing the details with the HOD | 2015-05-01 | 2015-06-01 |  | INR: 0.00 | Pending
Activity 3 | Contacting the same and fixing up an appointment | 2015-06-01 | 2015-08-01 |  | To be discussed after a meeting with the HOD and Superintendent | Pending
Activity 4 | Information about the project, the activities planned and the need for his/her association with the department as a consultant | 2015-06-01 | 2015-08-01 |  | INR: 0.00 | Pending
Activity 5 | Signing an MOU
Theme 5
Area for improvement: 5.1
Strategy 1: | Access to financial resources for the service users | Start Date | End Date | Responsible members | Budget
Activity 1 | Liaising with the mental hospital : Day care centre | 2015-06-01 | 2015-08-01 |  | INR: 0.00 | Pending
Activity 2 | Search for all organizations working for people with mental illness in Vadodara and maintaining a directory for same with the details mentioned in local language. | 2015-06-01 | 2015-08-01 |  | INR: 0.00 | Completed
Activity 3 | Ensuring the directory is located at a place within the OPD & IPD which is accessible to all | 2015-06-01 | 2015-08-01 |  | INR: 0.00 | Pending
Activity 4 | Survey to understand the kind of information/assistance the service users would want from the survey- housing/ loans/ employment or any other. | 2015-06-01 | 2015-06-01 |  | INR: 0.00 | Pending
Activity 5 | Survey questions to be verified and translated in Gujarati | 2015-06-01 | 2015-06-01 |  | INR: 0.00 | Pending
Activity 6 | The survey outcome to be shared with the HOD and further activities to be planned | 2015-06-01 | 2015-07-01 |  | INR: 0.00
Strategy 2: | Guidance for parents of children with special needs | Start Date | End Date | Responsible members | Budget
Activity 1 | Referrals to the clinical psychologist within the department, if appointed by then. |  |  |  | INR: 0.00 | Pending
Activity 2 | Maintaining and updating a register with the names of clinical and counselling psychologists within Vadodara for referral, in case a clinical psychologist is not appointed within the department. | 2015-06-01 | 2015-08-01 |  | INR: 0.00 | Completed
Activity 3 | Maintaining a directory with services available for children with disabilities within Vadodara, schools in Vadodara , any workshops/trainings/lectures- information to be updated for display within the OPD | 2015-06-01 | 2015-08-01 |  | INR: 0.00 | Pending
Activity 4 | Liaison with the pediatric department for referrals to the psychiatric department | 2015-06-01 | 2015-08-01 |  | INR: 0.00 | Pending
Activity 5 | Preparing a referral criterion form to be filled up by the pediatric department | 2015-06-01 | 2015-07-01 |  | INR: 0.00 | Pending
Activity 6 | Approval of the form from the HOD and implementation | 2015-06-01 | 2015-08-01 |  | INR: 0.00 | Pending
Activity 7 | Forming a parent-support group | 2015-08-01 |  |  | INR: 0.00 | Pending
Area for improvement: 5.4
Strategy 1: | Providing Leisure Activities to service users | Start Date | End Date | Responsible members | Budget
Activity 1 | A list of requirements within the OPD and IPD to be discussed with the HOD and Superintendent *Benches to be stationed within the OPD(waiting area) *TV *Radio *Newspaper * Designated area for recreation | 2015-06-01 | 2015-11-01 |  | To be discussed with the HOD and Superintendent | Pending
Activity 2 | Reading material to be made available within both the departments. Donated(In-house resources) + Purchased | 2015-06-01 | 2015-11-01 |  | To be discussed with the HOD and Superintendent | Pending
Activity 3 | To generate funds for the department, after discussing the same with the HOD | 2015-06-01 | 2015-11-01 |  | To be discussed with the HOD and Superintendent | Pending
Activity 4 | Yoga/ exercise or any activity for recreation to be initiated within the IPD | 2015-07-01 |  |  | INR: 0.00 | Pending
Activity 5 | Few service users who come to OPD for follow-up can be approached(Who teach Yoga-known resource) and can be given an honorarium |  |  |  | INR: 0.00 | Pending
Strategy 2: | Referrals to the care-giver SAATHI groups | Start Date | End Date | Responsible members | Budget
Activity 1 | Informing the care-givers of the support groups and encouraging them to be a part of the same. | 2015-05-01 |  |  | INR: 0.00 | On-going
Activity 2 | Ensuring all the psychiatrists , JR’s, Nursing staff inform the care-givers about the support groups | 2015-05-01 |  |  | INR: 0.00 | on-going
Activity 3 | Distribution of pamphlets | 2015-05-01 |  |  | INR: 0.00 | on-going
Activity 4 | Date of the meeting to be informed to the psychiatrist well in advance | 2015-05-01 |  |  | INR: 0.00 | On-going

## Facility4b
Theme 1
Area for improvement: 1.3
Strategy 1 | Cleanliness and maintenance of toilets | Start Date | End Date | Responsible members | Budget | Status- Pending / Complete
Activity 1 | Approval for required signages and display within the OPD & IPD lavatory (Local language) | 01/05/ 2015 | 2016-03-15 |  | Procured from the hospital | Complete
Activity 2 | Procure the checklist from the office of the Matron and evaluate the number of times it is currently cleaned | 01/04/ 2015 | 01/04/ 2015 |  | INR: 0.00 | Complete
Activity 3 | Decide the frequency of cleaning : OPD toilets (common) | 01/04/ 2015 | 01/07/ 2015 |  | INR: 0.00 | Complete
Activity 4 | SI to supervise cleaning (OPD & IPD) | 01/04/ 2015 | 01/07/ 2015 |  | INR: 0.00 | Complete
Activity 5 | Decide the frequency of cleaning: IPD toilets & Bathroom (Male and Female) | 01/04/ 2015 | 01/07/ 2015 |  | INR: 0.00 | Complete
Activity 6 | Requirements within the OPD & IPD toilets to be listed | 01/04/ 2015 | 01/05/ 2015 |  | INR: 0.00 | Complete
Activity 7 | Letter for repairing work to be sent to the superintendent | 01/05/ 2015 | 2016-03-31 |  | INR: 0.00 | In-process
Activity 8 | List prepared with civil and electrical work to be reviewed | 01/05/ 2015 | 2016-03-31 |  | INR: 0.00 | In-process
Activity 9 | Availability of water to be ensured within the OPD & IPD toilets | 01/05/ 2015 | 2016-03-15 |  | INR: 0.00 | In-process
Activity 10 | Partition between the drinking water facility and the toilet | 01/05/ 2015 |  |  | As per applicable norms of the facility Budget: | Pending
Activity 11 | Ensuring civil work of the western commodes in both the in-patient and out-patient departments is done | 01/05/ 2015 | 2016-03-15 |  | INR: 0.00 | In-process
Strategy 2: | Availability of hot water within the IPD bathrooms | Start Date | End Date | Responsible members | Budget | Status- Pending / Complete
Activity 1 | A note to be written by the IPD head nurses in the register maintained within the facility | 01/04/ 2015 | 01/04/ 2015 |  | INR: 0.00 | Completed
Activity 2 | Follow-up with another reminder if work is observed to be impending. | 01/05/ 2015 | 01/06/ 2015 |  | INR: 0.00 | Completed
Activity 3 | A follow-up of the solar water panels which are being currently installed. | 01/05/ 2015 | 01/08/ 2015 |  | INR: 0.00 | Completed
Activity 4 | Ensuring availability of hot water in both the male and female wards | 01/05/ 2015 | 2016-04-15 |  | INR: 0.00 | In-process
Strategy 3: | Accessibility for people with disabilities and people who are bedridden | Start Date | End Date | Responsible members | Budget | Status- Pending / Complete
Activity 1 | Circulating the handbook on accessibility for people with disabilities within the QR team members and presenting the team with pointers | 01/04/ 2015 | 01/04/ 2015 |  | Rs. 280/- | Completed
Activity 2 | Listing the adaptations that need to be done | 01/04/ 2015 | 2016-03-31 |  | INR: 0.00 | In-process
Activity 3 | Tactile flooring (on hold for now) |  |  |  | To be discussed with the HOD and Superintendent | Pending
Activity 4 | Railing cots - demand letter from the HOD | 01/05/ 2015 | 01/06/ 2015 |  | To be discussed with the HOD and Superintendent | Completed
Activity 5 | Bed Pans and catheters - Requirement to be given in the hospital register | 01/04/ 2015 | 01/05/ 2015 |  | INR: 0.00 | Completed
Activity 6 | Provision for hand-rails within the toilets (on hold for now) | 01/05/ 2015 | 01/10/ 2015 |  | As per hospital norms (Outsourced) | Pending
Activity 7 | Provision of commode chair within the IPD (on hold for now) | 01/05/ 2015 | 01/10/ 2015 |  |  | Pending
Area for improvement: 1.4
Strategy 1: | Designated area for food within the IPD | Start Date | End Date | Responsible members | Budget | Status- Pending / Complete
Activity 1 | Designated area to be created within the ward for service users and family members to have food | 01/05/ 2015 | 01/07/ 2015 |  | INR: 0.00 | Completed
Activity 2 | Display of appropriate signages accordingly | 01/05/ 2015 | 2016-03-15 |  | INR: 0.00 | Completed
Activity 3 | Supervising that the designated area is cleaned and hygiene is maintained. | 01/05/ 2015 |  |  | INR: 0.00 | Completed
Activity 4 | Guide the relatives to the place where food is served for the care-givers within the campus | 01/05/ 2015 |  |  | INR: 0.00 | Completed
Strategy 2: | To assess the food management & quality control procedure within the facility | Start Date | End Date | Responsible members | Budget | Status- Pending / Complete
Activity 1 | Check policy/ guidelines with regard to food within the hospital. | 01/05/ 2015 | 01/05/ 2015 |  | INR: 0.00 | Completed
Activity 2 | Sub-group meeting with the dietician | 01/05/ 2015 | 01/08/ 2015 |  | INR: 0.00 | Completed
Activity 3 | In-case a policy does not exist, draft a policy with regard to food management, quality control and hygiene. | 01/05/ 2015 | 2016-04-15 |  | INR: 0.00 | Completed
Activity 4 | Approval of the policy | 01/05/ 2015 | 2016-04-15 |  | INR: 0.00 | In-process
Strategy 3: | Supply of safe drinking water in good quality and quantity within the out-patient and in-patient department | Start Date | End Date | Responsible members | Budget | Status- Pending / Complete
Activity 1 | Availability of cold water , working of chiller plants | 01/05/ 2015 | 01/08/ 2015 |  | To be done once discussed with the HOD and the superintendent | Completed
Activity 2 | Sub-group meeting to discuss the budget | 01/05/ 2015 | 01/07/ 2015 |  | To be done once discussed with the HOD and the superintendent | Completed
Activity 3 | Portable water for OPD, making water jars available (20L), | 01/05/ 2015 | 01/06/ 2015 |  | INR: 0.00 | Completed
Activity 4 | Issuing a letter for portable water availability within the out-patient and in-patient department, making an additional water container available for service users and their care-givers within the IPD and OPD | 01/05/ 2015 | 01/06/ 2015 |  | INR: 0.00 | Completed
Activity 5 | Signages for drinking water to be displayed within the OPD | 01/05/ 2015 | 01/10/ 2015 |  | INR: 0.00 | Completed
Activity 6 | Responsibility of maintenance and refilling of the water containers within the OPD and IPD | 01/05/ 2015 | 01/05/ 2015 |  | INR: 0.00 | Completed
Activity 7 | Alternative arrangements to refill drinking water containers from the college building or nursing hostel in case of unavailability within the hospital for any reason | 01/05/ 2015 | 01/05/ 2015 |  | INR: 0.00 | Completed
Activity 8 | To avail the policy with regard to water management | 01/06/ 2015 | 2016-04-15 |  | INR: 0.00 | Completed
Activity 9 | In a situation where policy regarding the same does not exist, drafting one accordingly. | 01/06/ 2015 | 2016-04-15 |  | INR: 0.00 | In-process
Strategy 4: | Culturally appropriate clothing to be provided to the service users | Start Date | End Date | Responsible members | Budget | Status- Pending / Complete
Activity 1 | Survey to be conducted within the female IPD for their preference of clothing. | 01/05/ 2015 | 01/06/ 2015 |  | INR: 0.00 | Completed
Activity 2 | 2 sets of clothing to be made available within the IPD (Female) department, 2 piece uniform as provided in the male ward and kurta-salwar. |  |  |  | To be discussed with the HOD and Superintendent | Completed
Activity 3 | The type of clothing preferred, taking from the survey to be conveyed to the superintendent | 01/06/ 2015 | 01/06/ 2015 |  | To be discussed with the HOD and Superintendent | Completed
Activity 4 | The required amount of clothing to be made available within the IPD | 01/07/ 2015 | 2016-03-31 |  | To be discussed with the HOD and Superintendent | Completed
Theme 2
Area for improvement: 2.2
Strategy 1: | Equip the social worker, nursing staff members and non-clinical staff with skills to deal with issues of the service users | Start Date | End Date | Responsible members | Budget | Status- Pending / Complete
Activity 1 | Disseminating information to the social worker, nursing and non-clinical staff members to understand the needs of service users with mental illness through training | 01/06/ 2015 | 2016-03-16 |  | INR: 0.00 | Completed
Activity 2 | Recruiting psychiatric social worker within the department of psychiatry | 01/06/ 2015 |  |  | INR: 0.00 | lettter has been sent to the superintedent along with a follow-up
Activity 3 | Obtaining training details, modules from HMHV/HMHA or related sources for information | 01/05/ 2015 | 01/07/ 2015 |  | INR: 0.00 | Completed
Activity 4 | Training module for the said staff to be developed within the department of psychiatry. | 01/06/ 2015 | 01/08/ 2015 |  | INR: 0.00 | Completed
Strategy 2: | Exploring community resources and services and disseminating information about the same | Start Date | End Date | Responsible members | Budget | Status- Pending / Complete
Activity 1 | To make a register with the names of NGO's, Support groups, day care centres, workshops, training centres, vocational centres working for people and children with mental illness | 01/05/ 2015 | 01/10/ 2015 |  | INR: 0.00 | On-going
Activity 2 | Visit to HMHV for the QR team members to understand its working | 01/05/ 2015 | 01/05/ 2015 |  | INR: 0.00 | Completed
Activity 3 | Approval of the information from the HOD with regard to the information that will go in the register | 01/06/ 2015 | 2016-04-15 |  | INR: 0.00 | The current list has been shown to Dr., as and when new information is added, the same will be shown to him
Activity 4 | Display of the directory for easy access to the service users within the OPD and IPD |  | 2016-04-15 |  |  | On-going
Activity 5 | Ensuring a soft copy of the same is saved. |  |  |  |  | In-process
Strategy 3: | Recruit nursing staff trained in mental health within the department of Psychiatry | Start Date | End Date | Responsible members | Budget | Status- Pending / Complete
Activity 1 | Discuss the activity strategized with the HOD | 01/05/ 2015 | 01/06/ 2015 |  | INR: 0.00 | Completed
Activity 2 | Refer to the Mental Health Act requirements
Activity 3 | Request letter to be send to the superintendent office | 01/05/ 2015 | 01/06/ 2015 |  | INR: 0.00 | In-process
Strategy 4: | Clinical psychologist to be recruited to the department of Psychiatry | Start Date | End Date | Responsible members | Budget | Status- Pending / Complete
Activity 1 | Demand letter to be sent to the superintendent for recruiting a clinical psychologist | 01/06/ 2015 | 01/07/ 2015 |  | INR: 0.00 | completed
Activity 2 | Recruiting a clinical psychologist as a consultant till the post for a clinical psychologist within the department is created | 01/05/ 2015 | 01/08/ 2015 |  | No financial aid available at present
Strategy 5: | Training of the JR’s recruited within the department of psychiatry | Start Date | End Date | Responsible members | Budget | Status- Pending / Complete
Activity 1 | Drafting a policy for training within the department of psychiatry | 01/06/ 2015 | 2016-03-31 |  | INR: 0.00 | In-process
Activity 2 | Formal training of the JR’s on joining | 01/08/ 2015 |  |  | INR: 0.00 | As and when JR's join
Activity 3 | Developing content and preparing a module for the same | 01/07/ 2015 | 2016-03-15 |  | INR: 0.00 | In-process
Activity 3 | Approval of the module from the HOD | 01/08/ 2015 | 2016-03-31 |  | INR: 0.00 | In-process
Strategy 6: | Information dissemination on rights of the service users with mental illness | Start Date | End Date | Responsible members | Budget | Status- Pending / Complete
Activity 1 | Written document about rights of persons with disabilities to be made available through sources |  | 2016-04-15 |  | INR: 0.00 | In-process
Activity 2 | Training to the clinical and non-clinical staff with regard to the rights of service users | 01/06/ 2015 | 01/08/ 2015 |  | INR: 0.00 | In-process
Activity 3 | Approval of the content from the HOD | 01/07/ 2015 | 2016-04-15 |  | INR: 0.00 | Completed
Activity 4 | Display of user rights and responsibilities in local language both within the IPD & OPD | 01/08/ 2015 | 2016-04-15 |  |  | Once finalized and sent from the Centre
Strategy 7: | Access to mechanisms for expressing of opinion for service users | Start Date | End Date | Responsible members | Budget | Status- Pending / Complete
Activity 1 | Install suggestion/ complaint boxes within the OPD & IPD | 01/06/ 2015 | 2016-03-31 |  | To be discussed with the HOD and Superintendent | Complete
Activity 2 | Follow up for the installation of the Suggestion boxes from the AHA | 01/06/ 2015 | 01/07/ 2015 |  | Procured from the facility | Complete
Activity 3 | Essential stationary to be made available | 01/06/ 2015 | 01/07/ 2015 |  | Procured from the facility | Complete
Activity 4 | Maintain a register in the department with the matter specified | 01/07/ 2015 |  |  | INR: 0.00 | Complete
Activity 5 | Draft a policy specific to the department of psychiatry | 01/07/ 2015 | 2016-04-15 |  | INR: 0.00 | In-process
Area for improvement: 2.4
Strategy 1: | Ensuring constant supply of the psychotropic drugs for the service users | Start Date | End Date | Responsible members | Budget | Status- Pending / Complete
Activity 1 | Essential drug list to be displayed within the OPD & IPD | 01/05/ 2015 | 01/06/ 2015 |  | INR: 0.00 | Completed
Activity 2 | Information dissemination to the nursing staff on the effects and side-effects of the medications. | 01/07/ 2015 | 2016-03-16 |  | INR: 0.00 | In-process
Activity 3 | Policy pertaining to the supply of the psychotropic drugs to be retrieved from the AHA | 01/07/ 2015 | 01/08/ 2015 |  | INR: 0.00 | Pending
Activity 4 | Procurement plan: to be drafted and implemented, Indent monitoring requirement to be drafted | 01/06/ 2015 | 01/09/ 2015 |  | INR: 0.00 | In-process
Activity 5 | Regular follow-up with the store manager for the stock per month | 01/05/ 2015 |  |  | INR: 0.00 | Completed
Strategy 2: | Informing service users about the side-effects of the medications | Start Date | End Date | Responsible members | Budget | Status- Pending / Complete
Activity 1 | Prepare a list of common medications and related side-effects, educating the service user about the importance of medications and treatment for display within the OPD and IPD | 01/05/ 2015 | 2016-04-15 |  | INR: 0.00 | In-process
Activity 2 | Prepare pamphlets of common psychiatric disorders, medications and their side effects.
Activity 3 | Attach the pamphlets to the case papers after explaining the same verbally to the service user | 01/05/ 2015 | 01/06/ 2015 |  | INR: 0.00 | Completed
Activity 4 | Audio-visual medium for people who are illiterate | 01/05/ 2015 | 01/11/ 2015 |  | To be discussed with the HOD and Superintendent | In-process (we display this for SAATHI & MAITRI meetings, World Mental health day)
Activity 5 | Procure the soft copy of the same from HMHV | 01/07/ 2015 | 01/08/ 2015 |  | INR: 0.00 | Pending
Theme 3
Area for improvement: 3.1
Strategy 1: | Priorities of the Service users options will be discussed | Start Date | End Date | Responsible members | Budget | Status- Pending / Complete
Activity 1 | Sensitizing all the clinical and non-clinical staff on the benefits of involving service users for their treatment planning | 01/06/ 2015 |  |  | INR: 0.00 | In-process
Activity 2 | Compilation of all informed consent forms for all specialized procedures. | 01/05/ 2015 |  |  | INR: 0.00 | Completed
Activity 3 | SOP for applying restraint | 01/06/ 2015 | 31/4/2016 |  | INR: 0.00 | In-process
Strategy 2: | Develop criteria for discharge | Start Date | End Date | Responsible members | Budget | Status- Pending / Complete
Activity 1 | Document discharge criteria in IPD case sheet | 01/05/ 2015 | 01/08/ 2015 |  |  | Completed
Activity 2 | Check with HMHV for discharge procedure | 01/05/ 2015 | 01/05/ 2015 |  | INR: 0.00 | Completed
Activity 3 | Modify current standardized tools to record improvement in the service user and documenting the same | 01/05/ 2015 | 01/07/ 2015 |  | INR: 0.00 | Pending
Activity 4 | Standardized Checklist for discharge | 01/06/ 2015 | 01/07/ 2015 |  | INR: 0.00 | Completed
Activity 5 | Educating the care-givers for recovery of the service users | 01/06/ 2015 |  |  | INR: 0.00 | In-process
Strategy 3: | Implement the use of recovery plans in clinical practice in the OPD and IPD | Start Date | End Date | Responsible members | Budget | Status- Pending / Complete
Activity 1 | Training of the clinical and non-clinical staff by the Master trainers | 01/06/ 2015 |  |  | INR: 0.00 | In-process
Activity 2 | Distribution of notes to all the staff members | 01/06/ 2015 |  |  | INR: 0.00 | In-process
Activity 3 | Follow-up session | 01/09/ 2015 |  |  | INR: 0.00 | In-process
Activity 4 | Documentation | 01/06/ 2015 |  |  | INR: 0.00 | In-process
Area for improvement: 3.4
Strategy 1: | Maintaining separate file per service user within the out-patient department | Start Date | End Date | Responsible members | Budget | Status- Pending / Complete
Activity 1 | Request letter from the department of psychiatry | 01/05/ 2015 | 01/06/ 2015 |  | INR: 0.00 | Pending
Activity 2 | Follow-up and implementation | 01/06 /2015 | 01/08/ 2015 |  | INR: 0.00 | Pending
Activity 3 | A separate file for every new case within the department of psychiatry to be issued | 01/06/ 2015 | 01/08/ 2015 |  | To be procured from the hospital | Pending
Activity 4 | Informing the service users and respective care-givers of maintaining the file and carrying the same for every follow-up visit | 01/07/ 2015 |  |  | INR: 0.00 | Pending
Activity 5 | Recovery plans, social worker notes, clinical psychologist notes to be properly filed | 01/08 / 2015 |  |  | INR: 0.00 | Pending
Strategy 2: | Ensuring the information about service users is kept confidential. | Start Date | End Date | Responsible members | Budget | Status- Pending / Complete
Activity 1 | Explanation to the IPD staff members for the need for maintaining confidentiality | 01/05/ 2015 |  |  | INR: 0.00 | Completed
Activity 2 | Informing the IPD members of enquiring the identity of the person accessing the file. | 01/05/ 2015 |  |  | INR: 0.00 | Completed
Activity 3 | Discussing the same with the HOD | 01/05/ 2015 | 01/06/ 2015 |  | INR: 0.00 | Completed
Activity 4 | Construction of racks for storage of files or basing a cupboard by the nursing station with the specific purpose of storing files. | 01/07/ 2015 | 01/10/ 2015 |  | Enter As per applicable norms of the facility Budget: | Pending
Activity 5 | Draft a policy with regard to accessing information from the IPD for non-medical staff
Theme 4
Area for improvement: 4.1
Strategy 1: | Formation of grievance redressal cell | Start Date | End Date | Responsible members | Budget | Status- Pending / Complete
Activity 1 | AHA (HMHV) / Mr. Milesh Hamlai to help strategize activities with regard to Theme 4 | 01/05/ 2015 |  |  | INR: 0.00 | Completed
Activity 2 | Presentation to the GMERS - QR team members for a need for formation of grievance redressal cell and understand the way in which it is done- AHA (HMHV) | 01/06/ 2015 | 01/08/ 2015 |  | INR: 0.00 | Completed
Activity 3 | Discussion with the HOD | 01/06/ 2015 |  |  | INR: 0.00 | Completed
Activity 4 | Drafting an SOP and following upon it | 01/06/ 2015 | 2016-04-15 |  | INR: 0.00
Activity 5 | Review the existing policies from HMHV & HMHA, GMERS MCG (If any) |  |  |  | INR: 0.00 | Completed
Activity 6 | Approval from the Superintendent for the policy prepared. | 01/06/ 2015 | 2016-04-15 |  | INR: 0.00 | In-process
Area for improvement: 4.5
Strategy 1: | General policy on abuse, torture, harassment for service users as well as staff | Start Date | End Date | Responsible members | Budget | Status- Pending / Complete
Activity 1 | Discussion with the HOD for the same and follow-up | 01/06/ 2015 |  |  | INR: 0.00 | Completed
Activity 2 | Drafting an SOP and formation of a committee | 01/06/ 2015 | 01/08/ 2015 |  | INR: 0.00 | In-process
Activity 3 | Formal training of the same committee on SOP
Activity 4 | Awareness of the functioning and objective of the committee to be disseminated to all concerned. | 01/07/ 2015 | 01/08/ 2015 |  | INR: 0.00 | Pending
Strategy 2: | Access to legal aid | Start Date | End Date | Responsible members | Budget | Status- Pending / Complete
Activity 1 | Identify resources that will help service users advocate for their rights | 01/05/ 2015 | 2016-04-15 |  | INR: 0.00 | In-process
Activity 2 | Information related to concessions in bus pass/ train pass, disability certificate/ IQ testing/ Pension schemes to be explored | 01/06/ 2015 | 2016-03-31 |  | INR: 0.00 | Completed
Activity 3 | Discussing the details with the HOD after the resources have been identified | 01/05 /2015 | 2016-03-31 |  | INR: 0.00 | Completed
Activity 4 | Approval from the HOD for exhibiting related information within the OPD | 01/06/ 2015 | 2016-04-15 |  | INR: 0.00 | In-process
Theme 5
Area for improvement: 5.1
Strategy 1: | Access to financial resources for the service users | Start Date | End Date | Responsible members | Budget | Status- Pending / Complete
Activity 1 | Liaising with HMHV (for information related to pension scheme, placements, insurance; if any, referrals etc..) | 01/06/ 2015 | 01/08/ 2015 |  | INR: 0.00 | Pending
Activity 2 | Search for all organizations working for people with mental illness in Vadodara and maintaining a directory for same with the details mentioned in Gujarati | 01/06/ 2015 | 01/10/ 2015 |  | INR: 0.00 | Completed
Activity 3 | Ensuring the directory is located at a place within the OPD which is accessible to all | 01/06/ 2015 | 01/08/ 2015 |  | INR: 0.00 | In-process
Activity 4 | Ensuring a soft copy of the same is saved. | 01/07/ 2015 |  |  | INR: 0.00 | In-process
Activity 4 | Survey to understand the kind of information/assistance the service users would want from the survey- housing/ loans/ employment etc... | 01/06/ 2015 | 01/06/ 2015 |  | INR: 0.00 | Pending
Activity 5 | Survey questions to be validated and translated in Gujarati | 01/06/ 2015 | 01/06/ 2015 |  | INR: 0.00 | Pending
Activity 6 | The survey outcome to be shared with the HOD and everyone concerned and further activities to be planned. | 01/06/ 2015 | 01/07/ 2015 |  | INR: 0.00 | Pending
Strategy 2: | Guidance for parents of children with special needs | Start Date | End Date | Responsible members | Budget | Status- Pending / Complete
Activity 1 | Referrals to the clinical psychologist within the department, if appointed by then. |  |  |  | INR: 0.00 | Pending
Activity 2 | Maintaining a register with the contact details of facilities that provide guidance for children with disabilities (for disability certificates, IQ testing etc..) | 01/06/ 2015 | 01/08/ 2015 |  | INR: 0.00 | Completed
Activity 3 | Maintaining a directory with services available for children with special needs within Vadodara, schools in & around Vadodara , residential schools, any workshops/trainings/lectures- information to be updated for display within the OPD | 01/06/ 2015 | 01/08/ 2015 |  | INR: 0.00 | Completed
Activity 4 | Liaison with the pediatric department for referrals to the psychiatric department | 01/06/ 2015 | 01/08/ 2015 |  | INR: 0.00 | In-process
Activity 5 | Preparing a leaflet for general awareness about common psychiatric disorders in children. | 01/06/ 2015 | 01/07/ 2015 |  | INR: 0.00 | In-process
Activity 6 | Approval of the form from the HOD and implementation | 01/06/ 2015 | 01/08/ 2015 |  | INR: 0.00 | In-process
Activity 7 | Forming a parent-support group | 01/08/ 2015 |  |  | INR: 0.00 | Completed
Area for improvement: 5.4
Strategy 1: | Providing leisure activities to service users | Start Date | End Date | Responsible members | Budget | Status- Pending / Complete
Activity 1 | A list of requirements within the OPD and IPD to be discussed with the HOD and Superintendent *Benches to be stationed within the OPD(waiting area) * Cupboards & racks both within the IPD & OPD *TV *Radio *Newspaper *Yoga Mats * Designated area for recreation within the IPD | 01/06/ 2015 | 2016-04-15 |  |  | In-process
Activity 2 | Reading material to be made available within both the departments. Donated (In-house resources) | 01/06/ 2015 | 01/11/ 2015 |  | Supplied by the hospital | Completed
Activity 3 | To generate funds for the department by correspondence through CSR | 01/06/ 2015 | 01/11/ 2015 |  |  | Pending
Activity 4 | Yoga/ exercise or any activity for recreation to be initiated within the IPD | 01/07/ 2015 |  |  | INR: 0.00 | Pending
Activity 5 | Few service users who come to OPD for follow-up can be approached (Who teach Yoga-known resource) and can be given an honorarium through the funds generated; on voluntary basis. |  |  |  | As per available funds | Pending
Strategy 2: | To ensure functioning of the SAATHI self-help groups for caregivers | Start Date | End Date | Responsible members | Budget | Status- Pending / Complete
Activity 1 | Informing the care-givers of the support groups by displaying the information within the OPD | 01/05/ 2015 |  |  | INR: 0.00 | On-going
Activity 2 | Informing the psychiatrists , JR’s, Nursing staff (IPD & OPD) about the SAATHI meeting date well in advance for disseminating information about the same to the caregivers accordingly | 01/05/ 2015 |  |  | INR: 0.00 | completed
Activity 3 | Distribution of SAATHI flyers | 01/05/ 2015 |  |  | INR: 0.00 | completed
Activity 4 | Maintaining an attendance register for all the SAATHI meetings | 01/05/ 2015 |  |  | INR: 0.00 | completed
Activity 5 | Draft a policy with regard to the working of the group | 2015-07-01 | 2015-09-01 |  | INR: 0.00 | Pending

## Facility5a
Area for improvement:
Strategy:1 | Settingup the core gourp | Start Date | End Date | Responsible members | Budget | Status- Pending/Complete |  | New Deadline | Explanation for not meeting deadline | Proposed Plan for meeting new deadline
Activity 1 | Meeting with AHA, Dr., and other senior staff regarding formation of Core Group | 2015-02-23 | 2015-02-24 |  | INR 0 |  | Complete
Activity 2 | Development of the TOR for the Core Group |  | 2015-02-24 |  | INR 0 |  | Complete
Activity 3 | Meeting with AHA, Dr., and other senior staff regarding the core group meeting | 2015-03-09 | Till first meeting takes place |  | INR 0 |  | Complete
Activity 4 | Coordination with the AHA for the core group meeting | 2015-03-16 | 2015-03-17 |  | INR 0 |  | Complete
Activity 5 | First Core Group meeting | 2015-03-17 | 2015-03-17 |  | INR 0 |  | Complete
Activity 6 | Taking the reference and point discussed in the firt meeting develop an action plan and share it with Dr. | 2015-03-18 | 2015-03-21 |  | INR 0 |  | Complete
Activity 7 | Meeting of the core group minutes | 2015-03-18 | 2015-03-18 |  | INR 0 |  | Complete
Area of Improvement | Std 1.5 Service user can communicate freely and their right to privacy is respected
Strategy 2 Dealing with the system of phone calls
Activity 1 | Putting up the coin box at the main gate (pay and phone) | One month |  |  | N/A |  | Pending
Activity 2 | Putting up the written matter in the open ward regarding phone calls | One week |  |  | INR 0 |  | Pending
Activity 3 | Putting up a slide about the phone calls and proper communication channel – to inform the patients | One week |  |  | INR 0 |  | Pending
Activity 4 | Placing a sign and notice in Open Ward regarding phone calls and system | One week |  |  | INR 0 |  | Pending
Strategy 3. Dealing with issue of language translator
Activity 1 | Creating a dossier of language translator | Two months |  |  |  |  | Pending
Activity 2 | Contacting language translator | Two months |  |  |  |  | Pending
Area of Improvement | Std 1.7 Service users can enjoy fulfilling social and personal lives and remain engaged in community life and activities
Strategy 4. Developing recreation activities for patients
Activity 1 | Repair of treadmill and cycle | N/A |  |  | AHA will work on it |  | Pending
Activity 2 | Developing court of badminton | 3 months |  |  | N/A |  | Pending
Activity 3 | Taking out indoor games for the patients | 3 months |  |  | N/A |  | Pending
Activity 4 | Contacting Art of living and Bhranma Kumari for meditation and other activities | One week |  |  | INR 0 |  | Pending
Area of Improvement | Std 2.2 The Facility has skilled staff and provides good quality mental health services
Strategy 5. Dealing with issue of workload
Activity 1 | Human resource mapping | Three months |  |  | INR 0 |  | Pending
Activity 2 | Workload mapping | 3 months |  |  | INR 0 |  | Pending
Activity 3 | Writing to nursing colleges | One month |  |  | INR 0 |  | Pending
Activity 4 | Placing the request for vacancy of Occupational Therapists | AHA will tell |  |  | INR 0 |  | Pending
Activity 5 | Preparation of Job chart | Not given |  |  | INR 0 |  | Pending
Strategy 6. Issue of existing training material and its methodology
Activity 1 | Review of training design |  | - |  | 0 |  | Pending
Stretigy 7. Getting family support in patient recovery and bring caregivers together
Activity 1 | Caregiver Group for counselling | Three moths |  |  | N/A |  | Pending
Activity 2 | Family counselling along with the patient | 6 months |  |  | INR 0 |  | Pending
Activity 3 | Liaison for the purpose of counselling | N/A |  |  | INR 0 |  | Pending
Activity 4 | Putting up the notice regarding family counselling in OPD and Emergency – place, day and time | N/A |  |  | INR 0 |  | Pending
Activity 5 | Poster on Family counselling regarding what is this, benefits and importance | N/A |  |  | N/A |  | Pending
Activity 6 | Adding an option regarding job and educational opportunity. | N/A |  |  | N/A |  | Pending
Strategy 8. Dealing with the issue drug distribution
Activity 1 | Discussion with the head of the pharmacy for the proper system of drug distribution | 15 days |  |  | INR 0 |  | Pending
Activity 2 | Different color bags for pharmacy – drug distribution | N/A |  |  | N/A |  | Pending
Strategy 9. Dealing the issue of effective communication
Activity 1 | Training on effective Communication | After the TOT |  |  | N/A |  | Pending
Activity 2 | Monitoring of staff on behavioral aspects | N/A |  |  | INR 0 |  | Pending
Strategy 10. Dealing with the issues of organized information given to OPD patients / Caregivers – communication
Activity 1 | Development of information booklet | 3 months |  |  | INR 0 |  | Pending
Activity 2 | Setting up a help desk for the patients and caregivers | N/A |  |  | N/A |  | Pending
Strategy 11. Dealing with the issues of sorting out drop-out patients and contacting them
Activity 1 | Sorting out the drop out patients from the six month HIMS data | N/A | - |  | INR 0 |  | Pending
Activity 2 | Discussion with Dr regarding option in the HIMS software | N/A | - |  | INR 0 |  | Pending
Activity 3 | Seeking help of HMH- A for creating an option HIMS data | N/A | - |  | INR 0 |  | Pending
Strategy 12. Review and of medical records for ensuring the quality
Activity 1 | Looking at the clinical audits | 10 Months |  |  | INR 0 |  | Pending
Activity 2 | Training of MOs regarding referring patients to psychiatrists every after three months |  |  |  | INR 0 |  | Pending
Activity 3
Strategy 13. Training on CRPD / Rights
Activity 1 | Training on patients’ right and CRPD | After the TOT |  |  | N/A |  | Pending
Activity 2 | Human Rights and Mental health | After the TOT |  |  | N/A |  | Pending
Strategy 14. Dealing with the issue of staff performance, behaviour and encouragement
Activity 1 | Sensitivity workshop with the Attendants | After the TOT |  |  | N/A |  | Pending
Activity 2 | Circular for the Employee of the month | One month |  |  | INR 0 |  | Pending
Activity 3 | Board for the posting Employee of the month – sending out the request to the OT | One week |  |  | INR 0 |  | Pending
Activity 4 | Developing checklist to rate the staff performance | One week |  |  | INR 0 |  | Pending
Area of Improvement | Std 2.3 Treatment, psychological rehabilitation and links to support networks and other services are elements of a service user driven recovery plan and contributes to a service user’s ability to live independently in the community.
Strategy 15. Working on individual recover plan of the patient
Activity 1 | Training on how to develop individual recovery plan | After the TOT |  |  | N/A |  | Pending
Activity 2 | Small Group meeting to work on the indicators of individual recovery plan | N/A |  |  | INR 0 |  | Pending
Activity 3 | Preparation of list of priority illness | One month |  |  | INR 0 |  | Pending
Activity 4 | Development of checklist for induction | 3 months |  |  | INR 0 |  | Pending
Activity 5 | Credential and privilege form | 3 months |  |  | INR 0 |  | Pending
Activity 6 | Scan the personal file of the attendants | 3 months |  |  | INR 0 |  | Pending
Strategy 16. Advance directive and understanding
Activity 1 | Training on advance directive | - |  |  | INR 0 |  | Pending
Activity 2 | Collecting material on advance directive |  |  |  | INR 0 |  | Pending
Activity 3 | Presentation of advance directives | Not decided |  |  | INR 0 |  | Pending
Area of Improvement | Std 3.2 Procedures and safeguards are in place to prevent detention and treatment without free and informed consent.
Strategy 17. Staff knowledge and understanding about Mental health act
Activity 1 | Booster training on the Mental health act (1987) | One month |  |  | INR 0 |  | Pending
Activity 2
Activity 3
Area of Improvement | Std 4.1 Service users have the right to be free from verbal, mental, physical and sexual abuse and physical and emotional neglect.
Strategy 18 Dealing with torture and inhuman treatment
Activity 1 | Installation of CCTV Camera | Not decided yet |  |  | N/A |  | Pending
Activity 2 | Review of the seclusion policy | One month |  |  | INR 0 |  | Completed
Activity 3 | Training on Seclusion | After the TOT |  |  | N/A |  | Pending
Activity 4 | Documentation of the seclusion system and developing a proper documentation strategy | 3 months |  |  | INR 0 |  | On going
Strategy 19. Dealing with Attendants behaviour
Activity 1 | Quarterly, small team meeting with attendants. | N/A |  |  | INR 0 |  | Pending
Activity 2 | Self-appraisal of attendants | N/A |  |  | INR 0 |  | Pending
Activity 3 | Documentation of each meeting and review the discussion. | N/A |  |  | INR 0 |  | Pending
Activity 4 | Development of checklist for the regular supervision of attendants | N/A |  |  | INR 0 |  | Pending
Activity 5
Activity 6
Strategy 20. Dealing with emotional neglect of the patient
Activity 1 | Define emotional neglect | N/A |  |  | INR 0 |  | Pending
Activity 2 | Sensitization of the staff on emotional neglect | N/A |  |  | INR 0 |  | Pending
Activity 3 | Supervision and support of the staff | N/A |  |  | INR 0 |  | Pending
Strategy 21 Setting the system of seclusion and restrain
Activity 1 | Training on Seclusion | After the TOT |  |  | N/A |  | Pending
Activity 2 | Supervision and sensitization of the staff | N/A |  |  | INR 0 |  | Pending
Activity 3 | Finding out the challenges of the attendants and problem solving | N/A |  |  | INR 0 |  | Pending
Activity 4 | Training on how to communicate and deal with the patients and relatives | After the TOT |  |  | INR 0 |  | Pending
Activity 5 | Documentation of Seclusion and restraint | N/A |  |  | INR 0 |  | Pending
Activity 6 | Orientation of the nursing staff on to deal with inhuman and degrading treatment of patient | N/A |  |  | INR 0 |  | Pending
Activity 7 | Seting up the improve supervision by nursing staff of attendants | N/A |  |  | INR 0 |  | Pending
Strategy 22 Privacy of the patients in the ward
Activity 1 | Placing curtains in the wards. | N/A |  |  | INR 0 |  | Pending
Activity 2 | Developing Hand-outs for privacy for the staff | N/A |  |  | N/A |  | Pending
Activity 3 | Orientation of staff about privacy |  |  |  | INR 0 |  | Pending
Strategy 23 Working with the family and caregivers | [6 empty] | Pending
Activity 1 | Setting up the system about how and what information should be given to the relative | N/A |  |  | INR 0
Activity 2 | Development of a 6 day plan to discussion with the relatives of the patients. | One month |  |  | INR 0 |  | Pending
Activity 3 | Screening small clipping on different mental health issues to the families of the patients | One month |  |  | INR 0 |  | Pending
Activity 4 | Setting up the system of family counseling everyday between 3-4 pm | N/A |  |  | INR 0 |  | Pending
Activity 5 | Advertising family counseling system in the hosptial | N/A |  |  | INR 0 |  | Pending
Strategy 24 Dealing with fights among users
Activity 1 | To avert the fights training of staff on routine clinical practices. | N/A |  |  | INR 0 |  | Pending
Area of Improvement | Std 4.2 Alternative methods are used in place of seclusion and restraint as means of de-escalating potential crises:
Strategy 25 Developing De-escalation
Activity 1 | Development of set of indicators of to identify the patients | N/A |  |  | INR 0 |  | Pending
Activity 2 | Training on de-escalation | N/A |  |  | INR 0 |  | Pending
Activity 3 | Complete ban on physical restraint | With the immediate effect |  |  | INR 0 |  | Pending
Area of Improvement | Std 4.5 Safeguards are in place to prevent torture or cruel, inhuman or degrading treatment and other forms of ill-treatment and abuse.
Strategy 26.Policy regarding abuse and Grievances
Activity 1 | Awerenss regarding abuse among staff | N/A |  |  | N/A |  | Pending
Activity 2 | Setting up the system of complain | N/A |  |  | INR 0 |  | Pending
Activity 3 | Opening the complain box every Thursday | N/A |  |  | INR 0 |  | Pending
Activity 4 | Documentation of complains | N/A |  |  | INR 0 |  | Pending
Activity 5 | Revive grievances system of the hospital | N/A |  |  | INR 0 |  | Pending
Activity 6 | Appointment of the nodal person for grievances system | N/A |  |  | INR 0 |  | Pending
Activity 9 | Assistance to the patients in terms of paper, pen and writing down the complaint |  |  |  | INR 0 |  | Pending
Activity 10 | Awerness among staff about the institutational policy related to abuse | N/A |  |  | INR 0 |  | Pending
Activity 11 | Placing signage / write-up in the wards and OPD regarding the grievance redressal mechanism | N/A |  |  | INR 0 |  | Pending
Activity 12 | The role and responsibility of each staff need to be explained and demonstrated |  |  |  | INR 0 |  | Pending
Activity 13 | Develop linkage with district legal Aid services. |  |  |  | INR 0 |  | Pending
Activity 14 | Set-up a desk within the hospital for the legal aid. |  |  |  | INR 0 |  | Pending
Area of Improvement | Std 5.1 Service users are supported in gaining access to a place to live and have the financial resources necessary to live in the community.
Strategy 27 Accessibility of social services
Activity 1 | Linkages with the social welfare department | N/A |  |  | INR 0 |  | Pending
Activity 2 | Developing a reference kit to cater the different needs of patients like marriage, job, legal etc | N/A |  |  | INR 0 |  | Pending
Activity 3 | Develop a dialogue with the social welfare department and hospital | N/A |  |  | INR 0 |  | Pending
Activity 4 | Review mental health act in relation to voting rights | N/A |  |  | INR 0 |  | Pending

## Facility5b
Strategy | Theme | Start Date | End Date | Responsible members | Budget | Status- Pending/Complete August 28th,2015 | Remarks | New Timeline (add date of entering)
Theme 1: The right to an adequate standard of living (Article 28 of the CRPD)
Area of Improvement | Std 1.5 Service user can communicate freely and their right to privacy is respected
Strategy 2 Dealing with the system of phone calls
Activity 1 | Putting up the coin box at the main gate (pay and phone) | 2015-06-24 | 2015-07-24 |  | INR 0 | Completed |  | -
| At the new gate the regular phone can be used for the calls. (could be done as per the permit) | 2015-06-24 | 2015-08-24 |  |  | Completed |  | -
Activity 2 | Putting up the written matter in the open ward regarding phone calls | 2015-06-24 | 2015-06-30 |  | INR 0 | Completed |  | -
Activity 3 | Putting up a slide about the phone calls and proper communication channel – to inform the patients | 2015-06-24 | 2015-06-30 |  | INR 0 | Completed |  | -
Activity 4 | Placing a sign and notice in Open Ward regarding phone calls and system | 2015-06-24 | 2015-06-30 |  | INR 0 | Completed |  | -
Strategy 3. Dealing with issue of language translator | [7 empty] | -
Activity 1 | Creating a dossier of language translator | 2015-06-24 | 2015-07-24 |  | INR 0 | Completed |  | -
3.1.1 | Review the old contact list
3.1.2 | Contacting MS university for formal support
3.1.3 | Contacting individuals who are ready to volunteer
3.1.4 | Coming-up with the new list for language translator
3.1.5 | Incorporating the new list in the maunal
Activity 2 | Contacting language translator | 2015-06-24 | 2015-07-24 |  | INR 0 | Completed
Area of Improvement | Std 1.7 Service users can enjoy fulfilling social and personal lives and remain engaged in community life and activities
Strategy 4. Developing recreation activities for patients
Activity 1 | Repair of treadmill and cycle | 2015-06-24 | 2015-07-24 |  |  | Completed
4.1.1 | Contacting vendor for repair
4.1.2 | Sending treadmill and cycle for repair
Activity 2 | Developing badminton court | 2015-06-24 | 2015-07-24 |  | 5000 | Under process
4.2.1 | Placing demand to admin for each ward. |  |  |  |  | Completed
4.2.2 | Badminton rackets are being provided |  |  |  |  | completed
Activity 3 | Taking out indoor games for the patients | 2015-06-24 | 2015-07-24 |  | 10000 | Completed
Activity 4 | Meditation and yoga practices for the patients | 2015-06-24 | 2015-07-24 |  | INR 0 | Completed
4.1.1 | Discussion with Dr. for his approval
4.1.2 | Contacting for meditation
4.1.3 | Contacting art of living for yoga
4.1.4 | Inviting instructor to visit the hospital
4.1.5 | Setting up the system of yoga and medication in skill training center
4.1.6 | Involving patients who are not part of the skill centre and train them.
Area of Improvement | Std 2.2 The Facility has skilled staff and provides good quality mental health services
Strategy 5. Dealing with issue of workload
Activity 1 | Human resource mapping | 2015-04-29 | 2015-07-29 |  | INR 0 | Completed
5.1.1
5.1.2
5.1.3
Activity 2 | Workload mapping | 2015-06-24 | 2015-12-24 |  | INR 0 | Under process
5.2.1
5.2.2
5.2.3
Activity 3 | Getting support and help from the nursing colleges to tackle the issue of staff shortage | 2015-04-29 | 2015-07-24 |  | INR 0 | Completed
5.3.1 | Writing to nursing colleges
5.3.2 | Setting up the system and asigning jobs to the students
Activity 4 | Placing the request for vacancy of Occupational Therapists | 2015-06-24 | 2015-07-24 |  | INR 0 | Completed
Activity 5 | Preparation of Job chart | 2015-06-24 | 2015-12-24 |  | INR 0 | Completed
Strategy 6. Issue of existing training material and its methodology - skill development of the staff
Activity 1 | Review of training design | 2015-06-24 | 2015-12-24 |  | INR 0 | Under process
6.1.1 | collecting the PPTs of different trainings
6.1.2 | Working on the methodology of the training
6.1.3 | Compiling and developing a reference manual of training
6.1.4 | Intigrating the quality rights training into the training schedule of the hospital
Stretigy 7. Getting family support in patient recovery and bring caregivers together
Activity 1 | Review the system of caregiver counseling and linkages with Saathi Group for prolonged and sustainable systematic approach | 2015-06-24 | 2015-09-24 |  | INR 0 | Not completed
7.1.1 | Review of counseling material
7.1.2 | Developing material that are appropirate for caregivers counseling
Activity 2 | Caregivers' counselling along with the patient | 2015-06-24 | 2015-12-24 |  | INR 0 | Under process
7.2.1 | Developing the system of caregivers' counseling along with the patients
Activity 3 | Liaison for the purpose of counselling | 2015-06-24 | 2015-12-24 |  | INR 0
Activity 4 | Putting up the notice regarding family counselling in OPD and Emergency – place, day and time | 2015-06-24 | 2015-12-24 |  | INR 0 | Completed
7.4.1 | Developing the material to be placed in the wards
7.4.2 | Placing the material on the wall
Activity 5 | Poster on Family counselling regarding what is counseling, benefits and importance | 2015-06-24 | 2015-12-24 |  | INR 5000 | Being developed
7.5.1 | collecting the materials online
7.5.2 | Desiging the poster
7.5.3 | Getting the post printed
Activity 6 | Adding an option regarding job and educational opportunity in the poster. | 2015-06-24 | 2015-12-24
Strategy 8. Dealing with the issue drug distribution
Activity 1 | Discussion with the head of the pharmacy for the proper system of drug distribution | 2015-06-24 | 2015-07-10 |  | INR 0
Activity 2 | Different color bags for pharmacy – drug distribution | 2015-06-24 | 2015-07-24 |  |  | Completed
8.2.1 | Contacting head of the pharma department
8.2.2 | Discussion with Dr. for his approval
8.2.3 | Exploring the cost and place where this could bought
Strategy 9. Dealing the issue of effective communication
Activity 1 | Training on effective Communication | After the TOT |  |  | 5000 | Under process
Activity 2 | Monitoring of staff on behavioral aspects | 2015-06-24 | 2015-12-24 |  | INR 0 | Under process
9.2.1 | Developing the check-list for monitoring
9.2.2 | Circulating the check-list to all heads for monitoring
9.2.3 | Compiling the findings and sharing with the heads
Strategy 10. Dealing with the issues of organized information given to OPD patients / Caregivers – communication
Activity 1 | Development of information booklet | 2015-06-24 | 2015-08-07 |  | INR 0 | Not completed
10.1.1 | Collecting the materials which is corrently used for such purpose
10.1.2 | Compiling the materials and developing a booklet
10.1.3
Activity 2 | Setting up a help desk for the patients and caregivers (legal issues) | 2015-06-24 | 2015-12-24 |  | INR 0 | Not completed
10.2.1 | Searching for a legal person
10.2.2 | Developing a team which can work with the legal person
Strategy 11. Dealing with the issues of sorting out drop-out patients and contacting them
Activity 1 | Sorting drop-put patients from the HIMS data | 2015-06-24 | 2015-12-24 |  | INR 0 | Under process
10.1.1 | Discussion with Dr. regarding option in the HIMS software |  |  |  |  | Completed
10.1.2 | Seeking help of HMH- A for creating an option HIMS data |  |  |  |  | Completed
10.1.3 | Sorting out the drop out patients from the six month HIMS data |  |  |  |  | Under process
Strategy 12. Review of medical records for ensuring the quality- Looking at the clinical audits
Activity 1 | Clinical audits
12.1.1 | Defining indicators and objective of the audit - topic wise | 2015-06-24 | 2016-06-24 |  | INR 0 | On going
12.1.2 | Defining methodology of the audit for each - topic wise | 2015-06-24 | 2016-06-24 |  | INR 0 | On going
Activity 2 | Training / discussion with MOs regarding referring patients to psychiatrists every after three months | 2015-06-24 | 2016-06-24 |  | INR 0 | On going
Strategy 13. Training staff on CRPD and Human Rights
Activity 1 | Training on patients’ right and CRPD | 2015-08-25 | 2015-11-16 |  | INR 19000 | Completed
Activity 2 | Human Rights and Mental health | 2015-08-25 | 2015-11-16 |  | INR 19000 | Under procrss
Strategy 14. Dealing with the issue of staff performance, behaviour and encouragement
Activity 1 | Behaviour sensitivity workshop with the Attendants - as part of communication training | After the TOT |  |  | INR 0 | After the communication Training
Activity 2 | Employee of the month | 9/4//2015 | 2015-09-05 |  | INR 0 | In process
14.2.1 | Developing checklist to rate the staff performance
14.2.2 | Board for the posting Employee of the month – sending out the request to the OT
Theme 2: The right to enjoyment of the highest attainable standard of physical and mental health (Article 25 of the CRPD)
Area of Improvement | Std 2.3 Treatment, psychological rehabilitation and links to support networks and other services are elements of a service user driven recovery plan and contributes to a service user’s ability to live independently in the community.
Strategy 15. Working on individual recover plan of the patient
Activity 1 | Training on how to develop individual recovery plan | 2015-12-06 | 2015-09-30 |  | INR 20,000 | Completed
Activity 2 | Small Group meeting to work on the indicators of individual recovery plan | 2015-10-04 | 2015-10-05 |  | INR 0 | Completed
Activity 3 | Preparation of list of priority illness | 2015-10-04 | 2015-10-05 |  | INR 0 | Not completed
Strategy 16 | Staff Development
Activity 4 | Develop checklist for induction | 2015-04-23 | 2015-10-07 |  | INR 0 | Under process
Activity 5 | Credential and privilege form | 2015-04-23 | 2015-10-07 |  | INR 0 | Completed
Activity 6 | Scan personal files of the attendants to identify the skills and potential | 2015-04-23 | 2015-10-07 |  | INR 0 | Under Process
Strategy 17. Advance directive and understanding
Activity 1 | Training on advance directive | 2015-04-16 | 2015-12-16 |  | INR 0 | On-going
17.1.1 | Collecting material on advance directive
17.1.2 | Presentation on advance directives
Theme 3: The right to exercise legal capacity and the right to personal liberty and security of person (Articles 12 and 14 of the CRPD)
Area of Improvement | Std 3.2 Procedures and safeguards are in place to prevent detention and treatment without free and informed consent.
Strategy 18. Staff knowledge and understanding about Mental health act
Activity 1 | Booster training on the Mental health act (1987) | 2015-04-16 | 2015-05-16 |  | INR 0 | On-going
Area of Improvement | Std 4.1 Service users have the right to be free from verbal, mental, physical and sexual abuse and physical and emotional neglect.
Strategy 19 Dealing with torture and inhuman treatment
Activity 1 | Installation of CCTV Camera | 2015-04-29 | 2015-04-29 |  | INR 10000 | Suspended
19.1.1 | Invite quotation from the vendors for CCTV camera
19.1.2 | Review and selection of the vendor
19.1.3 | Installation of CCTV Cameras in the wards
Activity 2 | Review of the seclusion policy | 2015-04-29 | 2015-05-29 |  | INR 0
Activity 3 | Training on how to fill Seclusion forms | 2015-01-08 | 2015-08-30 |  | INR 0 | Competed
Activity 4 | Documentation of the seclusion system and developing a proper documentation strategy | 2015-04-29 | 2015-07-29 |  | INR 0 | On going
Strategy 20. Dealing with Attendants behaviour
Activity 1 | Quarterly, small team meeting with attendants. | 2015-04-29 | 2015-05-29 |  | INR 0 | Activity clubbed with strategy
20.1.1 | Documentation of each meeting and review the discussion.
Activity 2 | Self-appraisal of attendants | 2015-04-29 | 2015-07-29 |  | INR 0 | In process
Activity 3 | Seting up the improve supervision by nursing staff of attendants | 2015-04-29 | 2015-05-29 |  | INR 0 | Not completed
20.3.1 | Development of checklist for the regular supervision of attendants
Strategy 21. Dealing with emotional neglect of the patient
Activity 1 | Define emotional neglect | 2015-04-29 | 2015-05-15 |  | INR 0 | In process
Activity 2 | Sensitization of the staff on emotional neglect | 2015-04-29 | 2015-12-30 |  | INR 0 | On going
Activity 3 | Supervision and support of the staff to tackle with emotional neglect. | 2015-04-29 | 2015-12-30 |  | INR 0 | Not completed
21.3.1 | Developing a checklist to monitoring the staff to tackle with emotional neglect
21.3.2 | Filling up the check-list to monitor the staff
Strategy 22 Setting the system of seclusion and restraint
Activity 1 | Training on Seclusion - how to stop / alternativ method | After the TOT |  |  | INR 0 | Not completed
Activity 2 | Supervision and sensitization of the staff on seclusion restraint | 2015-04-29 | 2015-12-30 |  | INR 0 | On going
Activity 3 | Finding out the challenges of the attendants and problem solving | 2015-04-29 | 2015-12-30 |  | INR 0 | On going
Activity 4 | Training on how to communicate and deal with the patients and relatives | After the TOT |  |  | INR 0 | Not completed
Activity 5 | Documentation of Seclusion and restraint | 2015-04-29 | 2015-06-30 |  | INR 0 | Completed
Activity 6 | Orientation of the nursing staff on to deal with inhuman and degrading treatment of patient | 2015-08-25 | 2015-11-16 |  | INR 19000 | Under procrss
Strategy 23 Privacy of the patients in the ward
Activity 1 | Placing curtains in the wards. | 2015-04-29 | 2015-05-29 |  | INR 0 | Completed
Activity 2 | Developing Hand-outs for privacy for the staff | 2015-04-29 | 2015-07-29 |  | INR 0 | Under procrss
Activity 3 | Orientation of staff about privacy | 2015-08-25 | 2015-11-16 |  | INR 19000 | Under procrss
Strategy 24 Working with the family and caregivers
Activity 1 | Setting up the system about how and what information should be given to the relative | 2015-04-29 |  |  | INR 0
Activity 2 | Development of a 6 day plan to discussion with the relatives of the patients. | 2015-04-29 | 2015-05-29 |  | INR 0 | Not completed
Activity 3 | Screening small clipping on different mental health issues to the families of the patients | 2015-04-29 | 2015-05-29 |  | INR 0 | On-going
Activity 4 | Setting up the system of family counseling everyday between 3-4 pm | 2015-04-29 | 2015-05-29 |  | INR 0 | On-going
Activity 5 | Advertising family counseling system in the hosptial | 2015-04-29 | 2015-05-29 |  | INR 0 | In process
Strategy 25 Dealing with fights among users
Activity 1 | To avert the fights training of staff on routine clinical practices - train staff on rights issue | 2015-04-29 | 2015-04-29 |  | INR 0 | Under procrss
Theme 4: Freedom from torture or cruel, inhuman or degrading treatment or punishment and from exploitation, violence and abuse (Articles 15 and 16 of the CRPD)
Area of Improvement | Std 4.2 Alternative methods are used in place of seclusion and restraint as means of de-escalating potential crises:
Strategy 26 Developing De-escalation
Activity 1 | Defining set of indicators of to identify the patients | 2015-05-24 | 2015-09-24 |  | INR 0 | Not completed
Activity 2 | Training on de-escalation | 2015-05-24 | 2015-09-24 |  | INR 0 | Not completed
Activity 3 | Complete ban on physical restraint | 2015-05-24 | 2015-05-24 |  | INR 0 | Pending
26.3.1 | Taking-out circular informing staff about the complete ban on physical restraint
Area of Improvement | Std 4.5 Safeguards are in place to prevent torture or cruel, inhuman or degrading treatment and other forms of ill-treatment and abuse.
Strategy 27.Policy regarding abuse and Grievances
Activity 1 | Awerenss regarding abuse among staff | 2015-04-29 | 2015-04-29 |  | INR 0 | Completed
Activity 2 | Setting up the system of complain and grievances redressal | 2015-05-24 | 2015-10-24 |  | INR 0 | Completed
27.2.1 | Revive grievances system of the hospital |  |  |  |  | Completed
27.2.2 | Appointment of the nodal person for grievances system
27.2.3 | Opening the complain box every Thursday
27.2.4 | Documentation of complains
27.2.5 | Assistance to the patients in terms of paper, pen and writing down the complaint
27.2.6 | Placing signage / write-up in the wards and OPD regarding the grievance redressal mechanism
Activity 3 | Awerness among staff about the institutational policy related to abuse | 2015-05-24 | 2015-10-24 |  | INR 0 | Not completed
27.3.1 | The role and responsibility of each staff need to be explained and demonstrated |  |  |  | INR 0 | Pending
Activity 4 | Set-up a desk within the hospital for the legal aid. | 2015-05-24 | 2015-10-24 |  | INR 0 | Not completed
27.3.2 | Develop linkage with district legal Aid services.
Theme 5: The right to live independently and be included in the community (Article 19 of the CRPD)
Area of Improvement | Std 5.1 Service users are supported in gaining access to a place to live and have the financial resources necessary to live in the community.
Strategy 28 Accessibility of social services
Activity 1 | Linkages with the social welfare department | 2015-05-24 | 2015-12-24 |  | INR 0 | Not completed
28.1.1 | Develop a dialogue with the social welfare department and hospital
Activity 2 | Developing a reference kit to cater the different needs of patients like marriage, job, legal etc | 2015-05-24 | 2015-12-24 |  | INR 0 | Not completed
Activity 3 | Review mental health act in relation to voting rights | 2015-05-24 | 2015-06-24 |  | INR 0 | Not completed

## Facility6
Strategy: | Making infrastructural changes in the facility to accomodate persons with disabilities | Start Date | End Date | Responsible members | Budget | Status of the activity | New deadline (add date of entering) | Explanation for not meeting the deadline | Proposed plan for meeting deadline | No. of people in the meeting | Name and designation of the people in the meeting | Plan for sustainability
Activity 1 | Identifying areas within the facility where signage, ramps, handle bars and maps need to be made available/modified | Activity achieved |  |  |  | Complete |  |  |  | 8
Activity 2 | Preparing a chart/ list with all the requirements, to be shared with the rest of the team members | Activity achieved |  |  |  | Complete |  |  |  | 8
Activity 3 | Consulting a few users on how to make the map of the facility more user friendly - to be discussed with the team |  |  |  |  | Complete | 7th September, 2015 - activity achieved |  | Get the responsible persons to consult with a few users in the in-patient facility | 8
Acitvity 4 | Gather material and information on "how to build a barrier free environment" - best practices, government guidelines | Activity achieved |  |  |  | Complete |  |  |  | 8
Activity 5 | Finding a suitable painter and carpenter to make bring about these infrastructural changes | Activity achieved |  |  |  | Complete |  |  |  | 8
Activity 6 | Discussing the requirements with the painter and carpenter | Activity achieved |  |  |  | Complete |  |  |  | 4
Activity 7 | Preparing a budget |  | 30th June, 2015 |  |  | Complete |  |  |  | 4
Activity 8 | Making the changes |  | 15th July, 2015 |  |  | Complete |  |  |  | 8
Activitiy 9 | Installing a map of the facility and sign boards with health promotion messages | 22nd August, 2015 | 5th September, 2015 |  |  | Complete |  |  | Feed back the information received from the users, to help make a more user friendly map. share the plan with the painter and the carpenter. | 8
Activity 10 | Making other infrastructural changes in the toilets and bathrooms - handle bars and building ramps: PIU | 25th December, 2015 |  |  |  | End date cannot be estimated due to delays in the renovation at the hospital. |  |  |  | 4
Area for improvement: Standard 1.3 - Hygiene and sanitary requirements
Strategy | Improving and upgrading hygiene standards in the facility | [5 empty] | New deadline |  | Proposed plan for meeting deadline |  |  | Plan for sustainability
Activity 1 | Identifying areas of the hospital which need special attention in terms of maintaining hygiene standards | 1st July, 2015 | 2nd July, 2015 |  |  | Complete |  |  |  | 2 |  | Through daily rounds, conducted by the staff nurse in charge. Other staff members are expected to report to the staff nurse in charge, in case they find the hygiene standards not being maintained.
Activity 2 | Prepare a curriculum on the importance of hygiene and how to maintain hygiene with the nursing staff (based on their training) | 2nd July, 2015 | 12 th July, 2015 |  |  | Complete | 10th September, 2015 - Activity achieved |  | Sitting with the core team and planning innovative methods to conduct hygiene sensitisation for the staff, users and caregivers at the facility. Planning to make such an activity, exercise oriented. | 4
Activity 3 | Get examples and procedures from other hospitals regarding hygiene standards | 1 st July, 2015 | 2nd July, 2015 |  |  | Complete |  |  |  | 8
Activity 4 | Prepare a duty chart and schedule for each section of the staff - time and responsibility regarding maintaining hygiene | 5 th July, 2015 | 15 th July, 2015 |  |  | Complete |  |  |  | 6 |  | This responsibility has been taken up by the staff nurse in-charge, issued as per the orders of the hospital. Sweepers are expected to clean, staff nurses are expected to check the level of hygiene, and the head nurse monitors the conditions using checklists.
Activity 5 | Train staff on hygiene standards, its importance and the duty charts | 15th July, 2015 | 25th July, 2015 |  |  | Complete |  |  | Based on the activities proposed by the core team, conducting sensitisation in batches | 38
Activity 6 | Install signage and boards with basic message on maintaining hygiene and why it is important. For example - "wash hands here - it is important because..." | 10th July, 2015 | 25 th July, 2015 |  |  | Complete |  |  | The plan is to get these sign board painted along with the map of the facility | 3
Activity 7 | Conduct a group discussion with the users and caregivers on the importance of hygiene. Discussion regarding why maintaining hygiene is also difficult. - OT activity | 15th July, 2015 | 25th July, 2015 |  |  | Ongoing | The activity has begun in the OT. |  | Conducting the sensitisationa activities for the users simultaneously in separate batches from the staff | 2 |  | Group demonstrations around hygiene are held regularly in the OT, conducted by the OT in charges. The PSVs also help in conducting these demonstrations.
Activity 8 | Tracking progress and cleanliness looking at the charts - regular rounds in the wards (persons responsible for ensuring hygiene) | 25th July, 2015 |  |  |  | Ongoing |  |  |  | 6 |  | These charts have been formalised. These are submitted to the Jila Panchayat on a monthly basis as per the orders of the CDHO.
Activity 9 | Monitoring of charts and hygiene conditions - monthly | 31st December, 2015 |  |  |  | Ongoing - weekly monitoring |  |  |  | 6 |  | These charts have been formalised. These are submitted to the Jila Panchayat on a monthly basis as per the orders of the CDHO.
Activity 9 | Rewarding the staff who have upheld hygiene standards by making them the "employee of the month" - to be decided on the basis of rounds and a look at the duty charts | 1st August, 2015 |  |  |  | Ongoing |  |  | Creating job charts for each post. Sharing information about job charts to staff members in a public meeting and sharing with them, the reward process.The committee for rewarding the employee of the month has been decided. | 8 |  | Committee for rewarding the efforts of the staff.
Area for improvement: Standard 1.7 - Participation in community life and activities
Strategy 1 | Improving the accessibility of the male ward, and allowing movement of the users | Start Date | End Date | Responsible members | Budget | Status of the activity | New deadline |  | Plan for meeting the new deadline |  |  | Plan for sustainability
Strategy 1 | Call all levels of staff - meeting across the facility to discuss the project, especially with those who were not a part of the improvement plan | Activity achieved |  |  |  | Complete |  |  |  | 38 |  | This activity is now a part of the activity schedule for the service users. The users are brought out in the evening. The staff nurses on duty are in-charge of bringing them out, with the help of the attendants and the PSVs. This issue is taken up for discussion in every staff meeeting conducted on a monthly basis. The importance of users coming of the wards is strongly discussed in every meeting.
Activity 2 | Make a presentation on the QR project and work of the "Challengers" team till now. Asking for volunteers from the attendant staff to be a part of the team | Activity achieved |  |  |  | Complete |  |  |  | 38
Activity 3 | Inform the staff regarding conducting a "sensitisation activity" - allowing free movement of the users around the facility for 2 hours | Activity achieved |  |  |  | Complete |  |  |  | 38
Activity 4 | Inviting suggestions, comments and having a discussion regarding the problems related to conducting such an activity | Activity achieved |  |  |  | Complete |  |  |  | 38
Activity 5 | Preparing a plan with all the staff members present on how the activity will be conducted | Activity achieved |  |  |  | Complete |  |  |  | 38
Activity 6 | Conducting the "sensitisation activity"- allowing service users to move freely across the facility for a stipulated time duration, during OPD hours | Activity achieved |  |  |  | Complete |  |  |  | 5
Activity 7 | Create clusters of users to be brought out - such that each user gets a chance to come out of the wards without discrimination | Activity achieved |  |  |  | Complete |  |  |  | 5
Activity 8 | Prepare a schedule to bring out the users - turn by turn, according to their clusters | Activity achieved |  |  |  | Complete |  |  |  | 3
Activity 9 | Arrange an all staff meeting to discuss the activity and the plan ahead to bring the users out | Activity achieved |  |  |  | Complete |  |  |  | 38
Strategy 2 | Providing leisure activities to service users | Start Date | End Date | Responsible members | Budget | Status of the activity | [5 empty] | Plan for sustainability
Activity 1 | Get a list of service users to discuss the issue of leisure activities | Activity achieved |  |  |  | Complete |  |  |  | 3 |  | Activities are a part of the daily schedule for all the service users. This is due to the presence of a recreation room, with a clearly chalked out time table. Two staff members have been officially given charge of handling and managing the activities within the hospital.
Activity 2 | Prepare a set of interview questions related to service users' preferences for leisure activities | Activity achieved |  |  |  | Complete |  |  |  | 2
Activity 3 | Have a group or an individual discussion with the service users about what their preferences are | 9th June, 2015 | 20th June, 2015 |  |  | Complete |  |  |  | 2
Activity 4 | Make a list of activities which can be provided by the staff and the infrastructural requirements for these activities | 15th June, 2015 | 25th June, 2015 |  |  | Complete |  |  |  | 4
Activity 5 | Collaborate with other parties - individuals, NGOs etc. to bring in entertainment/activities from outside or to provide support for those organised within the hospital | 20th June, 2015 | 25th June, 2015 |  |  | Ongoing | The donor committee is in place now. |  | Getting one person responsible for collaborating with NGOs, especially as the social worker prepares to leave the facility. | 3 |  | A few NGOs have been contacted. The representatives from these NGOs come regularly to the hospital on a fixed day of the week, to organise activities for service users.
Activity 6 | Contact and make a list of volunteers for these activities | 15th June, 2015 | 22nd June, 2015 |  |  | Complete |  |  | Making one person responsible for making a list of volunteers. | 3
Activity 7 | Have a designated activity area |  | 25th June, 2015 |  |  | Complete |  |  |  | 10
Activity 8 | Have an activity schedule - consisting of activities within the hospital and those provided by individuals from outside | 20th June, 2015 | 28th June, 2015 |  |  | Complete |  |  |  | 3
Activity 9 | Communicate to the persons responsible for conducting these activities and assisting users - through a meeting | Activity achieved |  |  |  | Ongoing |  |  |  | 3
Area for improvement: Standard 2.2 - Skilled staff and good quality mental health services
Strategy 1 | Providing assistance, support and information to users coming to the facility | Start Date | End Date | Responsible members | Budget | Status of the activity | New deadline |  | Plan for achieving the new deadline |  |  | Plan for sustainability
Activity 1 | Prepare an agenda for setting up an enquiry table at the entrance of the facility | 21st August | 25th August, 2015 |  |  | Complete |  |  | The plan is to work on the activities listed above, ensure that a sustainable mechanism is in place and then move towards achieving this activity. | 7 |  | A designated area for an enquiry room has been allotted in the OPD. There are sign boards encouraging people to ask questions. The PSVs sit on this enquiry table, every evening. This is also considered to be the recovery room, where the psychiatrist sends service users for filling the recovery plans.
Activity 2 | Collect and Collate information to be disseminated at the enquiry table | 21st August, 2015 | 27th August, 2015 |  |  | Complete |  |  | Sit with the persons responsible in collating this information | 7
Activity 3 | Choose a permanent and visible place in the facility to place the enquiry table |  | 25th August, 2015 |  |  | Complete |  |  |  | 2
Activity 4 | Get infrastructure ready - table, chair, sign board, stationery material |  | 25th August, 2015 |  |  | Complete |  |  |  | 2
Activity 5 | Identify users who could work at the enquiry table and prepare a list |  | 25th August, 2015 |  |  | Complete - the PSVs |  |  | To initially train PSVs who could then train others | 4
Activity 6 | Train the users in working at the enquiry table | 27th August, 2015 | 5th September, 2015 |  |  | Ongoing |  |  | Training to be supported and conducted by the peer support volunteers | 4
Activity 7 | Make a plan for the expenditure related to the activities in the facility - in which activities the money will be spent | 21st August, 2015 | 27th August, 2015 |  |  | Complete |  |  | The plan is to prepare such a budget, as and when activities are conducted | 3
Activity 8 | Contact external bodies for funding related to this activities and other activities of the project - starting from the records of the donors maintained at the hospital |  | 30th August, 2015 |  |  | Ongoing |  |  | There is a record of the donors maintained at the hospital already. This will be expanded by adding more contact numbers and communicating the needs list to the donors. | 3
Strategy 2 | Ensuring staff involvement in the activities of the hospital and the improvement plan | Start Date | End Date | Responsible members | Budget | Status of the activity | New deadline |  | Plan for achieving the new deadline |  |  | Plan for sustainability
Activity 1 | To install a board at the entrance of the facility, consisting of updates regarding activities planned and conducted in the hospital and inviting suggestions |  | 30th June, 2015 |  |  | Complete |  |  | Helping the staff understand the need for having such a board | 3 |  | The board has been installed and is used regularly.
Activity 2 | Monthly meetings with the entire staff body for discussion of activities planned by the Challengers and a discussion of grievances - First saturday of every month | Activity conducted every month |  |  |  | Ongoing |  |  |  | 38 |  | Meetings are held on a monthly basis. These are convened by the staff nurse in charge, who reminds the administrative office and the head of the facility to issue an official order.
Activity 3 | Placement of a "suggestion box", a week before the meeting - inviting the staff members to express suggestions and grievances, anonymously | Activity achieved |  |  |  | Ongoing | 5th March, 2016 |  | Sitting with the core team and inviting suggestions from the staff body regarding making such a mechanism more active. Involving more persons responsible for ensuring that the suggestions and grievances are heard. | 8 |  | Suggestions are invited in an anonymous manner at the meetings itself. The staff members are given some time to think of their suggestions/complaints and put them in a box that is circulated, in an anonymous manner. These issues are then taken up for discussion.
Area for improvement: Standard 2.3 - Treatment and psycho-social rehabilitation; Standard 5.1 - Housing and financial resources
Strategy 1 | Creating networks with donors | Start Date | End Date | Responsible members | Budget | Status of the activity | New deadline |  | Plan for achieving the new deadline |  |  | Plan for sustainability
Activity 1 | Make a list with the name and types of donors - some are already available in the "diet register" | 1st August, 2015 | 3rd August, 2015 |  |  | Complete |  |  |  | 2
Activity 2 | Make a list of the provisions and facilities needed at the hospital | 1st August, 2015 | 3rd August, 2015 |  |  | Complete |  |  | To sit with the person responsible and prepare such a list | 2
Activity 3 | Get their contact numbers | 1st August, 2015 | 3rd August, 2015 |  |  | Complete |  |  |  | 2
Activity 4 | Contact them personally or on the phone to communicate the needs of the hospital | 3rd August, 2015 | 10th August, 2015 |  |  | ongoing | The activity will be ongoing as and when the needs arise |  | To begin working on this activity, after the above mentioned activities are achieved. | 3
Activity 5 | Plan a visit of the donors to the hospital - familiarise the donors with the needs and the activities of the hospital | 10th August, 2015 | 17th August, 2015 |  |  | Complete |  |  | TO begin working on this activity, after the above mentioned activities are achieved. | 10
Activity 6 | Acknowledge (after we have received support) the support provided by the donors by publicising their work in the newspapers, on the board, through pictures and letter of acknowledgement | 20th August, 2015 |  |  |  | Ongoing |  |  | A Donation committee has been formed. They are expected to meet and decide a reward process by the end of this week - 3rd January, 2015 | 5
Strategy 2 | Creating networks with NGOs | Start Date | End Date | Responsible members | Budget | Status of the activity | New deadline |  | Plan for achieving the new deadline
Activity 1 | Prepare a list of NGOs in Kutch and nearby areas - related or not related to mental health work | 1st August, 2015 | 3rd August, 2015 |  |  | Complete |  |  |  | 2
Activity 2 | Get their contact details | 1st August, 2015 | 3rd August, 2015 |  |  | Complete |  |  |  | 2
Activity 3 | Collect information about the work done by these NGOs | 3rd August, 2015 | 10th August, 2015 |  |  | Complete |  |  |  | 2
Activity 4 | Prepare an agenda for meeting with all the NGO heads and communicating with them | 10 th August, 2015 | 15 th August, 2015 |  |  | Complete |  |  | To plan and conduct this visit as and when the communicate their interest | 10
Activity 5 | Prepare a presentation about the services provided by the hospital, work done in the past and the daily challenges faced | 10th August, 2015 | 15th August, 2015 |  |  | Complete |  |  | A Donation committee has been formed. They are expected to meet and decide a reward process by the end of this week - 3rd January, 2015 | 10
Activity 6 | Acknowledge (after we have received support) the support provided by the donors by publicising their work in the newspapers, on the board, through pictures and letter of acknowledgement | 20th August, 2015 |  |  |  | This activity will be ongoing and when support from an NGO is received |  |  | A Donation committee has been formed. They are expected to meet and decide a reward process by the end of this week - 3rd January, 2015 | 5
Strategy 3 | Pre admission orientation | Start date | End date | Persons responsible | Budget | Status of the activity | New Deadline |  | Plan for achieving the new deadline
Activity 1 | Collect and collate information on essential medication, effects and side effects of medicines | 5th September, 2015 | 15th September, 2015 |  |  | Complete |  |  | To coordinate among the researchers and work on this activity once the other activities have been worked on.
Activity 2 | Have the list of essential medication on display outside the pharmacy | 1st September, 2015 | 5th September, 2015 |  |  | Complete |  |  | To begin working on this activity as and when the above mentioned activities have been achieved.
Activity 3 | Place a board in the out-patient and in-patient facility about the services available in the hospital (use the information on a board already present in the facility and not being used) | 1st September, 2015 | 10th September, 2015 |  |  | Ongoing - material for the board finalised, sent out for printing | 10th April, 2016 |  | The plan is to get this board painted along with the other boards at the facility
Activity 4 | Prepare a pamphlet on the facilities of the hospital, and the common effects and side effects of medication | 5th September, 2015 | 15th September, 2015 |  |  | Ongoing - the process of collating information and contacting possible funders has been initiated | 10th April, 2016 |  | Coordinate with the other researchers and collate this information to make a uniform pamphlet to be distributed across all the sites.
Activity 5 | Train the nursing and attendant staff regarding the pre-admission process - the nature of information to be given to users, how to handle crisis situations | 10th September, 2015 | 20th September, 2015 |  |  | Ongoing | 10th April, 2016 |  | TO begin working on this activity as and when the above mentioned activities have been achieved.
Activity 6 | Have two persons responsible for pre-admission orientation, according to shifts | 20th September, 2015 |  |  |  | Ongoing - policy for pre - admission orientation has been finalised | 15th April, 2016 |  | The person responsible for conducting the pre - admission orientation has already been identified - communications master trainers would be conducting this activity on a regular basis. One of them has a regular shift (9 am to 1 pm and 4 pm to 6 pm) duty at the facility.
Strategy 4 | Implementing a plan for users during their stay in the hospital | Start date | End date | Persons responsible | Budget | Status of the activity | New Deadline |  | Plan for achieving the new deadline
Activity 1 | Prepare a list of staff and allott 5 users to a staff member | 21st September, 2015 | 25 th September, 2015 |  |  | Complete |  |  |  | 2
Activity 2 | List the content to be included in individual treatment plans | 21st September, 2015 | 30th September, 2015 |  |  | Pending | 10th April, 2016 |  | Sit with the core team nurses, the psychiatrist, and the medical to understand treatment plans - integrate the recovery plan, OT sheet and information regarding support groups in the plan
Activity 3 | Orient the staff towards the structure of a treatment plan and its content | 1st October, 2015 | 10th October, 2015 |  |  | Pending | 10th April, 2016
Activity 4 | Train the staff and integrate the recovery plan into the treatment plan | 5th June, 2015 | 15th July, 2015 |  |  | Pending | 10th April, 2016
Activity 5 | Regularise physical examination and follow up | 30th September, 2015 |  |  |  | Complete |  |  |  | 3
Activity 6 | Prepare a revised intake sheet | 21st September, 2015 | 30th September, 2015 |  |  | Complete |  |  | Sit with the doctor in charge to prepare a sheet, and have persons responsible for filling in the sheet.
Activity 7 | Orient the staff towards the progress tracking sheet, attached to the in-patient files | 1st October, 2015 | 10th October, 2015 |  |  | Complete |  |  | To integrate this information in the program for developing an understanding of mental illness among the staff members
Activity 8 | Track the progress of the users - using the tracking sheet | 30th September, 2015 |  |  |  | Pending | 10th April, 2016
Activity 9 | Use information regarding progress in treatment to provide leisure activities and skills training according to the preferences of the users | 10th October, 2015 |  |  |  | Pending | 10th April, 2016 |  | Plan is to integrate this into the OT activities.
Activity 10 | Have bi - monthly group discussions on effects and side - effects of medication, hygiene related issues, sex education, health awareness and education etc. with the users | 10th October, 2015 |  |  |  | Ongoing - process initiated in the OT |  |  | Have the PSVs conduct this discussion
Activity 11 | Have monthly case discussions | 10th October, 2015 |  |  |  | Pending |  |  |  | 10
Activity 12 | Prepare a database of NGOs, and make attempts towards discharging the users, based on their treatment progress | 20th August (prepared) |  |  |  | Complete
Activity 13 | Develop a policy related to individual treatment plans at the facility | 10th October, 2015 |  |  |  | Complete
Strategy 5 | Developing a discharge plan | Start date | End date
Activity 1 | Maintain a contact register of the user and caregivers | 10th October, 2015 |  |  |  | Complete |  |  |  | 2
Activity 2 | Prepare a database of NGOs providing educational and employment opportunities to service users | 20th August (prepared) |  |  |  | Complete |  |  |  | 2
Activity 3 | Collect information for providing psycho-education | 10th October, 2015 | 15th October, 2015 |  |  | Complete
Activity 4 | Prepare a pamphlet with information useful for the users on discharge and emergency contact numbers | 10th October, 2015 | 15th October, 2015 |  |  | Pending | 10th April, 2016
Activity 5 | Create a policy regarding discharge plan | 15th October, 2015 |  |  |  | Complete
Strategy 6 | Post discharge follow up | Start date | End date
Activity 1 | Using the contacts in the register to make regular phone calls | 15th October, 2015 |  |  |  | Ongoing
Activity 2 | Encourage users to join support group, and visit the hospital regularly | 15th October, 2015 |  |  |  | Ongoing |  |  | To make the process more regularised and not in the form of an informal call.
Area for improvement: Standard 3.3 - Support to exercise legal capacity
Strategy 1 | To provide information regarding rights of the service users | Start date | End date | Persons responsible | Budget | Status of the activity | New deadline |  | Plan for meeting the new deadline
Activity 1 | Provide training to staff, users and caregivers regarding Human rights - to be covered by QualityRights. Additionally, training to be conducted with the entire staff body, locally. | 15th August, 2015 | 15th October, 2015 |  |  | Complete |  |  |  | 41
Activity 2 | Compile material on human rights to be delivered to the users on entry into the facility. Integrate this material into the pre-admission counselling process. | 30th August, 2015 |  |  |  | Complete |  |  | To sit with the human rights master trainers and compile information to be put up on the board. Get the board done along with the other boards painted at the facility | 3
Activity 3 | Prepare a pamphlet to be distributed to the users in the OPD and the in-patient facility. | 15th october 2015 | 20th October, 2015 |  |  | Ongoing - the pamphlet has been prepared - needs to be sent out to printing | 10th April, 2016 |  | To begin working on this activity along with the information on effects and side effects | 4
Activity 4 | Prepare a display board with information regarding rights within the OPD and the in-patient facility. | 20th October, 2015 |  |  |  | Ongoing - the material has been collected, the board to be printed and put up on display | 10th April, 2016 |  | To get the board painted along with the other boards at the site. | 4
Area for improvement: Standard 4.5 - Mechanisms to prevent abuse torture and inhuman treatment
Strategy 1 | Develop a complaint mechanism | Start date | End date | Persons responsible | Budget | Status of the activity | New Deadline |  | Plan for meeting the new deadline
Activity 1 | Get suggestions from the staff members regarding the nature of complaint mechanisms, while discussing complaing systems during training sessions | 6th August, 2015 | 26th August, 2015 |  |  | Complete |  |  |  | 41
Activity 2 | Get suggestions from the caregivers regarding the nature of complaint mechanisms, during caregiver meetings or in the OPD. | 10th September, 2015 | 19th September, 2015 |  |  | Complete |  |  |  | 12
Activity 3 | Conducting interviews with the users about the nature of complaint mechanisms ideal at the facility | 1st September, 2015 | 15th September, 2015 |  |  | Complete |  |  | To interact with as many users as possible for this activity | 5
Activity 4 | Collate the suggestions and feed them back to the core team | 20th September, 2015 | 25th September, 2015 |  |  | Complete |  |  |  | 8
Activity 5 | Contact members for developing an "external body" for managing complaints - for example, the visitor's committee | 26th September, 2015 | 10th October, 2015 |  |  | Ongoing |  |  |  | 9
Activity 6 | Elect a complaint management team from the facility - for collating and documenting complaints, as well as for investigation into the complaints - reporting to the external body | 26th September, 2015 | 10th October, 2015 |  |  | Ongoing
Activity 7 | Conduct a staff meeting to elect the body from the staff | 26th September, 2015 | 10th October, 2015 |  |  | Ongoing
Activity 8 | Document and make policies about the internal management team and the external body - their roles, responsibilities and powers | 15th September, 2015 | 10th October, 2015 |  |  | Ongoing
Activity 9 | Have a monthly round of managing and reporting complaints | 13 th October, 2015 onwards |  |  |  | Pending
Activity 10 | Choose an anonymous location (accessible to all) for managing complaints | 26th September, 2015 | 10th October, 2015 |  |  | Complete | 15th December, 2015
Activity 11 | Emplace complaint boxes and material - paper and pens, in the anonymous locations | 26th September, 2015 | 10th October, 2015 |  |  | Pending | 20th March,2016
Activity 12 | Inform the staff, caregivers and users about the new complaint mechanism in place | 10th october, 2015 | 12th october, 2015 |  |  | Pending | 10th April, 2016
Activity 13 | Invite monthly feedback regarding the management of such a mechanism from the staff, users and caregivers - suggestions for improvement, through a group discussion | 1st November, 2015 onwards |  |  |  | Pending

## Standard Sheet
Area for Improvement: (Put in the standard number and name- in the same format as QRT)
Strategy: (Add the strategy) | Start Date | End Date | Responsible Members | Budget | Status | New Deadline | Explanation for not meeting the deadline | Proposed Plan for meeting new deadlines | No of people in the meeting | Name & designation of the people who attended the meeting
Activity 1 | Date/Month/'15 | Date/Month/'15 | Full names of the members | INR: 0.00 | Complete/Pending
(Describe the Activity) Arrange an all staff meeting to discuss the activity and the plan ahead to bring the users out | 28 April'15 | 29 April'15 |  | INR 200 | Complete
Strategy: (Add the strategy)
Activity 2
(Describe the Activity)